## Summary
NLH-CA-017
| Original Analysis | Revised Analysis
Minimum | -100% | -100%
Maximum | 947.9% | 1884%
Variance | 35.87% | 86.98%
Standard Deviation | 59.89% | 93.26%
Average | 1.36% | 6.885%
Count | 591 | 710
Lower Standard Deviation | -58.53% | -86.38%
Upper Standard Deviation | 61.25% | 100.1%
Notes:
1. This analysis contains data for projects that have closed from 2017-2025. As a result, the criteria for excluding projects from the analysis has evolved over time to exclude projects/ programs that were not reflective of Capital Budget Application Estimation Accuracy.
2. Allowance for Unforeseen projects have been excluded from the Revised Statistical Analysis.
3. Sign Convention: Positive Variance = Actual costs are higher than budget. Negative Variance = Actuals costs are lower than budget.
4. Project/ Program titles may not be exactly the same as those denoted in the Capital Budget Application and may contain some abbreviations due to character restrictions in Newfoundland and Labrador Hydro’s system.
5. This analysis includes projects that closed in each of the applicable years.

## Original Analysis Data
Project # | Year Started | Year Closed | JDE Title | CBA / CAPEX Title | Budget | Actual Cost | Var $ | Var %
13251602 | 2016 | 2017 | Replace Surge Arrestors | Replace Surge Arrestors - Various Sites | 197.4 | 175.0706 | -22.3294 | -11.31%
13251606 | 2016 | 2017 | Upgrd Digital Fault Recorders | Upgrade Digital Fault Recorders - Various Sites | 502.5 | 550.0368 | 47.5368 | 9.46%
13251613 | 2016 | 2017 | Upgrade Warehouse Lighting-BIF | Upgrade Warehouse Lighting - Bishop's Falls | 195.6 | 121.6659 | -73.9341 | -37.8%
14301601 | 2016 | 2017 | CHD-Upgrd TS Mobile Substation | Upgrade Terminal Station for Mobile Substation - Cow Head | 484.7 | 387.3143 | -97.3857 | -20.09% |  | Values
13251708 | 2017 | 2017 | HRD-Upgrd Alum Supp Structures | Upgrade Aluminum Support Structures - Holyrood | 352.9 | 190.8158 | -162.0842 | -45.93% | Year Closed | Sum of Budget | Sum of Actual Cost | Sum of Var $
13251715 | 2017 | 2017 | VAR-Upgr Equipment Foundations | Upgrade Equipment Foundations - Various Sites | 389.2 | 245.336 | -143.864 | -36.96% | 2017 | 51531.3 | 48135.7016 | -3395.5984
12421614 | 2016 | 2017 | Hydrometeorological Equipment | Install Hydrometeorological Equipment - Various Sites | 314.1 | 183.3448 | -130.7553 | -41.63% | 2018 | 128434.9 | 114703.0601 | -13731.8399
12811603 | 2016 | 2017 | HLK-Rplc Cntrl/Comm Room A/C | Replace Control Room/Communications Room Air Conditioning - Hinds Lake | 94.3 | 96.4168 | 2.1168 | 2.245% | 2019 | 391099.1293 | 381220.7395 | -9878.3898
12901501 | 2015 | 2017 | CAT-Stat.Serv BRKR Replacement | Replace Station Service Breakers - Cat Arm | 1008.3 | 1036.8004 | 28.5004 | 2.827% | 2020 | 87133.8628 | 65911.4278 | -21222.435
12931509 | 2015 | 2017 | BDE-Upgrade Equipment Doors | Upgrade Equipment Doors - Various Sites | 348.5 | 412.7652 | 64.2652 | 18.44% | 2021 | 146289.126 | 133293.9097 | -12995.2163
12931514 | 2015 | 2017 | EBBE-Accommodations/SepticSyst | Replace Accommodations and Septic System - Ebbegunbaeg | 1550.8 | 2043.4628 | 492.6628 | 31.77% | 2022 | 62943.075 | 59177.8435 | -3765.2315
12931606 | 2016 | 2017 | BDE-Rplc Station Service XFMR | Replace PH1 Station Service Transformer - Bay d'Espoir | 401.2 | 533.1079 | 131.9079 | 32.88% | 2023 | 93835.5952 | 89924.7251 | -3910.8701
12971702 | 2017 | 2017 | HRD-Upgrade Access Roads | Upgrade Holyrood Access Road - Holyrood | 1162.6 | 825.6932 | -336.9068 | -28.98% | 2024 | 56323.1703 | 61026.144 | 4702.9737
12421601 | 2016 | 2017 | Rplc Battery Banks & Chargers | Replace Battery Banks and Chargers - Various Sites | 881.6 | 645.2465 | -236.3535 | -26.81% | 2025 | 38155.873 | 45816.3285 | 7660.4555
12421602 | 2016 | 2017 | Rpl MDR4000 MicrowaveRadioEast | Replace MDR 4000 Microwave Radio East - Various Sites | 1170.5 | 1154.4371 | -16.0629 | -1.372% | Grand Total | 1055746.0316 | 999209.8798 | -56536.1518
12421603 | 2016 | 2017 | Replace UPS Systems-HydroPlace | Replace UPS Systems - Hydro Place | 889.8 | 978.5309 | 88.7309 | 9.972%
12421608 | 2016 | 2017 | MDR,HVY-Terminal Station A/C's | Replace Air Conditioners - Various Sites | 191.9 | 196.2608 | 4.3608 | 2.272%
12421613 | 2016 | 2017 | Powerline Carrier-TL214/TL239 | Replace Powerline Carrier - Various Sites | 836.8 | 762.11 | -74.69 | -8.926% | Groupings
12421615 | 2016 | 2017 | SBH-Upgrd Telecontrol Facility | Upgrade Telecontrol Facilities - Sandy Brook Hill | 564 | 615.2495 | 51.2495 | 9.087%
13321601 | 2016 | 2017 | HWD/SVL-Replace Fuel Piping | Replace Fuel Piping - Hardwoods and Stephenville | 311.8 | 267.8725 | -43.9275 | -14.09% | -99.9% | -90%
13321691 | 2016 | 2017 | HWD&SVL GasGen EngineRefurbish | Refurbish Gas Generator Engines - Hardwoods and Stephenville | 3047.1 | 2968.2856 | -78.8144 | -2.587% | -89.9% | -80%
13331405 | 2014 | 2017 | Ugd D.Plt ProdDataCollectEqt | Upgrade Diesel Plant Production Data Collection Equipment-Various | 819.4 | 842.7319 | 23.3319 | 2.847% | -79.9% | -70%
13331603 | 2016 | 2017 | GYR-Instl Variable Freq.Drives | Install Variable Frequency Drives - Grey River | 169.9 | 257.4728 | 87.5728 | 51.54% | -69.9% | -60%
13461605 | 2016 | 2017 | BIF-Replace Service Bldg Roof | Replace Roof on Service Building - Bishop's Falls | 612.8 | 616.3406 | 3.5406 | 0.5778% | -59.9% | -50%
14011604 | 2016 | 2017 | NAN,CTW-Fire Suppression Systm | Install Fire Protection Systems - Cartwright and Nain | 4407.1 | 3652.201 | -754.899 | -17.13% | -49.9% | -40%
14011606 | 2016 | 2017 | Upgrade Transformers POV & CTW | Upgrade Transformer Systems - Postville and Cartwright | 465.2 | 465.1889 | -0.01112 | -0.00239% | -39.9% | -30%
14361601 | 2016 | 2017 | LAL-Additions for Load Growth | Additions for Load Growth - L'anse au Loup | 4175.6 | 3710.7617 | -464.8383 | -11.13% | -29.9% | -20%
13491603 | 2016 | 2017 | Replace Aircraft Makers-TL228 | Replace Aircraft Markers at Grand Lake Crossing - TL228 | 1567.9 | 1486.4391 | -81.4609 | -5.196% | -19.9% | -10%
14281692 | 2016 | 2017 | TL227 & L1 Upgrds Sally's Cove | TL 227 Distribution Line Sally's Cove L1 | 2250 | 1894.4776 | -355.5224 | -15.8% | -9.9% | -0.1%
13331701 | 2017 | 2017 | Overhaul Diesel Engines | Overhaul Diesel Engines - Various Sites | 2095.9 | 1619.7798 | -476.1202 | -22.72% | 0% | 9.9%
12961701 | 2017 | 2017 | HRD-Overhaul Turb.Valves Unt2 | Overhaul Turbine Valves Unit 2 - Holyrood | 2302.1 | 2496.5952 | 194.4952 | 8.449% | 10% | 19.9%
12961706 | 2017 | 2017 | Purch Capital Spares-Holyrood | Purchase Capital Spares Holyrood | 321.5 | 338.322 | 16.822 | 5.232% | 20% | 29.9%
12961707 | 2017 | 2017 | HRD-Cond.Asses.& Misc.Upgrds | Condition Assessment and Miscellaneous Upgrades - Holyrood | 2437.3 | 3058.1091 | 620.809 | 25.47% | 30% | 39.9%
12961702 | 2017 | 2017 | HRD-O/H U3 CoolWaterPump-West | HRD - Major Overhaul: Unit 3 Cooling Water Pump West | 210.8 | 196.0386 | -14.7614 | -7.003% | 40% | 49.9%
12961703 | 2017 | 2017 | HRD-O/H U3 ExtractPump North | HRD - Major Overhaul: Unit 3 Extraction Pump North | 142.9 | 191.3764 | 48.4764 | 33.92% | 50% | 59.9%
12961704 | 2017 | 2017 | HRD-O/HU2 BoilerFeedPump-West | HRD - Major Overhaul Unit 2 Boiler Feed Pump West | 279.3 | 273.901 | -5.399 | -1.933% | 60% | 69.9%
13251718 | 2017 | 2017 | Replace Surge Arrestors | Replace Surge Arrestors - Various Sites | 373.4 | 236.5843 | -136.8157 | -36.64% | 70% | 79.9%
14111702 | 2017 | 2017 | STA-Replace Fuel Tank 22E | Replace Fuel Tank 22E - St. Anthony | 199.8 | 138.973 | -60.827 | -30.44% | 80% | 89.9%
13251710 | 2017 | 2017 | Upgrd Off.Facil/Cntrl Bldgs | Upgrade Office Facilities & Control Buildings - Various Sites | 2197.3 | 1815.2033 | -382.0967 | -17.39% | 90% | 99.9%
13251711 | 2017 | 2017 | Upgrade Line Depots-Various | Line Depot Condition Assessment and Refurbishment Program - Various Sites | 1458.8 | 689.3875 | -769.4125 | -52.74%
13461706 | 2017 | 2017 | Install Fall Protection Equip | Install Fall Protection Equipment - Various Sites | 194.7 | 161.2649 | -33.435 | -17.17%
13331703 | 2017 | 2017 | VAR-Inspect Fuel Storage Tanks | Inspect Fuel Storage Tanks - Various Sites | 1058.8 | 717.2581 | -341.5419 | -32.26%
14011602 | 2016 | 2017 | POV-Additions for Load Growth | Additions for Load Growth - Postville - Black Tickle | 1453.8 | 881.7762 | -572.0238 | -39.35%
13251709 | 2017 | 2017 | GFL,BUC-Purch Backup Diesel SS | Purchase Backup Diesel For Station Service - Grand Falls and Buchans | 188.9 | 149.274 | -39.626 | -20.98%
20081710 | 2017 | 2017 | Replace Roof - Hydro Place | Replace Roof - Hydro Place | 923.4 | 503.5026 | -419.8974 | -45.47%
13501705 | 2017 | 2017 | Var-Install Demand Metering | Install Demand Metering - Various Sites | 89.7 | 73.4013 | -16.2987 | -18.17%
12931704 | 2017 | 2017 | BDE-PublicSafetyDams/Waterways | Upgrade Public Safety Around Dams and Waterways - Bay d'Espoir | 489 | 355.4848 | -133.5152 | -27.3%
12421704 | 2017 | 2017 | Rplc Network Communications Eq | Replace Network Communications Equipment - Various Sites | 199.3 | 228.6491 | 29.3491 | 14.73%
12421705 | 2017 | 2017 | Upgrade Site Facilities | Upgrade Site Facilities | 49 | 49.9137 | 0.9137 | 1.865%
13491708 | 2017 | 2017 | Perform WPLM Program | Wood Pole Line Management Program - Various Sites | 2404.1 | 3234.6081 | 830.5081 | 34.55%
13071701 | 2017 | 2017 | Purch Meters, Equip & Tanks | Purchase Meters and Metering Equipment - Various Sites | 198.8 | 273.866 | 75.066 | 37.76%
13251706 | 2017 | 2017 | Rplcmnt Due to In-Serv Failure | In-Service Failures - Various Sites | 1000 | 1437.207 | 437.207 | 43.72%
12421710 | 2017 | 2017 | Upgrd Access Roads-Microw Site | Upgrade Access Roads to Microwave Sites - Various Sites | 118.4 | 121.1352 | 2.7352 | 2.31%
12931709 | 2017 | 2017 | BDE-Rplc Floor Annunciators | Replace Floor Annunciator Panels - Bay d'Espoir | 46.8 | 45.4934 | -1.3066 | -2.792%
13251707 | 2017 | 2017 | Purch Capital Spares-Term Stns | Purchase Capital Spares - Terminal Stations | 495.8 | 397.8449 | -97.9551 | -19.76%
12901702 | 2017 | 2017 | CAT-Major OHaul.Inspection-U1 | Overhaul Turbine/Generators - Cat Arm | 305.4 | 334.111 | 28.711 | 9.401%
12791701 | 2017 | 2017 | Hydro Generation Tools & Equip | Purchase Tools and Equipment Less than $ 50,000 | 113.4 | 112.0489 | -1.3511 | -1.191%
13961703 | 2017 | 2017 | WAB-Replace Recloser | Replace Recloser - Wabush | 199.2 | 115.9747 | -83.2253 | -41.78%
13321703 | 2017 | 2017 | Purch Capital Spares-Gas Turb | Purchase Capital Spares - Gas Turbines | 185 | 161.2058 | -23.7942 | -12.86%
12981701 | 2017 | 2017 | Remove Safety Hazards-2017 | Remove Safety Hazards - Various Sites | 198.6 | 185.9109 | -12.6891 | -6.389%
12421707 | 2017 | 2017 | Purchase Test Equipment | Purchase Tools and Equipment less than $50,000 | 45.2 | 48.664 | 3.464 | 7.664%
13461711 | 2017 | 2017 | BF-Three Phase Construction | Three Phase Construction - Bishop's Falls | 49.6 | 43.2043 | -6.3957 | -12.89%
12851701 | 2017 | 2017 | BDE-Repl Powerhouse Lighting | Replace Powerhouse Lighting - Paradise River | 43.9 | 36.1856 | -7.7144 | -17.57%
12931712 | 2017 | 2017 | BDE-Repl Powerhouse#2 Lightin | Replace Powerhouse #2 Lighting - Bay d'Espoir | 48 | 46.1384 | -1.8616 | -3.878%
12971706 | 2017 | 2017 | Stage 1 Pumphouse Siding Repla | Stage 1 Pumphouse Siding Replacement - Holyrood | 49.9 | 51.8717 | 1.9717 | 3.951%
13491701 | 2017 | 2018 | Trans Line Upgrds-TL212& TL218 | Transmission Line Upgrades - TL212 and TL218 | 2511.5 | 1727.6704 | -783.8296 | -31.21%
12971601 | 2016 | 2018 | HRD-Powerhouse Envelope Upgrd | Upgrade Powerhouse Building Envelope - Holyrood | 6477.8 | 5640.8877 | -836.9123 | -12.92%
13251605 | 2016 | 2018 | Replace Disconnects 2016/2017 | Replace Disconnect Switches - Various Sites | 1967.8 | 1421.6373 | -546.1627 | -27.75%
13251716 | 2017 | 2018 | VAR-Repl Instrum Transformers | Replace Instrument Transformers - Various Sites | 1345.3 | 792.7631 | -552.5368 | -41.07%
14111703 | 2017 | 2018 | PHS-Replace Diesel Unit 2042 | Diesel Genset Replacements - Port Hope Simpson | 4374.3 | 2871.8409 | -1502.4591 | -34.35%
12931705 | 2017 | 2018 | Purch Capital Spares-Hydraulic | Purchase Capital Spares - Hydraulic | 487.4 | 629.5901 | 142.1902 | 29.17%
13251722 | 2017 | 2018 | VAR-Upgrade Power Transformers | Upgrade Power Transformers - Various Sites | 14559 | 9119.2081 | -5439.7919 | -37.36%
13321701 | 2017 | 2018 | SVL-Upgrd GasTurb Plt Life Ext | Gas Turbine Life Extension - Stephenville | 1353.2 | 593.922 | -759.278 | -56.11%
12841701 | 2017 | 2018 | USL-Inst Asset Health Mon Syst | Install Asset Health Monitoring System - Upper Salmon | 641.4 | 356.4498 | -284.9502 | -44.43%
13071702 | 2017 | 2018 | Purch Meter Calib Test Console | Purchase New Meter Calibration Test Console - Hydro Place | 196.9 | 209.3736 | 12.4736 | 6.335%
13251705 | 2017 | 2018 | OPD-Replace Power Transformers | Replace Power Transformers - Oxen Pond | 1147.6 | 648.3048 | -499.2952 | -43.51%
12421701 | 2017 | 2018 | Rplc Battery Banks & Chargers | Replace Battery Banks and Chargers - Various Sites (2017-2018) | 945.5 | 772.7428 | -172.7572 | -18.27%
12841702 | 2017 | 2018 | USL-Overhaul Main Gen Breaker | Refurbish Main Generator Breaker - Upper Salmon | 271.1 | 245.0667 | -26.0333 | -9.603%
13331702 | 2017 | 2018 | Auxiliary Upgrades | Diesel Plant Engine Auxiliary Upgrades - Various Sites | 1206.9 | 1126.6529 | -80.2471 | -6.649%
13491702 | 2017 | 2018 | Replace Insulators - TL227 | Replace Insulators - TL227 | 416.9 | 299.4214 | -117.4785 | -28.18%
12931708 | 2017 | 2018 | BDE-Inst Wind Mon Stn NSD SD-2 | Install Wind Monitoring Station North Salmon Dam SD-2 - Bay d'Espoir | 165.5 | 167.3131 | 1.8131 | 1.096%
12841601 | 2016 | 2018 | USL-Refurb Stat.Serv.WaterSyst | Refurbish Station Water System - Upper Salmon | 294.2 | 279.6762 | -14.5238 | -4.937%
12901701 | 2017 | 2018 | Water System Replacements | Water System Replacements - Bay d'Espoir and Cat Arm | 2553.8 | 1697.4616 | -856.3384 | -33.53%
13251303 | 2013 | 2018 | Rplace Instrument Transformers | Replace Instrument Transformers - Various Sites | 3668 | 3530.2062 | -137.7938 | -3.757%
13251714 | 2017 | 2018 | VAR-Install Frequency Monitors | Install Frequency Monitors - Various Sites | 157.8 | 126.3804 | -31.4196 | -19.91%
14011705 | 2017 | 2018 | CHT-Replace Diesel Unit 2034 | Diesel Genset Replacements - Charlottetown | 1432.5 | 1315.5202 | -116.9798 | -8.166%
13461705 | 2017 | 2018 | VAR-Install Pole Storage Ramps | Install Pole Storage Ramps - Various Sites | 816.4 | 477.7208 | -338.6791 | -41.48%
13251720 | 2017 | 2018 | VAR-Replace Insulators | Replace Insulators - Various Sites | 971.9 | 196.665 | -775.235 | -79.76%
14111701 | 2017 | 2018 | MSH-Rplc Automation Equipment | Replace Automation Equipment - Mary's Harbour | 1142 | 1047.8081 | -94.1919 | -8.248%
12931707 | 2017 | 2018 | BDE-Refurb Sump Lvl System PH2 | Refurbish Sump Level System for Powerhouse 2 - Bay d'Espoir | 303.2 | 230.7473 | -72.4527 | -23.9%
13321702 | 2017 | 2018 | HWD-Upgrd GasTurb Plt Life Ext | Gas Turbine Life Extension - Hardwoods | 956.7 | 469.2565 | -487.4435 | -50.95%
13251719 | 2017 | 2018 | VAR-Install Fire Protection | Install Fire Protection - Various Sites | 926.7 | 794.994 | -131.706 | -14.21%
12931703 | 2017 | 2018 | BDE-Upgrd Ventilation PH1&2 | Upgrade Ventilation in Powerhouse 1 and 2 - Bay d'Espoir | 997.9 | 685.6245 | -312.2755 | -31.29%
20081611 | 2016 | 2018 | Replace A/C Units 8 & 14-HYP | Replace Air Conditioning Units 8 and 14 - Hydro Place | 264.1 | 276.4231 | 12.3231 | 4.666%
13331602 | 2016 | 2018 | Replc Human Machine Interfaces | Upgrade Human Machine Interface - Various Sites | 434 | 458.0087 | 24.0087 | 5.532%
13251612 | 2016 | 2018 | Fire Protection-230kV TS,BDE | Install Fire Protection in 230 kV Stations - Bay d'Espoir | 766 | 592.8697 | -173.1303 | -22.6%
12931608 | 2016 | 2018 | BDE-UG SV Bypass Valve Unit1&2 | Replace Spherical By-Pass Valves Units 1 and 2 - Bay d'Espoir | 351.5 | 398.6093 | 47.1093 | 13.4%
13501703 | 2017 | 2018 | 2017/18-Distribution Upgrades | Distribution Upgrades - Various Sites | 1195.1 | 994.0176 | -201.0824 | -16.83%
13251723 | 2017 | 2018 | VAR-Cable Upgrades | Cable Upgrades - Various Sites | 932.1 | 664.7091 | -267.3909 | -28.69%
13501704 | 2017 | 2018 | BWT-Instl RecloserRemote Cntrl | Install Recloser Remote Control - Bottom Waters | 465.7 | 489.1726 | 23.4726 | 5.04%
13251713 | 2017 | 2018 | Replc Electromechanical Timers | Replace Electromechanical Timers - Various Sites | 197.8 | 263.2126 | 65.4126 | 33.07%
13491601 | 2016 | 2018 | 230kV TL266 Constr-SOP to HWDs | Construct 230 kV Transmission Line - Soldiers Pond to Hardwoods | 26560.9 | 26707.1371 | 146.2371 | 0.5506%
12421715 | 2017 | 2018 | MMH-Upgrd Telecontrol Facility | Upgrade Telecontrol Facilities - Mary March Hill and Blue Grass Hill | 757.1 | 623.2868 | -133.8132 | -17.67%
14111504 | 2015 | 2018 | Rplc Programmable Logic Cntrlr | Replace Programmable Logic Controllers - Various Sites | 958 | 1359.9236 | 401.9236 | 41.95%
12091701 | 2017 | 2018 | Inst AutoMeterReading-HVY | Install Automated Meter Reading - Happy Valley | 1970.2 | 1790.4916 | -179.7084 | -9.121%
13501603 | 2016 | 2018 | 2016/17-Distribution Upgrades | Upgrade Distribution Systems - Various Sites | 6635.9 | 6408.156 | -227.744 | -3.432%
12091601 | 2016 | 2018 | Inst AutoMeterReading-Lab.West | Install Automated Meter Reading - Labrador West | 967.2 | 1408.3221 | 441.1221 | 45.61%
13251603 | 2016 | 2018 | Replace Protection Relays-VAR | Replace Protective Relays - Various Sites | 1857 | 3314.7093 | 1457.7093 | 78.5%
12971703 | 2017 | 2018 | HRD-Upgrd UndrGrnd Plnt Drnage | Upgrade Underground Plant Drainage System - Holyrood | 923.1 | 1890.807 | 967.707 | 104.8%
13961803 | 2018 | 2018 | HVY-Additons for Load Growth | Additions for Load Growth - Happy Valley | 505 | 222.4552 | -282.5448 | -55.95%
13321801 | 2018 | 2018 | Purch Capital Spares-Gas Turb | Purchase Capital Spares - Gas Turbines | 626.9 | 534.6717 | -92.2283 | -14.71%
12981801 | 2018 | 2018 | Remove Safety Hazards-2018 | Remove Safety Hazards - Various | 199.4 | 166.3368 | -33.0632 | -16.58%
13461806 | 2018 | 2018 | Install Fall Protection Equip | Install Fall Protection Equipment - Various | 46.7 | 40.0556 | -6.6444 | -14.23%
13331801 | 2018 | 2018 | Overhaul Diesel Engines | Overhaul Diesel Units - Various Sites | 2852.4 | 2028.9873 | -823.4127 | -28.87%
13071801 | 2018 | 2018 | Meters and Metering Equipment | Purchase Metering and Metering Equipment - Various Sites | 198.5 | 236.6416 | 38.1416 | 19.21%
14011801 | 2018 | 2018 | Additions Load Growth-MAK,RIG | Additions for Load Growth - Makkovik and Rigolet | 730.1 | 301.9776 | -428.1224 | -58.64%
13251801 | 2018 | 2018 | Rplcmnt Due to In-Serv Failure | Terminal Station In-Service Failures | 1000 | 2268.9446 | 1268.9446 | 126.9%
13251802 | 2018 | 2018 | Var-Replace Surge Arrestors | Replace Surge Arrestors - Various Sites | 361.8 | 94.7661 | -267.0339 | -73.81%
13251803 | 2018 | 2018 | HRD-Upgrd Alum Supp Structures | Upgrade Aluminum Support Structures - Holyrood | 287.6 | 143.188 | -144.412 | -50.21%
13251805 | 2018 | 2018 | VAR-Upgr Equipment Foundations | Upgrade Terminal Station Equipment Foundations - Various Sites | 367 | 286.8618 | -80.1382 | -21.84%
12971802 | 2018 | 2018 | HRD-Install Raw Water Line | Install Raw Water Line - Holyrood | 1252.6 | 1528.5458 | 275.9458 | 22.03%
12961801 | 2018 | 2018 | HRD-In-Service Failures | Thermal In-Service Failures | 1250 | 2699.9082 | 1449.9082 | 116%
12961803 | 2018 | 2018 | HRD-Cond.Asses.& Misc.Upgrds | Condition Assessment and Miscellaneous Upgrades - Holyrood | 2749.6 | 3906.9442 | 1157.3442 | 42.09%
12421809 | 2018 | 2018 | Rplc TS Air Conditioner-BUC | Replace Air Conditioners - Various | 74.4 | 75.4694 | 1.0694 | 1.437%
13491808 | 2018 | 2018 | Perform WPLM Program | Wood Pole Line Management Program - Various Sites | 3532.9 | 3185.6229 | -347.2771 | -9.83%
13251806 | 2018 | 2018 | Upgrd Off.Facil/Cntrl Bldgs | Upgrade Office Facilities and Control Buildings - Various | 1180.6 | 955.8677 | -224.7323 | -19.04%
14111801 | 2018 | 2018 | Replc Human Machine Interfaces | Replace Human Machine Interface - St. Lewis | 280.8 | 242.5202 | -38.2798 | -13.63%
12421805 | 2018 | 2018 | Upgrade Site Facilities | Upgrade Site Facilities - Various | 49 | 46.8273 | -2.1727 | -4.434%
12421806 | 2018 | 2018 | Var-Replace Radomes | Replace Radomes - Various | 360.3 | 331.1138 | -29.1862 | -8.101%
12421808 | 2018 | 2018 | Upgrade RTUs | Replace RTUs - Various | 118.3 | 108.5157 | -9.7843 | -8.271%
12421804 | 2018 | 2018 | Rplc Network Communications Eq | Replace Network Communications Equipment - Various | 199.5 | 239.053 | 39.553 | 19.83%
12961802 | 2018 | 2018 | HRD-Pumps Overhaul | Overhaul Pumps - Holyrood | 438.3 | 302.6828 | -135.6172 | -30.94%
12961804 | 2018 | 2018 | HRD-U1 Generator Overhaul | Overhaul Unit 1 Generator - Holyrood | 1005 | 1060.5755 | 55.5755 | 5.53%
12961805 | 2018 | 2018 | HRD-U1 Turbine Valves O/Haul | Overhaul Unit 1 Turbine Valves - Holyrood | 2485.7 | 2247.747 | -237.953 | -9.573%
14011806 | 2018 | 2018 | PDR-Instl Sub-Surface Drainage | Install Sub-Surface Drainage System - Paradise River | 524.9 | 721.6131 | 196.7131 | 37.48%
12931803 | 2018 | 2018 | BDE-Hydraulic In-Serv Failures | Hydraulic In-Service Failures | 1251.1 | 452.4231 | -798.6769 | -63.84%
12931810 | 2018 | 2018 | BDE-PublicSafetyDams/Waterways | Public Safety Dams/Waterways - Bay d'Espoir | 394.7 | 344.1715 | -50.5285 | -12.8%
12791801 | 2018 | 2018 | Hydro Generation Tools & Equip | Hydro Generation Tools & Equip | 235.2 | 255.5992 | 20.3992 | 8.673%
12931815 | 2018 | 2018 | BDE-Refurbish Turbine Unit 2 | Refurbish Turbine Unit 2- BDE | 2520.7 | 1717.8404 | -802.8596 | -31.85%
12931816 | 2018 | 2018 | BDE-Cond.Monitoring Equipment | Condition Monitoring Equipment - BDE | 340.4 | 233.0878 | -107.3122 | -31.53%
13251809 | 2018 | 2018 | Upgrade Line Depots-Various | Line Depot Condition Assessment and Refurbishment - Various | 1233 | 1005.6007 | -227.3993 | -18.44%
12841801 | 2018 | 2018 | USL-O/Haul Turbine/Gen. Unit | Upper Salmon -Overhaul Turbine/Gen. Unit | 729.1 | 436.349 | -292.751 | -40.15%
12811801 | 2018 | 2018 | HLK-Replace Coolers | Replace Coolers - Hinds Lake | 516.8 | 429.8845 | -86.9155 | -16.82%
20081801 | 2018 | 2018 | Purchase Office Equipment-HYP | Replace Office Desk Chairs - Hydro Place | 90 | 26.2783 | -63.7217 | -70.8%
12931813 | 2018 | 2018 | BDE-Replace Control Cable PH1 | Replace Control Cable PH1 - BDE | 515.1 | 423.6075 | -91.4925 | -17.76%
12841802 | 2018 | 2018 | USL-Refurbish Accommodation | Refurbish Accommodation - USL | 74.5 | 51.4691 | -23.0309 | -30.91%
20081803 | 2018 | 2018 | Rplc Washroom Fixtures - HYP | Replace Washroom Fixtures - Hydro Place | 49.5 | 50.2615 | 0.76149 | 1.538%
12971804 | 2018 | 2018 | Stage 2 Emerg Diesel Gen Refur | Stage 2 Emergency Diesel Generator Refurbishment - Holyrood | 49.5 | 9.3213 | -40.1787 | -81.17%
12421807 | 2018 | 2018 | Purchase Test Equipment | Purchase Tools and Equipment less than $50,000 | 46 | 30.6813 | -15.3187 | -33.3%
20081804 | 2018 | 2018 | Security Improvements | Security Improvements - Hydro Place | 45.5 | 8.47 | -37.03 | -81.38%
12931817 | 2018 | 2018 | BDE - Penstock 3 Laser Scanning | Penstock 3 Laser Scanning - Bay d'Espoir | 46.3 | 31.3326 | -14.9674 | -32.33%
12931818 | 2018 | 2018 | BDE - Penstock 3 PressTransducer | Penstock 3 Press Transducer - Bay d'Espoir | 29.5 | 45.0508 | 15.5508 | 52.71%
20081805 | 2018 | 2018 | ParkingLot Access Imprvmts-HYP | Parking Lot Access Improvements - Hydro Place | 47.4 | 41.4768 | -5.9231 | -12.5%
20081806 | 2018 | 2018 | Main Breaker Replacement - HYP | Main Breaker Replacement-HYP | 18.4 | 17.5 | -0.9 | -4.891%
12421801 | 2018 | 2019 | Rplc PBX Telephone Systems | Replace PBX Phone Systems - Various | 1242.3 | 1379.6253 | 137.3253 | 11.05%
12421802 | 2018 | 2019 | Rplc MDR6000 Microwave Radios | Replace MDR 6000 Microwave Radio - Various | 1201 | 1233.0772 | 32.0772 | 2.671%
12421803 | 2018 | 2019 | Replace Tele-Protection TL261 | Replace Teleprotection - TL261 | 517.4 | 492.987 | -24.413 | -4.718%
12421810 | 2018 | 2019 | Rplc Battery Banks & Chargers | Replace Battery Banks and Chargers - Various | 937.9 | 903.1731 | -34.7269 | -3.703%
12931801 | 2018 | 2019 | InstlRemoteOper-SalmonR.Spillw | Install Remote Operation of Salmon Spillway - Bay d'Espoir | 2508.4 | 1818.4012 | -689.9988 | -27.51%
12931806 | 2018 | 2019 | Energy Efficiency Improvements | Energy Efficiency Improvements - Various Sites | 445.1 | 387.7348 | -57.3652 | -12.89%
12931811 | 2018 | 2019 | BDE-Instl Infrared Viewports | Install Infrared Viewports - VAR | 257.5 | 100.4698 | -157.0302 | -60.98%
12931814 | 2018 | 2019 | Instl Diesel Fuel Metering Dev | Install Diesel Fuel Metering Devices - BDE, PRV, VIC, GCL | 406.6 | 264.3975 | -142.2025 | -34.97%
12971801 | 2018 | 2019 | HRD-Upgrade Cranes and Hoists | Upgrade Cranes and Hoists - Holyrood | 380.6 | 345.1238 | -35.4762 | -9.321%
13251804 | 2018 | 2019 | VAR-Repl Instrum Transformers | Replace Instrument Transformers - Various Sites | 1181.1 | 670.5452 | -510.5548 | -43.23%
13251807 | 2018 | 2019 | Var-Upgrade Fault Recorders | Upgrade Fault Recorder System for 2018- Various Sites | 1026.9 | 636.9772 | -389.9228 | -37.97%
13251808 | 2018 | 2019 | Insulator Replacement -Var-M19 | Replace Insulators - Various Sites | 961.8 | 228.7218 | -733.0782 | -76.22%
13251811 | 2018 | 2019 | Perform Grounding Upgrades-HPD | Perform Grounding Upgrades - Various Sites | 293.8 | 373.9864 | 80.1864 | 27.29%
13251814 | 2018 | 2019 | Replc Disconnect Switches-M19 | Replace Disconnect Switches - Various Sites | 2458.5 | 1160.2887 | -1298.2113 | -52.81%
13251815 | 2018 | 2019 | Upgrade Power XFMR's (18-19) | Upgrade Power Transformers - Various Sites | 4829 | 2240.7098 | -2588.2902 | -53.6%
13251816 | 2018 | 2019 | Instl Fire Protection 230kV ST | Install Fire Protection in 230 kV Stations - Various Sites | 764.9 | 377.0449 | -387.8551 | -50.71%
13251817 | 2018 | 2019 | Rplc Transformer T1 - Buchans | Replace Transformer T1 - Buchans | 2335.1 | 2257.4354 | -77.6646 | -3.326%
13251820 | 2018 | 2019 | Purchase Mobile DC Power Systm | Purchase Mobile DC Power Systems | 966.5 | 658.2083 | -308.2917 | -31.9%
13321802 | 2018 | 2019 | HWD/SVL GT Equip Refurbishment | Gas Turbine Equipment Replacement and Refurbishment - Hardwoods and Stephenville | 1427.2 | 1197.2788 | -229.9212 | -16.11%
13501803 | 2018 | 2019 | 2018/19-Distribution Upgrades | Distribution System Upgrades - Various Sites | 3155 | 3219.6105 | 64.6105 | 2.048%
13501804 | 2018 | 2019 | EHW/BCX - RecloserRemote Cntrl | Install Recloser Remote Control - English Harbour West and Barachoix | 338.7 | 267.8528 | -70.8471 | -20.92%
14011807 | 2018 | 2019 | NAN-Rplc Second Contain Liner | Replace Secondary Containment System Liner - Nain | 3089.6 | 5180.7068 | 2091.1068 | 67.68%
20081802 | 2018 | 2019 | Upgrd Exterior Building - HYP | Upgrade Exterior of Building - Hydro Place | 665.9 | 579.2426 | -86.6574 | -13.01%
13401802 | 2018 | 2019 | Turbine Hot GasPath Inspection | Turbine Hot Gas Path Level 2 Inspection and Overhaul - Holyrood Gas Turbine | 11146.5 | 9829.5611 | -1316.9389 | -11.81%
12901601 | 2016 | 2019 | CAT-SpherValve/Def ServoMotors | Upgrade Work - Cat Arm | 1911.3 | 2570.9537 | 659.6537 | 34.51%
12931506 | 2015 | 2019 | BDE-Rplc PumpHouse/Equipment | Replace Pump House and Associated Equipment - Bay d'Espoir | 545.2 | 1051.0373 | 505.8373 | 92.78%
12931601 | 2016 | 2019 | BDE-Upgrade Site Facilities | Replace Site Facilities - Bay d'Espoir | 11981.3 | 13121.8682 | 1140.5682 | 9.52%
12931706 | 2017 | 2019 | BDE-Rplc Slip Rings Units 1-6 | Replace Slip Rings Units 1-6 - Bay d'Espoir | 472.3 | 301.1664 | -171.1336 | -36.23%
12931710 | 2017 | 2019 | Contr Structure Refurbishments | Control Structure Refurbishments | 2188.2 | 1927.5433 | -260.6567 | -11.91%
12931804 | 2018 | 2019 | BDE-Vent Chamber Replacement | Replace Vent Chambers - BDE | 380.7 | 199.3452 | -181.3548 | -47.64%
12971803 | 2018 | 2019 | HRD-Outbuilding Fire Detection | Install Fire Detection in Outbuildings - Holyrood | 198.6 | 158.5842 | -40.0158 | -20.15%
13251610 | 2016 | 2019 | Upgrade Data Alarm Mgmt-STB | Upgrade Data Alarm Systems - Various Sites | 308.5 | 361.4071 | 52.9071 | 17.15%
13251611 | 2016 | 2019 | Instl BRKR Fail Protection-TS | Install Breaker Failure Protection - Various Sites | 277 | 793.1427 | 516.1427 | 186.3%
13251701 | 2017 | 2019 | Replace Protective Relays-M18 | Replace Protective Relays - Various Sites | 1816.7 | 1839.3336 | 22.6336 | 1.246%
13251703 | 2017 | 2019 | HRD-Rplc Stn Serv Cable Feed | Replace 66 kV Station Service Feed - Holyrood | 1261.4 | 606.3337 | -655.0663 | -51.93%
13251704 | 2017 | 2019 | HRD-Replace Substation | Replace Substation - Holyrood | 1198 | 791.1895 | -406.8105 | -33.96%
13251712 | 2017 | 2019 | Instl BRKR Failure Protection | Install Breaker Failure Protection - Various Sites | 622.9 | 551.4077 | -71.4923 | -11.48%
13251717 | 2017 | 2019 | VAR-Replace Disconnects | Replace Disconnects - Various Sites | 3369.9 | 1188.4301 | -2181.4699 | -64.73%
13251721 | 2017 | 2019 | VAR-Perform Grounding Upgrades | Perform Grounding Upgrades - Various Sites | 1719.4 | 2626.3449 | 906.9449 | 52.75%
13461704 | 2017 | 2019 | Constr Storage Bldg MAK & CHT | Construct Storage Building - Makkovik and Charelottetown | 639.7 | 532.1648 | -107.5352 | -16.81%
14011802 | 2018 | 2019 | Upgd DieselPlt Ventilation-CTW | Upgrade Ventilation - Cartwright | 465.7 | 484.1515 | 18.4515 | 3.962%
14011805 | 2018 | 2019 | BKT-Inspect Fuel Storage Tanks | Inspect Fuel Storage Tanks - Black Tickle | 818.7 | 1044.4445 | 225.7445 | 27.57%
13491492 | 2014 | 2019 | 230kV TransmissionLine BDE-WAV | 230 kV Transmission Line - Bay d'Espoir to Western Avalon | 291658 | 286817.7549 | -4840.2451 | -1.66%
14011905 | 2019 | 2019 | Inspect Fuel Storage Tanks-GYR | Inspect Fuel Storage Tanks - Gray River | 203.1 | 317.0214 | 113.9214 | 56.09%
13881902 | 2019 | 2019 | Instl Pole Storage Ramps-WAB | Install Pole Storage Ramps - Wabush | 301.7 | 185.3397 | -116.3603 | -38.57%
13331901 | 2019 | 2019 | Overhaul Diesel Engines | Overhaul Diesel Units - Various | 2511.3 | 2154.4067 | -356.8933 | -14.21%
14011903 | 2019 | 2019 | Upgrd Diesel Plt Bldg-Ramea | Upgrade Diesel Plant Building - Ramea | 352.5 | 272.0043 | -80.4957 | -22.84%
14011906 | 2019 | 2019 | Upgrade Line Depots-Roddickton | Upgrade Line Depots - Roddickton | 344.7 | 313.4826 | -31.2174 | -9.056%
12981901 | 2019 | 2019 | Remove Safety Hazards-2019 | Remove Safety Hazards - Various | 197.5 | 210.8144 | 13.3144 | 6.741%
21881901 | 2019 | 2019 | HWD-Upgrade HMI and AVR | Upgrade HMI and AVR - Hardwoods | 685.9 | 493.8231 | -192.0769 | -28%
13071901 | 2019 | 2019 | Meters and Metering Equipment | Purchase Meters and Metering Equipment - Various | 196.4 | 178.181 | -18.219 | -9.276%
12421906 | 2019 | 2019 | Var-Replace Radomes | Replace Radomes - Various | 263.5 | 253.1481 | -10.3519 | -3.929%
12421903 | 2019 | 2019 | Rplc Tele-Protection TL202/206 | Replace Teleprotection - TL202 & TL206 | 196.8 | 225.7597 | 28.9597 | 14.72%
12421904 | 2019 | 2019 | Rplc Network Communications Eq | Replace Network Communications Equipment - Various | 189.5 | 180.4093 | -9.0907 | -4.797%
12421908 | 2019 | 2019 | Upgrade RTUs | Upgrade Remote Terminal Units - Various | 167.7 | 165.0186 | -2.6814 | -1.599%
12421905 | 2019 | 2019 | Upgrade Site Facilities | Upgrade Site Facilities - Various | 49.4 | 50.2554 | 0.85542 | 1.732%
12421907 | 2019 | 2019 | Purchase Test Equipment | Purchase Tools and Equipment less than $50,000 | 45.6 | 42.1151 | -3.4849 | -7.642%
13321902 | 2019 | 2019 | HWD/HVY-Constr Heated Storage | Construct Heated Storage for Spare Parts and Lube Oil - Hardwoods and Happy Valley | 49.8 | 61.9637 | 12.1638 | 24.43%
12951901 | 2019 | 2019 | GCL-Overhaul Turbine/Generator | Overhaul Turbine/Generator Unit - GCL | 562.2 | 503.6457 | -58.5543 | -10.42%
12791901 | 2019 | 2019 | Hydro Generation Tools & Equip | Purchase Tools and Equipment Less than $ 50,000 | 133.5 | 124.42 | -9.08 | -6.802%
12941901 | 2019 | 2019 | BDE-Refurbish Turbine Unit 7 | Refurbish Turbine Unit 7 - BDE | 4179 | 4282.6782 | 103.6782 | 2.481%
12931910 | 2019 | 2019 | BDE-Hydraulic In-Serv Failures | Hydraulic In-Service Failures | 1250 | 1374.3921 | 124.3921 | 9.951%
20081902 | 2019 | 2019 | Security Improvements - HYP | Security Improvements - Hydro Place | 47.1 | 28.2976 | -18.8024 | -39.92%
20081901 | 2019 | 2019 | Purchase Office Equipment-HYP | Purchase Office Equipment | 38 | 20.3895 | -17.6105 | -46.34%
12931909 | 2019 | 2019 | BDE-Upgrd SumpLevelSys PH1 | Upgrade Sump Level System Powerhouse 1 - BDE | 131.6 | 118.2189 | -13.3811 | -10.17%
12811903 | 2019 | 2019 | HLK-Refurbish Generator Rotor | Refurbish Generator Rotor - HLK | 1340.299 | 1544.8498 | 204.5508 | 15.26%
12961901 | 2019 | 2019 | HRD-Overhaul U3 Turbine Valve | Overhaul Unit 3 Turbine Valve - Holyrood | 3290.5 | 2682.9733 | -607.5267 | -18.46%
12961902 | 2019 | 2019 | HRD-Cond.Assessment/Misc Upgrd | Condition Assessment and Miscellaneous Upgrades - Holyrood | 1968.8 | 2941.7036 | 972.9036 | 49.42%
12961903 | 2019 | 2019 | HRD-Thermal In-Service Failure | Thermal In-Service Failures | 1250 | 2327.4256 | 1077.4256 | 86.19%
12971901 | 2019 | 2019 | HRD-Rplc 258VDC Battery Banks | Replace 258VDC Battery Banks - Holyrood | 330 | 350.6723 | 20.6723 | 6.264%
12681901 | 2019 | 2019 | Thermal Generation Tools&Equip | Purchase Tools and Equipment Less than $ 50,000 | 15.4 | 18.0717 | 2.6717 | 17.35%
12931901 | 2019 | 2019 | BDE-Upgrd Public Safety,Dams | Upgrade Public Safety Around Dams and Waterways - BDE | 678.5 | 737.4564 | 58.9564 | 8.689%
13501904 | 2019 | 2019 | Cond.Assess SubCable FHD-CHI | Condition Assessment for Submarine Cable - Farewell Head to Change Islands | 300.1 | 166.2941 | -133.8059 | -44.59%
13491908 | 2019 | 2019 | Perform WPLM Program | Wood Pole Line Management Program - Various Sites | 2467 | 2873.4173 | 406.4173 | 16.47%
13881901 | 2019 | 2019 | Additional Load Dist.Syst-WAB | Additions for Load - Distribution System | 186.7 | 80.9272 | -105.7728 | -56.65%
13251905 | 2019 | 2019 | VAR-Upgr TS Equip Foundations | Upgrade Terminal Station Equipment Foundations - Various (2019) | 306.2 | 242.3876 | -63.8124 | -20.84%
13251918 | 2019 | 2019 | Refurb Cntrl Building -HRD/CBC | Refurbish Control Building - HRD, CBC | 650.3 | 616.4578 | -33.8422 | -5.204%
13251901 | 2019 | 2019 | Terminal Stat In-Serv Failures | Terminal Station In-Service Failures | 1000 | 1744.6067 | 744.6067 | 74.46%
13251902 | 2019 | 2019 | Var-Replace Surge Arrestors | Replace Surge Arrestors - Various (2019) | 163.6 | 119.4258 | -44.1742 | -27%
13251903 | 2019 | 2019 | Var-Upgrade Cables | Upgrade Cables - Various (2019) | 500 | 297.006 | -202.994 | -40.6%
12971902 | 2019 | 2019 | HRD-Instl Vestibule Powerhouse | Building Vestibule Powerhouse - Holyrood | 49.3 | 37.3438 | -11.9562 | -24.25%
12971903 | 2019 | 2019 | HRD-Tank 3&4 Life Expect Study | Tanks 3 & 4 Life Expectancy Study - Holyrood | 48.3172 | 34.18 | -14.1372 | -29.26%
14101901 | 2019 | 2019 | STA-Supply/Install Waterline | Supply & Install Replacement Waterline - St. Anthony | 47.4 | 46.5735 | -0.82653 | -1.744%
12961904 | 2019 | 2019 | HRD-Unit 3 Electrical Testing | Unit 3 Electrical Testing - Holyrood | 39.1131 | 33.4188 | -5.6943 | -14.56%
13331802 | 2018 | 2020 | DieselPltEngine-CoolingSysUpgr | Diesel Plant Engine Cooling System Upgrades - Various Sites | 1310 | 1437.5344 | 127.5344 | 9.735%
14011803 | 2018 | 2020 | Diesel Plt Fire Protection-POV | Diesel Plant Fire Protection - Postville | 842 | 872.0761 | 30.0761 | 3.572%
14011804 | 2018 | 2020 | Energy Efficient Lighting-DPlt | Install Energy Efficiency Lighting in Diesel Plants - Various | 345.2 | 335.9397 | -9.2603 | -2.683%
13321901 | 2019 | 2020 | SVL-OHaul Olympus GasGenerator | Overhaul Olympus Gas Generator - Stephenville | 1666.8 | 1605.3137 | -61.4863 | -3.689%
21881902 | 2019 | 2020 | HWD-Replace Main Fuel Valves | Replace Main Fuel Valves - Hardwoods | 404.2 | 293.0207 | -111.1793 | -27.51%
13401901 | 2019 | 2020 | HRD GT-Upgrd CompressAirSystem | Upgrade Compressed Air System - Holyrood Gas Turbine | 388.4 | 203.315 | -185.085 | -47.65%
14271903 | 2019 | 2020 | Instl Reclosed RemoteCntrl-RHR | Install Recloser Remote Control (2019-2020) - Rocky Harbour | 386 | 131.4482 | -254.5518 | -65.95%
14011901 | 2019 | 2020 | Increase Fuel Storage - MAK | Additions for Load - Isolated Generation Systems | 2182.5 | 2578.1254 | 395.6254 | 18.13%
12421902 | 2019 | 2020 | Upgrd Telecontrol Facilities | Upgrade Telecontrol Facilities - Gull Pond Hill and Bay d’Espoir Hill | 673.9 | 749.3001 | 75.4001 | 11.19%
13501903 | 2019 | 2020 | 2019/20-Distribution Upgrades | Distribution System Upgrades - Various Sites | 5880.9 | 6245.9032 | 365.0032 | 6.207%
13251810 | 2018 | 2020 | Replace Protective Relays-M19 | Replace Protective Relays - Various Sites | 7535.5 | 4147.7088 | -3387.7912 | -44.96%
13251812 | 2018 | 2020 | Instl BRKR Failure Protection | Install Breaker Failure - Various Sites | 855.5 | 566.0153 | -289.4847 | -33.84%
13251819 | 2018 | 2020 | TS Flood Mitigation - SPL | Implement Terminal Station Flood Mitigation - Springdale | 974 | 673.1173 | -300.8827 | -30.89%
13881801 | 2018 | 2020 | Refurbish Wabush Terminal Stat | Refurbish Wabush Terminal Station | 5548.5 | 3445.6882 | -2102.8118 | -37.9%
13251904 | 2019 | 2020 | VAR-Repl Instrum Transformers | Replace Instrument Transformers - Various (2019-20) | 1100.1 | 877.5705 | -222.5295 | -20.23%
13251914 | 2019 | 2020 | Replc Disconnect Switches-M20 | Replace Disconnects - Various (2019-20) | 2350.7 | 1341.9522 | -1008.7478 | -42.91%
13251916 | 2019 | 2020 | Instl Fire Protect 230kVST-OPD | Install Fire Protection in 230 kV Stations - OPD (2019-20) | 883.3 | 399.6995 | -483.6004 | -54.75%
13251907 | 2019 | 2020 | Var-Upgrad Fault Recorders-BHL | Upgrade Fault Recorders - BHL (2019) | 623.5 | 278.1333 | -345.3667 | -55.39%
13251912 | 2019 | 2020 | Instl BRKRFailProtect-STB/STD | Install Breaker Failure Protection - STB, STD (2019-20) | 582.6 | 297.2845 | -285.3155 | -48.97%
13251908 | 2019 | 2020 | Insulator Replacement -Var-M20 | Replace Insulators - Various (2019-20) | 989 | 182.2252 | -806.7748 | -81.57%
13251911 | 2019 | 2020 | Perform Grounding Upgrades-M20 | Perform Grounding Upgrades - Various (2019-20) | 1845.5 | 4061.3314 | 2215.8314 | 120.1%
13251915 | 2019 | 2020 | Upgrade Power XFMR's (19-20) | Upgrade Power Transformers - Various (2019-20) | 9102.7 | 5761.9806 | -3340.7194 | -36.7%
13251906 | 2019 | 2020 | Upgrd XFMR Paralleling-WAV-M20 | Upgrade Transformer Paralleling - WAV | 301.8 | 232.6507 | -69.1493 | -22.91%
13251919 | 2019 | 2020 | Upgrd TS Mob.SubStation-STA | Upgrade Terminal Station for Mobile Substation - St. Anthony | 492 | 593.6632 | 101.6632 | 20.66%
13251813 | 2018 | 2020 | Upgrd Data Alarm ManagementM19 | Upgrade Data Alarm Management - Sunnyside | 611.4 | 572.7145 | -38.6855 | -6.327%
12931701 | 2017 | 2020 | BDE-Refurbish PH Station Serv | Refurbish Powerhouse Station Services - Bay d'Espoir | 4347.1 | 3951.4134 | -395.6866 | -9.102%
12931807 | 2018 | 2020 | Prot.Guards TurbPits BDE/USL | Install Protective Guards in Turbine Pits - BDE, USL | 541 | 245.8418 | -295.1582 | -54.56%
12931809 | 2018 | 2020 | Refurbish Hydraulic Structures | Refurbish Hydraulic Structures - Various | 4367.3 | 1929.5158 | -2437.7842 | -55.82%
12931812 | 2018 | 2020 | BDE-Rplc Int/Ext Coat SurgeTk1 | Replace Interior and Exterior Coating on Surge Tank 1 - BDE | 3564.1 | 2107.1363 | -1456.9637 | -40.88%
12931908 | 2019 | 2020 | BDE-Rplc Control Cable PH1 | Replace Control Cable PH1 - BDE (2019) | 415.6 | 238.7892 | -176.8108 | -42.54%
12931902 | 2019 | 2020 | BDE-Reburbish Hydraulic Struct | Refurbish Hydraulic Structures - BDE (2019-20) | 5036.5 | 401.279 | -4635.221 | -92.03%
12931904 | 2019 | 2020 | BDE-Refurbish Draft Tube Deck | Refurbish Draft Tube Deck Phase 1 - BDE | 1032.4 | 1354.8981 | 322.4981 | 31.24%
12931905 | 2019 | 2020 | BDE-Overhaul Unit 1 | Overhaul Unit 1 - BDE | 202 | 268.1303 | 66.1303 | 32.74%
12931903 | 2019 | 2020 | BDE-Rplc U 1-6 Gen.BearingSeal | Replace Units 1-6 Generator Bearing Cover Seals - BDE | 656.7 | 179.374 | -477.326 | -72.69%
12931906 | 2019 | 2020 | BDE-Rplc Condition Monitor Eqp | Replace Condition Monitoring Equipment - BDE (2019) | 382.7 | 314.2607 | -68.4393 | -17.88%
12811901 | 2019 | 2020 | HLK-Rplc T/G Cool Water Pump | Replace T/G Cooling Water Pump and Strainer - HLK | 408.5 | 448.6202 | 40.1202 | 9.821%
12811902 | 2019 | 2020 | HLK,PRV-Rplc Drainage Pumps | Replace Drainage Pumps - HLK, PRV | 774 | 571.0445 | -202.9555 | -26.22%
13332001 | 2020 | 2020 | Overhaul Diesel Units-Var | Overhaul Diesel Units - Various | 2310.915 | 1923.2427 | -387.6723 | -16.78%
13502006 | 2020 | 2020 | Upgrade Line Depots - BUR FOG | Upgrade Line Depots - Various | 648.3 | 724.178 | 75.878 | 11.7%
13072001 | 2020 | 2020 | Meters and Metering Equipment | Purchase Meters and Metering Equipment - Various | 244.214 | 180.6076 | -63.6064 | -26.05%
12422006 | 2020 | 2020 | Var-Replace Radomes | Replace Radomes - Various | 384.512 | 215.1132 | -169.3988 | -44.06%
12422008 | 2020 | 2020 | Upgrade RTUs | Upgrade Remote Terminal Units - Various | 157.054 | 156.0019 | -1.0521 | -0.6699%
12422010 | 2020 | 2020 | Rplc Batt Banks & Chargers-VAR | Replace Battery Banks and Chargers - Various | 195.955 | 263.6608 | 67.7058 | 34.55%
12422005 | 2020 | 2020 | Upgrade Site Facilities | Upgrade Site Facilities - Various | 45.522 | 46.3798 | 0.85776 | 1.884%
12422004 | 2020 | 2020 | Rplc Network Communications Eq | Replace Network Communications Equipment - Various | 186.797 | 193.3442 | 6.5472 | 3.505%
14012003 | 2020 | 2020 | Rplc Sewage Lift System-RIG | Replace Sewage Lift System - Rigolet | 127.926 | 203.1138 | 75.1878 | 58.77%
12932010 | 2020 | 2020 | Hydraulic In-Serv Failures | Hydraulic In-Service Failures | 1250 | 1287.2367 | 37.2367 | 2.979%
12922001 | 2020 | 2020 | Refurbish Access Road to Ebbeg | Refurbish Access Road to Ebbegunbaeg | 803.142 | 804.3129 | 1.1709 | 0.1458%
12902001 | 2020 | 2020 | Overhaul Unit 2 - Cat Arm | Overhaul Unit 2 - Cat Arm | 326.492 | 388.5783 | 62.0863 | 19.02%
12902004 | 2020 | 2020 | InstPartial DisMon-HLK,CAT,GCL | Install Partial Discharge Monitoring System - HLK,CAT,GCL | 451.417 | 495.6979 | 44.281 | 9.809%
12902003 | 2020 | 2020 | Penstock Lvl 2 Cond. As. CAT | Penstock Level 2 Condition Assessment - CAT | 261.216 | 254.6524 | -6.5636 | -2.513%
12932006 | 2020 | 2020 | Upgrade Bear Brook Crossing | Upgrade Bear Brook Crossing | 435.354 | 718.0934 | 282.7394 | 64.94%
12982001 | 2020 | 2020 | Remove Safety Hazards-2020 | Remove Safety Hazards - Various | 198.552 | 218.4151 | 19.8631 | 10%
12842002 | 2020 | 2020 | Instal Frazil Ice Forecas. UPS | Install Frazil Ice Forecast - UPS | 176.987 | 230.1898 | 53.2028 | 30.06%
12962003 | 2020 | 2020 | HRD-Thermal In-Service Failure | Thermal In-Service Failures | 2000.042 | 1836.6861 | -163.3559 | -8.168%
13252005 | 2020 | 2020 | Upg. Terminal St. Equip Founda | Upgrade Terminal Station Equipment Foundations - Various (2020) | 349.9 | 242.5254 | -107.3746 | -30.69%
13252018 | 2020 | 2020 | Upgrade Control Building - WAV | Refurbish Control Building - WAV (2020) | 333.7298 | 248.5773 | -85.1525 | -25.52%
13252001 | 2020 | 2020 | Terminal Stat In-Serv Failures | Terminal Station In-Service Failures | 1500.046 | 1081.0307 | -419.0153 | -27.93%
13252009 | 2020 | 2020 | Repl. TS Batt. Banks and Charg | Replace TS Battery Banks and Chargers - Various | 123.543 | 89.1301 | -34.4129 | -27.85%
13252002 | 2020 | 2020 | Replace Surge Arresters - VAR | Replace Surge Arrestors - Various (2020) | 132.28 | 102.2014 | -30.0786 | -22.74%
13252003 | 2020 | 2020 | Var-Upgrade Cables | Upgrade Cables - Various (2020) | 473.611 | 160.902 | -312.709 | -66.03%
13252011 | 2020 | 2020 | Purchase SF6 Multi Analyzer | Purchase SF6 Multi Analyzer - Various | 207.049 | 155.7007 | -51.3483 | -24.8%
14112001 | 2020 | 2020 | Upgrade Fuel Storage Tanks CHT | Upgrade Fuel Storage Tanks - Charlottetown | 467.169 | 310.6504 | -156.5186 | -33.5%
13492008 | 2020 | 2020 | Perform WPLM Program | Wood Pole Line Management Program - Various Sites | 2792.724 | 2882.6142 | 89.8902 | 3.219%
12932001 | 2020 | 2020 | Upgrd Public Safety,Dams | Upgrade Public Safety, Dams | 728.514 | 467.1982 | -261.3158 | -35.87%
20082001 | 2020 | 2020 | Purchase Office Equipment-HYP | Purchase Office Equipment | 60.9 | 6.9706 | -53.9294 | -88.55%
12682001 | 2020 | 2020 | Thermal Generation Tools&Equip | Purchase Tools and Equipment less than $50,000 | 15.7 | 21.5057 | 5.8057 | 36.98%
12422007 | 2020 | 2020 | Purchase Test Equipment | Purchase Tools and Equipment less than $50,000 | 93.4 | 46.2635 | -47.1365 | -50.47%
12682002 | 2020 | 2020 | HRD - Tools and Equipment 50K | Purchase Tools and Equipment less than $50,000 | 26 | 26.5213 | 0.5213 | 2.005%
12792001 | 2020 | 2020 | Hydro Generation Tools & Equip | Purchase Tools and Equipment Less than $ 50,000 | 21 | 36.1166 | 15.1166 | 71.98%
12931702 | 2017 | 2021 | BDE-U1-6 Rplc Exciter Control | Replace Exciter Controls Units 1 to 6 - Bay d'Espoir | 3347 | 2343.2927 | -1003.7073 | -29.99%
13251601 | 2016 | 2021 | Upgrade Circuit Breakers 16/20 | Upgrade Circuit Breakers - Various Sites | 61460.4 | 44310.9252 | -17149.4748 | -27.9%
14011808 | 2018 | 2021 | MAK-Diesel Genset Replacement | Diesel Genset Replacements - Makkovik | 8900.2 | 10456.444 | 1556.244 | 17.49%
13251913 | 2019 | 2021 | Upgrd Data Alarm System HRDM20 | Upgrade Data Alarm Systems - HRD (2019-20) | 636.8 | 789.3047 | 152.5047 | 23.95%
13251917 | 2019 | 2021 | Upgrd RecloseCircuit BRKRs-HRD | Upgrade Reclosing Circuit Breakers B12L65 & B2L68 - HRD | 367.6 | 171.4778 | -196.1222 | -53.35%
13881903 | 2019 | 2021 | Refurbish 230kV TS WAB-M20 | Refurbish 230kV TS - WAB | 4969.8 | 1989.1801 | -2980.6199 | -59.97%
12922002 | 2020 | 2021 | Install Remote Seepage MS-BDE | Install Remote Seepage Monitoring System - BDE | 394.7 | 1260.66 | 865.96 | 219.4%
12932003 | 2020 | 2021 | BDE-Refurb U 5 Gen Stator | Refurbish U5 Generatpr Stator -BDE | 5630 | 6854.3221 | 1224.3221 | 21.75%
14112008 | 2020 | 2021 | Diesel Genset Replace MSH | Diesel Genset Replacements - Mary's Harbour | 3900.714 | 3527.9937 | -372.7203 | -9.555%
14012001 | 2020 | 2021 | Diesel Plant Vent. Up. NAN | Diesel Plant Ventilation Upgrade - Nain | 853.076 | 653.1224 | -199.9536 | -23.44%
12942001 | 2020 | 2021 | Rplc Diesel Genset-VCS | Replace Diesel Genset-VCS | 944.028 | 1064.0392 | 120.0112 | 12.71%
21842002 | 2020 | 2021 | Inspect Generator Rotor - HVY | Generator Assessment - Happy Valley Gas Turbine | 1097.604 | 1221.9491 | 124.3451 | 11.33%
13252015 | 2020 | 2021 | Upgrade Power Transformers - V | Upgrade Power Transformers - Various (2020-21) | 1245.723 | 1228.4232 | -17.2998 | -1.389%
13252013 | 2020 | 2021 | Upgrade Data Alarm Systems MDR | Upgrade Data Alarm Systems - MDR (2020-21) | 326.499 | 380.4052 | 53.9062 | 16.51%
13252014 | 2020 | 2021 | Replace Disconnect Switches | Replace Disconnects - Various (2020-21) | 1069.847 | 1223.7236 | 153.8766 | 14.38%
13252016 | 2020 | 2021 | Install Fire Protec, 230kV STB | Install Fire Protection in 230 kV Stations - STB (2020-21) | 681.195 | 390.2868 | -290.9082 | -42.71%
13252008 | 2020 | 2021 | Replace Insulators - Various | Replace Insulators - Various (2020-21) | 243.106 | 226.6151 | -16.4909 | -6.783%
12962001 | 2020 | 2021 | HRD-Rewind Unit 3 Stator | Rewind Unit 3 Stator - Holyrood | 6945.6 | 7285.6551 | 340.0551 | 4.896%
21842001 | 2020 | 2021 | HVYGT-Replace Fire Suppression | Replace Fire Supression System - Happy Valley Gas Turbine | 2642.45 | 1923.0097 | -719.4403 | -27.23%
12932005 | 2020 | 2021 | Replace Control Cables BDE | Replace Control Cables BDE | 311.291 | 312.2041 | 0.9131 | 0.2933%
13252012 | 2020 | 2021 | Instl BRKRFailProtect-BUC/HBY | Upgrade Breaker Failure Protection (2020-2021) | 510.169 | 958.8475 | 448.6785 | 87.95%
13972003 | 2020 | 2021 | Additions for Load-DistMAK HPD | Additions for Load - Distribution System - Makkovik and Hopedale | 846.113 | 824.0509 | -22.0621 | -2.607%
13252004 | 2020 | 2021 | Repla Instr. Transformers VAR | Replace Instrument Transformers - Various (2020-21) | 339.054 | 690.3462 | 351.2922 | 103.6%
13502003 | 2020 | 2021 | 2020/21-Distribution Upgrades | Distribution System Upgrades (2020-2021) - Various | 3257.1 | 3485.513 | 228.413 | 7.013%
13252006 | 2020 | 2021 | Upgrade Station Lighting - VAR | Upgrade Station Lighting - HRD | 414.833 | 316.0256 | -98.8074 | -23.82%
12852001 | 2020 | 2021 | Rplc TG Cont & Vib Mon Sy PRV | Replace Turbine and Generator Control & Vibration Monitoring System - PRV | 238.571 | 277.1194 | 38.5484 | 16.16%
12932002 | 2020 | 2021 | Reburbish Hydraulic Struct VAR | Reburbish Hydraulic Structures VAR | 5368.415 | 5182.5133 | -185.9017 | -3.463%
13502091 | 2020 | 2021 | SUP-EV Charger Installation | Construction and Installation of an Electric Vehcile Fast Track Network | 259.4 | 367.7847 | 108.3847 | 41.78%
14112092 | 2020 | 2021 | MSH - Integrate Renewables PH2 | Integrate Renewable PH2 - Mary's Harbour | 498 | 1.4552e-14 | -498 | -100%
12852102 | 2021 | 2021 | Penstock Lvl 2 Cond Assess PRV | Penstock Level II Condition Assessment - PRV | 196.8 | 256.7393 | 59.9393 | 30.46%
12932101 | 2021 | 2021 | Upgrd Public Safety Dams BDE21 | Upgrade Public Safety Around Dams and Waterways - BDE | 436.28 | 380.6985 | -55.5815 | -12.74%
13252101 | 2021 | 2021 | Terminal Stat In-Serv Failures | Terminal Station In-Service Failures | 1800 | 1178.0273 | -621.9727 | -34.55%
13252105 | 2021 | 2021 | Upg. Terminal St. Equip Founda | Upgrade Terminal Station Equipment Foundations - Various (2021) | 175.4 | 163.5641 | -11.8359 | -6.748%
14012102 | 2021 | 2021 | Inspect Fuel Stg Tks - Postvil | Inspect Fuel Storage Tanks - Postville | 532.6 | 350.282 | -182.318 | -34.23%
13252107 | 2021 | 2021 | Upgrade Fault Recorders - Var | Upgrade Fault Recorders - Various (2021) | 346.408 | 219.5125 | -126.8955 | -36.63%
13072101 | 2021 | 2021 | Meters and Metering Equipment | Purchase Meters and Metering Equipment - Various | 233.4 | 228.5207 | -4.8793 | -2.091%
14012103 | 2021 | 2021 | Rplc Fuel Storage Tank - PR | Replace Fuel Storage Tanks - PR | 350.3 | 234.0964 | -116.2036 | -33.17%
13252102 | 2021 | 2021 | Replace Surge Arresters - VAR | Replace Surge Arresters - Various (2021) | 61.649 | 54.3044 | -7.3446 | -11.91%
13252119 | 2021 | 2021 | Pur SF6 Reclaim Units-SVL/HVY | Purchase SF6 Reclaim Units - Various | 142.722 | 142.2401 | -0.48187 | -0.3376%
12422104 | 2021 | 2021 | Rplc Network Communications Eq | Replace Network Communications Equipment - Various | 194 | 242.8356 | 48.8356 | 25.17%
12422105 | 2021 | 2021 | Upgrade Site Facilities | Upgrade Site Facilities - Various | 48.943 | 48.375 | -0.56799 | -1.161%
20682105 | 2021 | 2021 | Perform Minor Enhancements HYP | Perform Minor Enhancements - Hydro Place | 372.1 | 281.1013 | -90.9987 | -24.46%
12422110 | 2021 | 2021 | Rplc Batt Banks & Chargers-VAR | Replace Battery Banks and Chargers - Various | 327.2 | 350.4117 | 23.2117 | 7.094%
12982101 | 2021 | 2021 | Remove Safety Hazards-2021 | Remove Safety Hazards - Various | 199.1 | 224.7445 | 25.6445 | 12.88%
12682102 | 2021 | 2021 | HRD GT - Tools and Equipment | Purchase Tools and Equipment Less than $ 50,000 - HRD GT | 45.6 | 37.3845 | -8.2155 | -18.02%
13252103 | 2021 | 2021 | Upgrd Cables, Trenches, AC/DC | Upgrade Cables - various (2021) | 496.693 | 251.938 | -244.755 | -49.28%
12932102 | 2021 | 2021 | BDE - Unit 5 Gen Overhaul | Unit 5 Generator Overhaul - BDE | 220.427 | 303.222 | 82.795 | 37.56%
12852101 | 2021 | 2021 | PRV - Generator Overhaul | Generator Overhaul - PRV | 341.906 | 316.1892 | -25.7168 | -7.522%
12932110 | 2021 | 2021 | Hydraulic Generation In-Servic | Hydraulic In-Service Failures | 1250 | 2059.1178 | 809.1178 | 64.73%
12792101 | 2021 | 2021 | Hydro Generation Tools & Equip | Purchase Tools and Equipment Less than $ 50,000 | 194.3 | 168.8137 | -25.4863 | -13.12%
12932105 | 2021 | 2021 | BDE - Replace Air Conditioning | Replace Air Conditioning - BDE | 162.9 | 177.8179 | 14.9179 | 9.158%
20082101 | 2021 | 2021 | Purchase Office Equipment-HYP | Purchase Office Equipment | 62.264 | 20.4248 | -41.8392 | -67.2%
13492108 | 2021 | 2021 | Perform WPLM Program | Wood Pole Line Management Program - Various Sites | 2896.9 | 2964.946 | 68.046 | 2.349%
13332101 | 2021 | 2021 | Overhaul Diesel Units-Var | Overhaul Diesel Units - Various | 1232.9 | 790.3924 | -442.5076 | -35.89%
12422108 | 2021 | 2021 | Upgrade RTUs | Upgrade Remote Terminal Units - Various | 183.4 | 199.1898 | 15.7898 | 8.609%
12422106 | 2021 | 2021 | Var-Replace Radomes | Replace Radomes - Various | 240.4 | 231.9067 | -8.4933 | -3.533%
12972101 | 2021 | 2021 | HRD-Boiler Cond Assessmt/Upgrd | Boiler Condition Assessment/Upgrade - Holyrood | 3000 | 3889.2474 | 889.2474 | 29.64%
12972103 | 2021 | 2021 | HRD-Inspect Chemical Tanks | Inspect Chemical Tanks - Holyrood | 919.8 | 514.6453 | -405.1547 | -44.05%
12962103 | 2021 | 2021 | HRD-Thermal In-Service Failure | Thermal In-Service Failure - Holyrood | 2000 | 5807.515 | 3807.515 | 190.4%
12962104 | 2021 | 2021 | HRD-O/H U3 Boiler Feed Pump E | Overhaul Unit 3 Boiler Feed Pump - Holyrood | 373 | 257.7866 | -115.2134 | -30.89%
12962101 | 2021 | 2021 | HRD-O/H Unit 1 Turbine / Value | Overhaul Unit 1 Turbine / Valve - Holyrood | 8026.6 | 9765.0063 | 1738.4063 | 21.66%
20682103 | 2021 | 2021 | Core IT/OT Infrastructure | Upgrade Core IT Infrastructure - Hydro Place | 262.776 | 257.5458 | -5.2302 | -1.99%
20682104 | 2021 | 2021 | Refresh Security Software HYP | Refresh Cyber Security Infrastructure - Hydro Place | 217.494 | 211.2176 | -6.2764 | -2.886%
20682109 | 2021 | 2021 | Upgrd Hydro ECC Wall Infrastr | Upgrade Hydro ECC Wall Infrastructure - Hydro Place | 188.476 | 142.3349 | -46.1411 | -24.48%
12962102 | 2021 | 2021 | HRD-O/H Unit 3 Generator | Overhaul Unit 3 Generator - Holyrood | 572.7 | 610.9818 | 38.2818 | 6.684%
12422107 | 2021 | 2021 | Purchase Test Equipment | Purchase Tools and Equipment less than $50,000 | 40 | 34.0015 | -5.9985 | -15%
12682101 | 2021 | 2021 | Thermal Generation Tools&Equip | Purchase Tools and Equipment less than $50,000 | 18.8 | 7.9027 | -10.8973 | -57.96%
13252109 | 2021 | 2021 | Repl. TS Batt. Banks and Charg | Replace TS Battery Banks and Chargers - Various | 177.4 | 156.5489 | -20.8511 | -11.75%
20682108 | 2021 | 2021 | Hydro - Mobile Devices | Hydro - Mobile Devices | 48.2 | 47.1449 | -1.0551 | -2.189%
14011908 | 2019 | 2022 | Rplc Diesel Genset 2052 - CTW | Diesel Genset Replacements (2019-2020) | 3947.4 | 4163.9017 | 216.5017 | 5.485%
14012002 | 2020 | 2022 | Replace Auto. Equipment RIG | Replace Automation Equipment - Rigolet | 363.8 | 459.4468 | 95.6468 | 26.29%
13402002 | 2020 | 2022 | HRD GT Partial Disch. Mon. | Install Partial Discharge Monitoring - Holyrood Gas Turbine | 612.755 | 521.333 | -91.422 | -14.92%
13502017 | 2020 | 2022 | Install Recloser Remote Contro | Install Recloser Remote Control (2020-2021) - Hampden and Upper Salmon | 256.647 | 285.012 | 28.365 | 11.05%
13882003 | 2020 | 2022 | Refurbish 230kV TS WAB-M21 | Refurbish 230 kV Terminal Station Part 2 - WAB (2020-21) | 2465.576 | 1509.4403 | -956.1357 | -38.78%
14022001 | 2020 | 2022 | Install Fault Recorders - HVY | Install Fault Recorders - HVY (2020-21) | 687.951 | 393.8016 | -294.1494 | -42.76%
13882093 | 2020 | 2022 | WAB L34/L35 Protection Upgrade | Wabush L34 and L35 Protective Relays - CIAC | 259.302 | 0 | -259.302 | -100%
13402102 | 2021 | 2022 | Purchase Capital Spares – GT | Purchase Capital Spares - Holyrood Gas Turbine | 213.8 | 200.7921 | -13.0079 | -6.084%
13402101 | 2021 | 2022 | HRD GT-Const LO Cooler Hood | Construct LO Cooler Hood - Holyrood Gas Turbine | 318.8 | 562.2037 | 243.4037 | 76.35%
14011904 | 2019 | 2022 | Rplc Human Machine Interface | Replace Human Machine Interface - Cartwright | 306.9 | 306.491 | -0.40904 | -0.1333%
13962103 | 2021 | 2022 | HVY L7-Additon for Load Growth | Addition for Load Growth - Happy Valley L7 | 617.6 | 613.2703 | -4.3297 | -0.7011%
13462102 | 2021 | 2022 | Rplc Light Duty Mobile Equip | Replace Light Duty Mobile Equipment - Various Sites | 549.6 | 601.0809 | 51.4809 | 9.367%
13252115 | 2021 | 2022 | Upgrade Power Transformers - V | Upgrade Power Transformers - Various (2021-22) | 4312.318 | 3072.2791 | -1240.0389 | -28.76%
13252111 | 2021 | 2022 | Perform Grounding Upgrades-M22 | Perform Grounding Upgrades - Various Sites (2021-22) | 2107.3 | 1732.1113 | -375.1887 | -17.8%
13252110 | 2021 | 2022 | Replace Protective Relays-M22 | Replace Protective Relays - Various Sites (2021-22) | 2007 | 1765.0953 | -241.9047 | -12.05%
13252116 | 2021 | 2022 | Upgrs XFMR Parallel-HWD T1-T4 | Upgrades XFMR Parallel | 176.2 | 184.1815 | 7.9815 | 4.53%
21842103 | 2021 | 2022 | HVYGT-Upgrade Compressed Air | Upgrade Compressed Air System - Happy Valley Gas Turbine | 145.8 | 186.6058 | 40.8058 | 27.99%
21842101 | 2021 | 2022 | HVYGT-Replace Voltage Regulato | Replace Voltage Regulator - Happy Valley Gas Turbine | 342.3 | 283.1753 | -59.1247 | -17.27%
21842102 | 2021 | 2022 | Rplc Fuel Lube Glycol Pump HVY | Replace Fuel Oil, Lube Oil, and Glycol Pumps - Happy Valley Gas Turbine | 405.2 | 405.0603 | -0.13969 | -0.03447%
13252113 | 2021 | 2022 | Upgrade Data Alarm Mgmt. OPD | Upgrade Data Alarm Management - OPD (2021-22) | 353.309 | 561.5813 | 208.2723 | 58.95%
13252112 | 2021 | 2022 | Install Breaker Fail OPD DR | Install Breaker Failure Protection (2021-22) | 451.472 | 480.5956 | 29.1236 | 6.451%
13252114 | 2021 | 2022 | Replace Disconnect Switches | Replace Disconnect Switches - Various (2021-22) | 1292.7 | 1554.6703 | 261.9703 | 20.27%
13502103 | 2021 | 2022 | 2021/22-Distribution Upgrades | Upgrade of Worst-Performing Distribution Feeders (2021-2022) | 1124.5 | 1841.9017 | 717.4017 | 63.8%
13252106 | 2021 | 2022 | Upgrade Station Lighting - VAR | Upgrade Station Lighting - Various (2021) | 278.9 | 201.905 | -76.995 | -27.61%
13252104 | 2021 | 2022 | Repla Instr. Transformers VAR | Replace Instrument Transformers - Various (2021-22) | 460.9 | 729.6884 | 268.7884 | 58.32%
20682203 | 2022 | 2022 | Upgrade Core IT/OT Infrastruct | Upgrade Core IT/OT Infrastructure (2022) - Hydro Place | 308.2 | 308.2768 | 0.07683 | 0.02493%
20682204 | 2022 | 2022 | Refresh Security Software HYP | Refresh Cyber Security Infrastructure (2022) - Hydro Place | 221.7 | 333.3953 | 111.6953 | 50.38%
20682205 | 2022 | 2022 | Perform Minor Enhancements HYP | Perform Software Upgrades and Minor Enhancements - Hydro Place | 621.7 | 493.687 | -128.013 | -20.59%
12422201 | 2022 | 2022 | Replace RTUs (2022) - Various | Upgrade Remote Terminal Units (2022) - Various | 171.1 | 153.1715 | -17.9285 | -10.48%
12422203 | 2022 | 2022 | Upgr Site Facilities VAR 22 | Upgrade Site Facilities (2022) - Various | 49.6 | 50.3063 | 0.70634 | 1.424%
13332201 | 2022 | 2022 | Overhaul Diesel Units-Var | Overhaul Diesel Units (2022) - Various | 1360.5 | 1216.9338 | -143.5662 | -10.55%
14112202 | 2022 | 2022 | Upgr Fuel Storage Tanks MSH 22 | Upgrade Fuel Storage Tanks (2022) - Mary's Harbour | 499.1 | 622.6749 | 123.5749 | 24.76%
12422208 | 2022 | 2022 | Replace Mobile Devices - Hydro | Replace Mobile Devices | 49.7 | 48.8921 | -0.80786 | -1.625%
13252205 | 2022 | 2022 | Upgr Terminal Stn Fdn BCX/LLK | Upgrade Terminal Station Foundations - BCX/LLK | 614.5 | 552.4733 | -62.0267 | -10.09%
20682211 | 2022 | 2022 | STLF HYDRO 22 | Replacement of Short-Term Load Forecasting Software | 439.5 | 409.1187 | -30.3813 | -6.913%
13492201 | 2022 | 2022 | Wood Pole Line Management Prgm | Wood Pole Line Management Program (2022) | 1603.5 | 1986.4668 | 382.9668 | 23.88%
12982201 | 2022 | 2022 | Remove Safety Hazards - Var | Remove Safety Hazards (2022) - Various | 199.6 | 170.5701 | -29.0299 | -14.54%
12422204 | 2022 | 2022 | Rplc Batt Banks & Chargers-VAR | Replace Battery Banks and Chargers (2022) - Various | 226.6 | 192.7347 | -33.8653 | -14.94%
12422205 | 2022 | 2022 | Purchase Tools and Equipment | Purchase Tools and Equipment Less than $50,000 (2022) | 42 | 56.0279 | 14.0279 | 33.4%
12422206 | 2022 | 2022 | Var - Replace Radomes 2022 | Replace Radomes (2022) - Various | 179.9 | 124.7468 | -55.1532 | -30.66%
13502191 | 2021 | 2022 | Phase 2 - EV fast Charging Net | Phase 2 - EV charging Network | 1581.501 | 1844.0956 | 262.5946 | 16.6%
13252122 | 2021 | 2022 | Replace HTGS T2 | Replace Holyrood Thermal Generating Station T2 | 1393.157 | 2047.8321 | 654.6752 | 46.99%
13251910 | 2019 | 2022 | Replace Protective Relays-M20 | Replace Protective Relays - Various (2019-20) | 4579.4 | 2781.0307 | -1798.3693 | -39.27%
13402202 | 2022 | 2022 | Purchase Tools & Equipment -GT | Purchase Tools and Equipment Less than $50,000 (2022) - Gas Turbine | 19.6 | 20.0301 | 0.43014 | 2.195%
13252209 | 2022 | 2022 | Install Breaker Fail - DLK | Install Breaker Failure Protection - DLK (2022-23) | 171.216 | 59.6105 | -111.6055 | -65.18%
13252107 | 2021 | 2022 | Upgrade Fault Recorders - Var | Upgrade Fault Recorders - Various (2021) | 346.408 | 219.5125 | -126.8955 | -36.63%
13252109 | 2021 | 2022 | Repl. TS Batt. Banks and Charg | Replace TS Battery Banks and Chargers - Various | 177.4 | 156.5489 | -20.8511 | -11.75%
14272290 | 2022 | 2022 | Hampden New Line from TS SUPP | Hampden New Line from TS | 443.8 | 415.3142 | -28.4858 | -6.419%
12932204 | 2022 | 2022 | Upgrd Public Safety Dams BDE22 | Upgrade Public Safety Around Dams and Waterways - BDE | 469.5 | 587.4774 | 117.9774 | 25.13%
12962204 | 2022 | 2022 | Tools and Equip. <50K Therm 22 | Purchase Tools and Equipment Less than $50,000 (2022) - Thermal Plants | 18.9 | 18.5074 | -0.39263 | -2.077%
12962205 | 2022 | 2022 | Turbine Valve Overhaul Unit 3 | Turbine Valve Overhaul Unit 3 - Holyrood | 3623.5 | 2485.5916 | -1137.9084 | -31.4%
12932205 | 2022 | 2022 | Overhaul Turbine Gen - BDE | Overhaul Unit 6 - BDE | 225.4 | 564.4001 | 339.0001 | 150.4%
12932206 | 2022 | 2022 | Overhaul Turbine Gen - Unit 4 | Overhaul Unit 4 - BDE | 225 | 251.1359 | 26.1359 | 11.62%
12932209 | 2022 | 2022 | Purchase Tools & Eq. <50K | Purchase Tools and Equipment Less than $50,000 (2022) - Hydraulic Plants | 187.3 | 151.9023 | -35.3977 | -18.9%
20082201 | 2022 | 2022 | Tools & Equipment - Admin 2022 | Purchase Office Equipment Less Than $50,000 (2022) | 67.1 | 68.8243 | 1.7243 | 2.57%
12902002 | 2020 | 2022 | Refurb Sump Lvl Sys-CatArm | Refurbish Sump Level Control System - Cat Arm | 355.923 | 895.6326 | 539.7096 | 151.6%
12842001 | 2020 | 2022 | Rplc Sump Pump-Upper Salmon | Rplc Sump Pump-Upper Salmon | 407.153 | 396.2344 | -10.9186 | -2.682%
12962002 | 2020 | 2022 | Up.Uninterruptible Pow 3&4 HRD | Upgrade Uninterruptible Power Supply 3 & 4 - Holyrood | 348.7 | 512.7327 | 164.0327 | 47.04%
12922101 | 2021 | 2022 | Lvl 2 Condition Assessment SRS | Level II Condition Assessment - SRS | 556.808 | 481.6585 | -75.1495 | -13.5%
12932103 | 2021 | 2022 | BDE-Refurb U 6 Gen Stator | Refurbish Unit 6 Generator Stator - BDE | 9160.879 | 7106.4588 | -2054.4202 | -22.43%
12812101 | 2021 | 2022 | HLK-Rep Frazil Ice Monitor Sys | Replace Frazil Ice Monitor System - HLK | 199.5 | 336.7249 | 137.2249 | 68.78%
12922102 | 2021 | 2022 | Burnt Dam-Replace 60kW Diesel | Replace 60 kW Diesel Generator - Burnt Dam | 1161.7 | 383.2038 | -778.4962 | -67.01%
12972102 | 2021 | 2022 | HRD-Upgrd WasteWater Equal.Sys | Upgrade Waste Water Equalization System - Holyrood | 2361.1 | 2668.957 | 307.857 | 13.04%
12932203 | 2022 | 2022 | BDE Unit 6 Replace Control Ca | BDE Unit 6 Replace Control Cables | 304.8 | 331.6525 | 26.8525 | 8.81%
12972201 | 2022 | 2022 | HRD - Upgrade Wastewater Treat | Upgrade Wastewater Treatment Plant 600 V Variable Frequency Drives - Holyrood | 70.1 | 58.2025 | -11.8975 | -16.97%
12972202 | 2022 | 2022 | Air Receivers Condition Assess | Air Receivers Condition Assessment and Upgrades - Holyrood | 336.5 | 192.3849 | -144.1151 | -42.83%
12962202 | 2022 | 2022 | Major Pump Overhaul - Holyrood | Major Pumps Overhaul - Holyrood | 491.3 | 907.7166 | 416.4166 | 84.76%
12972203 | 2022 | 2022 | HRD-Boiler Cond Assessmt/Upgrd | Boiler Condition Assessment and Miscellaneous Upgrades - Holyrood | 3014.2 | 3899.3703 | 885.1703 | 29.37%
14362001 | 2020 | 2023 | Rplc Diesel Plant Roof-LAL,STA | Replace Diesel Plant Roof - LAL/STA | 2313.5555 | 1335.8991 | -977.6564 | -42.26%
20082002 | 2020 | 2023 | Replace Elevator Motors HYP | Replace Elevator Motors and Controls Equipment - HYP | 882.8477 | 964.652 | 81.8043 | 9.266%
13462105 | 2021 | 2023 | L2 Chargers for Electric Veh. | Install Level 2 Chargers for Electric Vehicles | 478.005 | 357.2934 | -120.7116 | -25.25%
13462001 | 2020 | 2023 | RplcLight&HvyDty Vehicles -VAR | Replace Lignt and Heavy Duty Vehicles - Various (2020) | 8848.5694 | 4055.059 | -4793.5103 | -54.17%
13252108 | 2021 | 2023 | Instl Fire Protect 230kVST-MDR | Install Fire Protection in 230 kV Stations - Massey Drive | 921.499 | 521.9126 | -399.5863 | -43.36%
12932104 | 2021 | 2023 | BDE-Replace Annunciators | BDE-Replace Annunciators | 384.9684 | 353.3838 | -31.5846 | -8.204%
12962105 | 2021 | 2023 | HRD-Upgrd Dist.Control System | Upgrade Distributed Control System Hardware - Holyrood | 1122.6141 | 863.5919 | -259.0222 | -23.07%
20082102 | 2021 | 2023 | HYP-Rplc Transfer Switches/Hrd | Replace Transfer Switches and Associated Hardware - Hydro Place | 2324.6091 | 1485.3389 | -839.2703 | -36.1%
13462101 | 2021 | 2023 | Rplc Vehicles&Aerial Devices | Replace Light- and Heavy-Duty Vehicles (2021-2022) | 5909.7557 | 1838.9963 | -4070.7594 | -68.88%
12422202 | 2022 | 2023 | Rplc Network Comms EQ 2022 | Replace Network Communications Equipment (2022) | 312.5964 | 203.258 | -109.3384 | -34.98%
12902201 | 2022 | 2023 | SSLR Communication Link Upgrad | SSL communication Link Upgrade - CAT | 163.1583 | 192.6158 | 29.4576 | 18.05%
20682206 | 2022 | 2023 | Upgr Energy MGMT System 22 | Upgrade Energy Management System (2022) - Hydro Place | 335.5683 | 446.3595 | 110.7912 | 33.02%
13462203 | 2022 | 2023 | Replace Light- Duty Mobile Equ | Replace Light-Duty Mobile Equipment (2022) - Various | 775.2853 | 705.4096 | -69.8757 | -9.013%
13462290 | 2022 | 2023 | Replace Tracks - V7271 <50k | Replace Tracks - V7271 - Supplemental | 96.62 | 45 | -51.62 | -53.43%
13252117 | 2021 | 2023 | Upgrade Circuit Breakers 21/22 | Upgrade Circuit Breakers (2021-2022) - Various | 12048.6929 | 8193.3203 | -3855.3726 | -32%
13252202 | 2022 | 2023 | Upgrade Circuit Breakers 22/23 | Upgrade Circuit Breakers (2022-2023) - Various | 8402.5238 | 5643.3502 | -2759.1737 | -32.84%
21842201 | 2022 | 2023 | Install Infrared Scanning Port | Install Infrared Scanning Ports - Happy Valley Gas Turbine | 87.5574 | 53.0414 | -34.516 | -39.42%
13402201 | 2022 | 2023 | Holyrood GT Control Systems Up | Control System Replacement - Holyrood Gas Turbine | 262.1713 | 192.3079 | -69.8634 | -26.65%
13252203 | 2022 | 2023 | Instll Fire Protect 230kv- BUC | Install Fire Protection in 230 kV Stations - BUC (2022-23) | 492.8023 | 390.8944 | -101.9079 | -20.68%
13252204 | 2022 | 2023 | Replace Protective Relays-M23 | Replace Protective Relays - Various (2022-23) | 2253.2078 | 1407.7079 | -845.4999 | -37.52%
12962203 | 2022 | 2023 | Unit 3 Gen. Comp Cond Asst | Unit 3 Generator Components Condition Assessment and Miscellaneous Upgrades | 422.0236 | 544.6956 | 122.672 | 29.07%
13502203 | 2022 | 2023 | Upgrade Distribution Feeders | Upgrade of Worst-Performing Distribution Feeders (2022-2023) | 2761.098 | 3052.5192 | 291.4212 | 10.55%
12922201 | 2022 | 2023 | Refurb Hydlic Struct Burnt Dam | Refurbish Hydraulic Structures - Burnt Dam (2022-23) | 3756.277 | 3003.7782 | -752.4988 | -20.03%
13252206 | 2022 | 2023 | Repl TS Batt Banks/Chargers22 | Replace TS Battery Banks and Chargers - EHW, HWD, SDP, SHE, SOK | 315.2393 | 369.0905 | 53.8512 | 17.08%
12932207 | 2022 | 2023 | Replace Generator Bearing Seal | Replace Units 1-6 Generator Bearing Cover Seals - BDE | 296.4675 | 149.2869 | -147.1806 | -49.64%
12902202 | 2022 | 2023 | Replace Surface Air Coolers | Replace Surface Air Coolers for Both Units - CAT | 869.0732 | 583.5549 | -285.5183 | -32.85%
13252207 | 2022 | 2023 | Upgrade Power Transformers-22 | Upgrade Power Transformers - Various (2022-23) | 3758.9072 | 2642.7505 | -1116.1567 | -29.69%
12842201 | 2022 | 2023 | Replace Rotary Strainer - USL | Replace Rotary Strainer - USL | 239.9966 | 238.4998 | -1.4968 | -0.6237%
12932210 | 2022 | 2023 | Replace Monorail Beams | Replace Monorail Beams & Associated Mounts SRS - BDE | 592.8804 | 874.5932 | 281.7129 | 47.52%
13502202 | 2022 | 2023 | Install Recloser Remote Contro | Install Recloser Remote Control (2021-2022) - Various | 360.4826 | 213.7629 | -146.7196 | -40.7%
13252209 | 2022 | 2023 | Install Breaker Fail - DLK | Install Breaker Failure Protection - DLK (2022-23) | 171.2 | 59.6105 | -111.5895 | -65.18%
13252208 | 2022 | 2023 | Replace Disconnects - Various | Replace Disconnect Switches - Various (2022-23) | 1235.7013 | 1002.3861 | -233.3152 | -18.88%
13252211 | 2022 | 2023 | Upgrade Reclosing Circuit Brea | Upgrade Reclosing Circuit Breakers - SSD B1L03 & HRD B1L65 (2022-23) | 210.9698 | 231.818 | 20.8483 | 9.882%
13252210 | 2022 | 2023 | Replace Station Lighting - BUC | Upgrade Station Lighting - BUCTS and HWDTS (2022-23) | 202.6364 | 314.9315 | 112.2951 | 55.42%
13252212 | 2022 | 2023 | Replace Instrument Transformer | Replace Instrument Transformers - Various (2022-23) | 402.3595 | 487.9087 | 85.5492 | 21.26%
14012290 | 2022 | 2023 | Rplc Diesel Plant RF MAK SUPP | Makkovik Diesel Generating Station Roof Replacement - Supplemental | 891.6241 | 733.8948 | -157.7293 | -17.69%
12962291 | 2022 | 2023 | Lt Stage Blades Holyrood Supp | Purchase Turbine Last Stage Blades - Holyrood - Supplemental | 1432.6215 | 1595.5372 | 162.9157 | 11.37%
12842290 | 2022 | 2023 | USL Rotor Rim Shrinking (Supp) | Upper Salmon Hydroelectric Generating Station Rotor Rim Shrink and Stator Recentering - Supplemental | 4236.3289 | 9146.6379 | 4910.3091 | 115.9%
12972290 | 2022 | 2023 | HRD SUPP Rpl Tank Farm Undgrd | Holyrood Tank Farm Underground Firewater System Replacment - Supplemental | 1469.6289 | 1262.9116 | -206.7173 | -14.07%
12972292 | 2022 | 2023 | HRD SUPP Day Tank Refurb | Holyrood Inspect and Refurbish Day Tank - Supplemental | 846.7719 | 942.1432 | 95.3712 | 11.26%
12422309 | 2023 | 2023 | Rplc standalone PHX phone sys | Replace Standalone PBX Phone Systems (2023) | 175.5 | 208.9658 | 33.4658 | 19.07%
12422305 | 2023 | 2023 | Purchase Tools and Equipment | Purchase Tools and Equipment Less than $50,000 (2023) - Telecontrol | 40.4 | 47.4011 | 7.0011 | 17.33%
12422303 | 2023 | 2023 | Upgr Site Facilities VAR 23 | Upgrade Site Facilities (2023) | 45.2 | 47.1129 | 1.9129 | 4.232%
12422308 | 2023 | 2023 | Purchase Mobile Devices Hydro | Purchase Mobile Devices (2023) | 83.4 | 116.3509 | 32.9509 | 39.51%
20682305 | 2023 | 2023 | Prfm soft upgrs/minor echan 23 | Perform Software Upgrades and Minor Enhancements (2023) | 451.2 | 357.3164 | -93.8836 | -20.81%
20682303 | 2023 | 2023 | Upgrade Core IT/OT Infrastruct | Upgrade Core OT Infrastructure (2023) | 171.7 | 255.2619 | 83.5619 | 48.67%
20682304 | 2023 | 2023 | Upde Cyber Security Software23 | Update Cyber Security Infrastructure (2023) | 232.1 | 230.5331 | -1.5669 | -0.6751%
12962302 | 2023 | 2023 | Overhaul Pumps Holyrood 23 | Overhaul Pumps (2023) - Holyrood | 742.4 | 1429.8882 | 687.4882 | 92.6%
12962303 | 2023 | 2023 | Tools and Equip. Thermal 23 | Purchase Tools and Equipment Less than $50,000 (2023) - Thermal Plants | 55.1 | 122.782 | 67.682 | 122.8%
13332301 | 2023 | 2023 | Diesel In-Service Failures 23 | Diesel In-Service Failures (2023) | 480.4 | 727.1768 | 246.7768 | 51.37%
12972301 | 2023 | 2023 | HRD-Boiler Cond Assessmt/Upgrd | Boiler Condition Assessment and Miscellaneous Upgrades (2023) - Holyrood | 2926.6 | 4336.3612 | 1409.7612 | 48.17%
12962305 | 2023 | 2023 | Refurb Workshop Roof - HRD | Refurbish Workshop Roof (2023) - Holyrood | 243.7 | 237.7527 | -5.9473 | -2.44%
12422301 | 2023 | 2023 | Replace RTUs (2023) - Various | Replace Remote Terminal Units (2023) | 179.7 | 234.4336 | 54.7336 | 30.46%
13402301 | 2023 | 2023 | Purchase Tools & Equipment -GT | Purchase Tools and Equipment Less than $50,000 (2023) - Gas Turbine | 18.3 | 16.6577 | -1.6423 | -8.974%
21882301 | 2023 | 2023 | Gas Turbine In-Service Failure | Gas Turbine In-Service Failures (2023) | 344.2 | 3606.7459 | 3262.5459 | 947.9%
13252301 | 2023 | 2023 | Terminal Stat In-Serv Failures | Terminal Station In-Service Failures (2023) | 1300 | 2846.6948 | 1546.6948 | 119%
12982301 | 2023 | 2023 | Remove Safety Hazards - Var | Remove Safety Hazards (2023) | 198.2 | 207.0342 | 8.8342 | 4.457%
12932301 | 2023 | 2023 | Hydraulic In-Serv Failures 23 | Hydraulic In-Service Failures (2023) | 1500 | 4081.0911 | 2581.0911 | 172.1%
12932303 | 2023 | 2023 | Upgr Public Safety Dams BDE 23 | Upgrade Public Safety Around Dams and Waterways (2023) | 482.1 | 795.4595 | 313.3595 | 65%
12962301 | 2023 | 2023 | Thermal In-Service Failures 23 | Thermal In-Service Failures (2023) | 3300 | 2887.8278 | -412.1722 | -12.49%
12422302 | 2023 | 2023 | Rplc Network Comms EQ 2023 | Replace Network Communications Equipment (2023) | 189 | 238.6899 | 49.6899 | 26.29%
12972303 | 2023 | 2023 | Upgr Bio-Green Sewage HRD | Refurbish BioGreen Sewage System (2023) - Holyrood | 256.6 | 504.9448 | 248.3448 | 96.78%
14012302 | 2023 | 2023 | SBN-Dsl Genset Rplc Unit 2056 | Diesel Genset Replacement Program (2023-2025) | 543 | 474.6987 | -68.3013 | -12.58%
12922301 | 2023 | 2023 | SRS - Replace Emergency Lift | Replace Emergency Lift (2023) - Salmon River Spillway | 49.8 | 90.7418 | 40.9418 | 82.21%
20082301 | 2023 | 2023 | Purchase office equipment <50k | Purchase Office Equipment Less Than $50,000 (2023) | 75.6 | 55.6933 | -19.9067 | -26.33%
12932305 | 2023 | 2023 | Pur Tools & Eq. <50K Hydraulic | Purchase Tools and Equipment Less than $50,000 (2023) - Hydraulic Plants | 144.9 | 149.9791 | 5.0791 | 3.505%
13072301 | 2023 | 2023 | Meters and Metering Equipment | Purchase Meters and Metering Equipment (2023) | 226.6 | 202.9578 | -23.6422 | -10.43%
12422306 | 2023 | 2023 | Rplc Batt Banks & Chargers-VAR | Replace 48 V Battery Banks and Chargers (2023) | 439.7 | 418.9626 | -20.7374 | -4.716%
13332302 | 2023 | 2023 | Overhaul Diesel Units-Var | Overhaul Diesel Units (2023) | 1502 | 1347.2625 | -154.7375 | -10.3%
12942302 | 2023 | 2023 | BDE unit 7 lvl 2 cond asst | Unit 7 Condition Assessment (2023) - Bay d'Espoir | 597.5 | 379.4053 | -218.0947 | -36.5%
12902301 | 2023 | 2023 | Hydraulic Unit 1&3 Overhaul | Hydraulic Unit Overhauls Program (2023) | 975.7 | 1289.4118 | 313.7118 | 32.15%
13492301 | 2023 | 2023 | Wood Pole Line Management Prgm | Wood Pole Line Management Program (2023) | 2824.4 | 5085.8377 | 2261.4377 | 80.07%
13492302 | 2023 | 2023 | Transmission Inservice Failure | Transmission In-Service Failures (2023) | 151.7 | 193.5891 | 41.8891 | 27.61%
12812102 | 2021 | 2024 | HLK-Annunciator Replacement | HLK-Annunciator Replacement | 371.1331 | 483.6696 | 112.5365 | 30.32%
13402001 | 2020 | 2024 | HRD GT-Combustor Inpection | Perform Combustor Inspection - Holyrood Gas Turbine | 5473.5432 | 5120.9907 | -352.5525 | -6.441%
14112203 | 2022 | 2024 | Diesel Genset Rplc Unit STL | Diesel Genset Replacement Unit 2039 - St. Lewis | 1980.8 | 1580.0628 | -400.7372 | -20.23%
13332202 | 2022 | 2024 | Instll Fire Prtct Diesel RAM | Install Fire Protection in Diesel Plants (2022-2023) - Ramea | 1928.8 | 1515.6301 | -413.1699 | -21.42%
13962203 | 2022 | 2024 | Lab City L22Voltage Conversion | Labrador City L22 Voltage Conversion (2022-2023) | 1491.2 | 2175.6355 | 684.4355 | 45.9%
13462201 | 2022 | 2024 | Purchase 46 ft Category B | Purchase 46' Material Handler Aerial Device on Track Unit | 758 | 740.9146 | -17.0854 | -2.254%
13462202 | 2022 | 2024 | Purchase 85' Material Handler | Purchase 85' Material Handler Aerial Device on Track Unit | 1353.9 | 1201.724 | -152.176 | -11.24%
14012303 | 2023 | 2024 | Replace Building Ext Postville | Replace Building Exterior (2023-2024) - Postville | 683.3 | 1200.8386 | 517.5386 | 75.74%
13882301 | 2023 | 2024 | Cond asst Condensers 1&2 WABTS | Major Condition Assessment and Miscellaneous Refurbishments Synchronous Condenser 1 and 2 (2023-2024) - Wabush Terminal Station | 1093.3 | 1049.263 | -44.037 | -4.028%
13462305 | 2023 | 2024 | Replace HVAC Unit BIF | Replace HVAC System (2023-2024) - Bishop's Falls | 172.2 | 274.4595 | 102.2594 | 59.38%
14012390 | 2023 | 2024 | CHT/MSH rplc unit 2090/2044 | Replace Unit 2090/2044 - Charlottetown and Mary's Harbour | 401.022 | 492.5594 | 91.5374 | 22.83%
12962390 | 2023 | 2024 | Pur/RplcLT Blades Unit 1&2 SUP | Holyrood Thermal Generating Station Unit 1 and Unit 2 Turbine Last Stage Blades - Supplemental | 6408.7 | 6673.0654 | 264.3654 | 4.125%
12962292 | 2022 | 2024 | Upgrd Tur Ctrl Sys Unit 2 SUPP | Holyrood Upgrade Turbine Control System Unit 2 - Supplemental | 726 | 752.1551 | 26.1551 | 3.603%
12422304 | 2023 | 2024 | Rplc Pwr Ln Carrier (2023-24) | Replace Power Line Carrier (2023–2024) - TL223 and TL224 | 957.7 | 879.4252 | -78.2748 | -8.173%
21842301 | 2023 | 2024 | Rpl Human Machine Inter 2023 | Replace Human Machine Interface (2023) - Happy Valley Gas Turbine | 138.6 | 166.2288 | 27.6288 | 19.93%
21842302 | 2023 | 2024 | Rpl Oil Mist Seperator 23/24 | Replace Oil Mist Separator (2023-2024) - Happy Valley Gas Turbine | 400.6 | 179.0169 | -221.5831 | -55.31%
13252302 | 2023 | 2024 | Instll Fire Protect 230kv- DLK | Install Fire Protection in 230 kV Stations (2023-2024) - Deer Lake | 614.5 | 534.4027 | -80.0973 | -13.03%
13252305 | 2023 | 2024 | InstallCAT T1S oil spill cont | Install Oil Spill Containment Transformer T1S (2023-2024) - Cat Arm | 581.6 | 873.8137 | 292.2137 | 50.24%
13462403 | 2024 | 2024 | Replace Grader V9829 BDE | Replace Grader Unit V9829 (2024) - Bay d'Espoir | 836.7 | 872.9393 | 36.2393 | 4.331%
12422410 | 2024 | 2024 | Install Anemometer Cat Arm 24 | Install Anemometer (2024) - Cat Arm | 68.6 | 100.7424 | 32.1424 | 46.85%
12972403 | 2024 | 2024 | HRD Marine Term Arm 24 | Overhaul Marine Terminal Loading Arms (2024) - Holyrood | 511 | 468.3003 | -42.6997 | -8.356%
12422420 | 2024 | 2024 | Replace CCTV System 24 | Replace CCTV Cameras (2024) | 317.6 | 369.7161 | 52.1161 | 16.41%
12422421 | 2024 | 2024 | Replace SONET Multiplexers 24 | Replace SONET Multiplexors (2024) | 430.4 | 398.6951 | -31.7049 | -7.366%
12922402 | 2024 | 2024 | Rpl Timber Crib 24 Burnt Dam | Replace Timber Crib and Insulation (2024) - Burnt Dam Spillway | 161.8 | 100.0608 | -61.7392 | -38.16%
12962406 | 2024 | 2024 | Refurb Fuel Oil Store 4 HRD | Refurbish Fuel Oil Storage Tank 4 (2024) - Holyrood | 1920 | 2150.8605 | 230.8605 | 12.02%
20082401 | 2024 | 2024 | Lvl 2 EV Chargers - HYP 24 | Upgrade Fleet Infrastructure Program - Install L2 EV Chargers (2024) - Hydro Place | 322.635 | 143.5823 | -179.0527 | -55.5%
12842401 | 2024 | 2024 | Penstock lvl2 Cond asst 24 USL | Penstock Level II Condition Assessment (2024) - Upper Salmon | 382.8 | 149.2214 | -233.5787 | -61.02%
12952401 | 2024 | 2024 | GCL-Overhaul Hydraulic units24 | Overhaul Hydraulic Units (2024) | 323.8 | 376.8143 | 53.0143 | 16.37%
13252010 | 2020 | 2024 | Replace Transformer T7 - HRD | Replace Transformer T7 - HRD | 2678.14 | 4701.0658 | 2022.9258 | 75.53%
13882202 | 2022 | 2024 | IOC SCADA Data Link | IOC SCADA Data Link | 28.218 | 28.8798 | 0.66184 | 2.345%
13252022 | 2020 | 2024 | Valentine Gold Interconnection | Valentine Gold Interconnection - Supplemental | 16347.4 | 16148.7257 | -198.6743 | -1.215%
12972204 | 2022 | 2024 | Replace Underground Fire Water | Replace Underground Fire Water Distribution System - Holyrood | 1706.3 | 3080.4524 | 1374.1524 | 80.53%
12842301 | 2023 | 2024 | Rpl PHstation srvice panel USL | Replace Powerhouse Station Service Panel (2023-2024) - Upper Salmon | 1568.5 | 2526.6794 | 958.1794 | 61.09%
14112290 | 2022 | 2024 | CHT Winterize Unit 2102 SUPP | CHT Winterize Unit 2102 and Install Mobile - Supplemental | 1314.7 | 1786.7325 | 472.0325 | 35.9%
13492490 | 2024 | 2024 | TL201 Dyn line rating sys<750k | Install Line Monitoring System (2024) - TL201 | 469.902 | 455.1293 | -14.7727 | -3.144%
20082404 | 2024 | 2024 | Upgr HVAC Network Eng/Con HYP | Upgrade HVAC Supervisory Controllers (2024) - Hydro Place | 149.6 | 136.9756 | -12.6244 | -8.439%
12962490 | 2024 | 2024 | Instl L1 Blade Unit 1 Turb HRD | Install L-1 Blades Unit 1 (2024) Holyrood | 581.263 | 512.496 | -68.767 | -11.83%
14282490 | 2024 | 2024 | TL226,TL239,TL259 WIDEN ROW | Widen Rights-of-Way of Transmission Lines TL239 & TL259 (2024) | 668.914 | 624.2195 | -44.6945 | -6.682%
12812401 | 2024 | 2025 | Flatten Downstream Slope 24/25 | Flatten Downstream Slope (2024-2025) - Hinds Lake | 3229.5 | 1821.7461 | -1407.7539 | -43.59%
12842501 | 2025 | 2025 | Inst Power Canal SBoom 25 USL | Install Power Canal Public Safety Boom (2025) - Upper Salmon | 463.8 | 268.6314 | -195.1686 | -42.08%
13252412 | 2024 | 2025 | Upgr Reclosing CBreakers TL247 | Replace Circuit Breaker Reclosing Controllers (2024–2025) - TL247 | 328.2 | 238.2979 | -89.9021 | -27.39%
20082403 | 2024 | 2025 | General Prop Rehab HYP | General Property Rehabilitation (2024) - Hydro Place | 234 | 401.482 | 167.482 | 71.57%
13252407 | 2024 | 2025 | Install Proct 230KV Voisey's | Install Fire Protection in 230 kV Stations (2024–2025) - Voisey's Bay | 652.8 | 504.362 | -148.438 | -22.74%
12422504 | 2025 | 2025 | Replace CCTV Cameras 25 | Install CCTV Systems (2025) | 440.1 | 353.6907 | -86.4093 | -19.63%
12902502 | 2025 | 2025 | Lvl2 Cond Asst Phouse 25 CAT | Perform Level 2 Condition Assessment - Powerhouse Slope (2025) - Cat Arm | 169.4 | 138.1864 | -31.2137 | -18.43%
18192501 | 2025 | 2025 | Pur Surveying soft/equip 25 | Purchase Surveying Software and Equipment (2025) | 316.4 | 286.6651 | -29.7349 | -9.398%
12422412 | 2024 | 2025 | Rpl MDR8000 Microwave Radios | Replace MDR8000 Microwave Radios (2024-2025) | 1453.8 | 1424.1702 | -29.6298 | -2.038%
13402502 | 2025 | 2025 | Inps Fuel Tanks 25 HRD | Inspect Fuel Tanks (2025) - Holyrood | 608 | 575.507 | -32.493 | -5.344%
12932406 | 2024 | 2025 | Rpl PWhouse Air Con BDE 24/25 | Replace Powerhouse 1 Air Conditioning Unit (2024-2025) - Bay d'Espoir | 289 | 291.0157 | 2.0157 | 0.6975%
12932404 | 2024 | 2025 | Refurb Intake Gate 1 24/25 BDE | Refurbish Intake 1 (2024-2025) - Bay d'Espoir | 3344 | 3418.668 | 74.668 | 2.233%
13252312 | 2023 | 2025 | Upg Station Lighting Var 23/24 | Replace Terminal Station Lighting (2023-2024) | 917.4 | 1432.1492 | 514.7492 | 56.11%
12972501 | 2025 | 2025 | LV2 Cond asst Stage 1&2 WSump | Perform Level 2 Condition Assessment - Stage I & II Cooling Water Sump Structures (2025) - Holyrood | 1747.033 | 1838.5639 | 91.5309 | 5.239%
12422507 | 2025 | 2025 | Refurb Meterological STN 25 | Refurbish Meteorological Stations (2025) | 167.8 | 179.8792 | 12.0792 | 7.199%
14012304 | 2023 | 2025 | Upgrade Fuel Storage Nain | Replace Intermediate Fuel Storage Tanks (2023-2024) - Nain | 721.1 | 1313.8397 | 592.7397 | 82.2%
12932304 | 2023 | 2025 | BDE Water Sys Assessment/Upgr | Water System Condition Assessment and Upgrades (2023) - Bay d'Espoir | 665.9 | 1387.0284 | 721.1284 | 108.3%
12972404 | 2024 | 2025 | Refurb Outbuilding&Powerhouse | Refurbish Outbuilding and Powerhouse Building Envelopes (2024-2025) - Holyrood | 1195.6 | 1292.9245 | 97.3245 | 8.14%
13402402 | 2024 | 2025 | Constr Main Platform 24/25 GT | Construct Maintenance Platform (2024-2025) - Holyrood Gas Turbine | 359.2 | 404.9963 | 45.7963 | 12.75%
12972401 | 2024 | 2025 | Upgr UPS 1&2 HRD 24/25 | Upgrade UPS 1 & 2 (2024-2025) - Holyrood | 370.6 | 423.0747 | 52.4747 | 14.16%
12932201 | 2022 | 2025 | BDE- TUBE SUB LVL1-2 COND ASST | Draft Tube Deck Substructure Level 2 Condition Assessment | 343.6 | 984.9386 | 641.3386 | 186.7%
12902401 | 2024 | 2025 | Rpl Annun panels 24/25 cat arm | Replace Annunciator Panels (2024-2025) - Cat Arm | 351.4 | 603.0922 | 251.6922 | 71.63%
12922302 | 2023 | 2025 | Rpl Diesel Genset Ebbegunbaeg | Replace Diesel Genset 1 (2023-2024) - Ebbegunbaeg | 1026.3 | 1130.5443 | 104.2443 | 10.16%
20682510 | 2025 | 2025 | Upgr Work Protection Code25/26 | Upgrade Work Protection Code Application (2025-2026) | 708.64 | 592.214 | -116.426 | -16.43%
13332501 | 2025 | 2025 | Replace Roof Grey River 25 | Replace Roof (2025) - Grey River | 390.8 | 519.7822 | 128.9822 | 33%
13252405 | 2024 | 2025 | Upg Station Lighting Var 24/25 | Upgrade Station Lighting (2024-2025) - Bottom Waters, Deer Lake, Doyles, Indian River, and Western Avalon Terminal Stations | 520.6 | 680.1284 | 159.5284 | 30.64%
12922401 | 2024 | 2025 | Refurb Surge Tank 1 24/25 BDE | Refurbish Surge Tank 1 (2024-2025) - Bay d'Espoir | 2287.2 | 3485.6652 | 1198.4652 | 52.4%
21882503 | 2025 | 2025 | Inspt fuel tanks25 Stephenvile | Inspect Fuel Tanks (2025) - Stephenville | 676.9 | 1048.1662 | 371.2663 | 54.85%
21882402 | 2024 | 2025 | Inspt fuel tanks 24 HardwoodGT | Inspect Fuel Tanks (2024) - Hardwoods Gas Turbines | 692.9 | 1038.7661 | 345.8661 | 49.92%
12962403 | 2024 | 2025 | Upgr Unit 1 contr sys24/25 HRD | Upgrade Unit 1 Control System (2024-2025) - Holyrood | 652.6 | 732.5407 | 79.9407 | 12.25%
12932302 | 2023 | 2025 | Refurb SuprStructure SRS 23/24 | Refurbish Superstructure (2023-2024) - Salmon River Spillway | 2828.3 | 959.4117 | -1868.8884 | -66.08%
13252310 | 2023 | 2025 | Upgr Data Alarm system Buchans | Replace Data Alarm System Annunciators (2023) - Buchans | 166 | 425.808 | 259.808 | 156.5%
12422406 | 2024 | 2025 | Upgrade SCADA Network (2024) | Upgrade SCADA Network (2024) | 402.3 | 843.668 | 441.368 | 109.7%
14012101 | 2021 | 2025 | NAN-Diesel Genset Replac-21/22 | Diesel Genset Replacements (2021-2022) | 2846.8 | 3346.7633 | 499.9633 | 17.56%
13882201 | 2022 | 2025 | Install Fault Recorder WABTS | Upgrade Fault Recorders - WABTS (2022-2023) | 422.4 | 656.9887 | 234.5887 | 55.54%
13252309 | 2023 | 2025 | Ugr Breakr Fail Proc SSD 230KV | Install Breaker Failure Protection (2023-2024) - Sunnyside | 289.7 | 1477.4993 | 1187.7993 | 410%
13072201 | 2022 | 2025 | Replace Metering System | Replace Metering System | 5875.8 | 9295.4733 | 3419.6733 | 58.2%
|  |  |  | TOTAL | 1055746.0316 | 999209.8798 | -56536.1518 | -5.355%

## Original Statistical Analysis
Values
Var % | CBA / CAPEX Title | Sum of Budget | Sum of Actual Cost | Category | Chart Data | Stats Data
-100% | Integrate Renewable PH2 - Mary's Harbour | 498 | 1.4552e-14 | (>=100%) | -100% | -100% | 0
-100% | Wabush L34 and L35 Protective Relays - CIAC | 259.302 | 0 | (>=100%) | -100% | -100% | 0
-92.03% | Refurbish Hydraulic Structures - BDE (2019-20) | 5036.5 | 401.279 | (99.9%-90%) | -92.03% | -92.03% | 0
-88.55% | Purchase Office Equipment | 60.9 | 6.9706 | (89.9%-80%) | -88.55% | -88.55% | 0
-81.57% | Replace Insulators - Various (2019-20) | 989 | 182.2252 | (89.9%-80%) | -81.57% | -81.57% | 0
-81.38% | Security Improvements - Hydro Place | 45.5 | 8.47 | (89.9%-80%) | -81.38% | -81.38% | 0
-81.17% | Stage 2 Emergency Diesel Generator Refurbishment - Holyrood | 49.5 | 9.3213 | (89.9%-80%) | -81.17% | -81.17% | 0
-79.76% | Replace Insulators - Various Sites | 971.9 | 196.665 | (79.9%-70%) | -79.76% | -79.76% | 0 | Min | -100%
-76.22% | Replace Insulators - Various Sites | 961.8 | 228.7218 | (79.9%-70%) | -76.22% | -76.22% | 0 | Max | 947.9% | Count of Chart Data
-73.81% | Replace Surge Arrestors - Various Sites | 361.8 | 94.7661 | (79.9%-70%) | -73.81% | -73.81% | 0 | Var | 35.87% | Category | Total
-72.69% | Replace Units 1-6 Generator Bearing Cover Seals - BDE | 656.7 | 179.374 | (79.9%-70%) | -72.69% | -72.69% | 0 | Std Dev | 59.89% | (>=100%) | 2
-70.8% | Replace Office Desk Chairs - Hydro Place | 90 | 26.2783 | (79.9%-70%) | -70.8% | -70.8% | 0 | Avg | 1.36% | (19.9%-10%) | 73
-68.88% | Replace Light- and Heavy-Duty Vehicles (2021-2022) | 5909.7557 | 1838.9963 | (69.9%-60%) | -68.88% | -68.88% | 0 | Count | 591 | (29.9%-20%) | 55
-67.2% | Purchase Office Equipment | 62.264 | 20.4248 | (69.9%-60%) | -67.2% | -67.2% | 0 | Lower SD | -58.53% | (39.9%-30%) | 50
-67.01% | Replace 60 kW Diesel Generator - Burnt Dam | 1161.7 | 383.2038 | (69.9%-60%) | -67.01% | -67.01% | 0 | Upper SD | 61.25% | (49.9%-40%) | 32
-66.08% | Refurbish Superstructure (2023-2024) - Salmon River Spillway | 2828.3 | 959.4117 | (69.9%-60%) | -66.08% | -66.08% | 0 |  |  | (59.9%-50%) | 23
-66.03% | Upgrade Cables - Various (2020) | 473.611 | 160.902 | (69.9%-60%) | -66.03% | -66.03% | 0 |  |  | (69.9%-60%) | 12
-65.95% | Install Recloser Remote Control (2019-2020) - Rocky Harbour | 386 | 131.4482 | (69.9%-60%) | -65.95% | -65.95% | 0 |  |  | (79.9%-70%) | 5
-65.18% | Install Breaker Failure Protection - DLK (2022-23) | 171.216 | 59.6105 | (69.9%-60%) | -65.18% | -65.18% | 0 |  |  | (89.9%-80%) | 4
-65.18% | Install Breaker Failure Protection - DLK (2022-23) | 171.2 | 59.6105 | (69.9%-60%) | -65.18% | -65.18% | 0 |  |  | (9.9%-0.01%) | 89
-64.73% | Replace Disconnects - Various Sites | 3369.9 | 1188.4301 | (69.9%-60%) | -64.73% | -64.73% | 0 |  |  | (99.9%-90%) | 1
-63.84% | Hydraulic In-Service Failures | 1251.1 | 452.4231 | (69.9%-60%) | -63.84% | -63.84% | 0 |  |  | >100% | 19
-61.02% | Penstock Level II Condition Assessment (2024) - Upper Salmon | 382.8 | 149.2214 | (69.9%-60%) | -61.02% | -61.02% | 0 |  |  | >500% | 1
-60.98% | Install Infrared Viewports - VAR | 257.5 | 100.4698 | (69.9%-60%) | -60.98% | -60.98% | 0 |  |  | 0%-9.9% | 78
-59.97% | Refurbish 230kV TS - WAB | 4969.8 | 1989.1801 | (59.9%-50%) | -59.97% | -59.97% | 0 |  |  | 10%-19.9% | 43
-58.64% | Additions for Load Growth - Makkovik and Rigolet | 730.1 | 301.9776 | (59.9%-50%) | -58.64% | -58.64% | 0 |  |  | 20%-29.9% | 24
-57.96% | Purchase Tools and Equipment less than $50,000 | 18.8 | 7.9027 | (59.9%-50%) | -57.96% | -57.96% | 1 |  |  | 30%-39.9% | 24
-56.65% | Additions for Load - Distribution System | 186.7 | 80.9272 | (59.9%-50%) | -56.65% | -56.65% | 1 |  |  | 40%-49.9% | 14
-56.11% | Gas Turbine Life Extension - Stephenville | 1353.2 | 593.922 | (59.9%-50%) | -56.11% | -56.11% | 1 |  |  | 50%-59.9% | 17
-55.95% | Additions for Load Growth - Happy Valley | 505 | 222.4552 | (59.9%-50%) | -55.95% | -55.95% | 1 |  |  | 60%-69.9% | 7
-55.82% | Refurbish Hydraulic Structures - Various | 4367.3 | 1929.5158 | (59.9%-50%) | -55.82% | -55.82% | 1 |  |  | 70%-79.9% | 8
-55.5% | Upgrade Fleet Infrastructure Program - Install L2 EV Chargers (2024) - Hydro Place | 322.635 | 143.5823 | (59.9%-50%) | -55.5% | -55.5% | 1 |  |  | 80%-89.9% | 7
-55.39% | Upgrade Fault Recorders - BHL (2019) | 623.5 | 278.1333 | (59.9%-50%) | -55.39% | -55.39% | 1 |  |  | 90%-99.9% | 3
-55.31% | Replace Oil Mist Separator (2023-2024) - Happy Valley Gas Turbine | 400.6 | 179.0169 | (59.9%-50%) | -55.31% | -55.31% | 1 |  |  | Grand Total | 591
-54.75% | Install Fire Protection in 230 kV Stations - OPD (2019-20) | 883.3 | 399.6995 | (59.9%-50%) | -54.75% | -54.75% | 1
-54.56% | Install Protective Guards in Turbine Pits - BDE, USL | 541 | 245.8418 | (59.9%-50%) | -54.56% | -54.56% | 1
-54.17% | Replace Lignt and Heavy Duty Vehicles - Various (2020) | 8848.5694 | 4055.059 | (59.9%-50%) | -54.17% | -54.17% | 1
-53.6% | Upgrade Power Transformers - Various Sites | 4829 | 2240.7098 | (59.9%-50%) | -53.6% | -53.6% | 1
-53.43% | Replace Tracks - V7271 - Supplemental | 96.62 | 45 | (59.9%-50%) | -53.43% | -53.43% | 1
-53.35% | Upgrade Reclosing Circuit Breakers B12L65 & B2L68 - HRD | 367.6 | 171.4778 | (59.9%-50%) | -53.35% | -53.35% | 1
-52.81% | Replace Disconnect Switches - Various Sites | 2458.5 | 1160.2887 | (59.9%-50%) | -52.81% | -52.81% | 1
-52.74% | Line Depot Condition Assessment and Refurbishment Program - Various Sites | 1458.8 | 689.3875 | (59.9%-50%) | -52.74% | -52.74% | 1
-51.93% | Replace 66 kV Station Service Feed - Holyrood | 1261.4 | 606.3337 | (59.9%-50%) | -51.93% | -51.93% | 1
-50.95% | Gas Turbine Life Extension - Hardwoods | 956.7 | 469.2565 | (59.9%-50%) | -50.95% | -50.95% | 1
-50.71% | Install Fire Protection in 230 kV Stations - Various Sites | 764.9 | 377.0449 | (59.9%-50%) | -50.71% | -50.71% | 1
-50.47% | Purchase Tools and Equipment less than $50,000 | 93.4 | 46.2635 | (59.9%-50%) | -50.47% | -50.47% | 1
-50.21% | Upgrade Aluminum Support Structures - Holyrood | 287.6 | 143.188 | (59.9%-50%) | -50.21% | -50.21% | 1
-49.64% | Replace Units 1-6 Generator Bearing Cover Seals - BDE | 296.4675 | 149.2869 | (49.9%-40%) | -49.64% | -49.64% | 1
-49.28% | Upgrade Cables - various (2021) | 496.693 | 251.938 | (49.9%-40%) | -49.28% | -49.28% | 1
-48.97% | Install Breaker Failure Protection - STB, STD (2019-20) | 582.6 | 297.2845 | (49.9%-40%) | -48.97% | -48.97% | 1
-47.65% | Upgrade Compressed Air System - Holyrood Gas Turbine | 388.4 | 203.315 | (49.9%-40%) | -47.65% | -47.65% | 1
-47.64% | Replace Vent Chambers - BDE | 380.7 | 199.3452 | (49.9%-40%) | -47.64% | -47.64% | 1
-46.34% | Purchase Office Equipment | 38 | 20.3895 | (49.9%-40%) | -46.34% | -46.34% | 1
-45.93% | Upgrade Aluminum Support Structures - Holyrood | 352.9 | 190.8158 | (49.9%-40%) | -45.93% | -45.93% | 1
-45.47% | Replace Roof - Hydro Place | 923.4 | 503.5026 | (49.9%-40%) | -45.47% | -45.47% | 1
-44.96% | Replace Protective Relays - Various Sites | 7535.5 | 4147.7088 | (49.9%-40%) | -44.96% | -44.96% | 1
-44.59% | Condition Assessment for Submarine Cable - Farewell Head to Change Islands | 300.1 | 166.2941 | (49.9%-40%) | -44.59% | -44.59% | 1
-44.43% | Install Asset Health Monitoring System - Upper Salmon | 641.4 | 356.4498 | (49.9%-40%) | -44.43% | -44.43% | 1
-44.06% | Replace Radomes - Various | 384.512 | 215.1132 | (49.9%-40%) | -44.06% | -44.06% | 1
-44.05% | Inspect Chemical Tanks - Holyrood | 919.8 | 514.6453 | (49.9%-40%) | -44.05% | -44.05% | 1
-43.59% | Flatten Downstream Slope (2024-2025) - Hinds Lake | 3229.5 | 1821.7461 | (49.9%-40%) | -43.59% | -43.59% | 1
-43.51% | Replace Power Transformers - Oxen Pond | 1147.6 | 648.3048 | (49.9%-40%) | -43.51% | -43.51% | 1
-43.36% | Install Fire Protection in 230 kV Stations - Massey Drive | 921.499 | 521.9126 | (49.9%-40%) | -43.36% | -43.36% | 1
-43.23% | Replace Instrument Transformers - Various Sites | 1181.1 | 670.5452 | (49.9%-40%) | -43.23% | -43.23% | 1
-42.91% | Replace Disconnects - Various (2019-20) | 2350.7 | 1341.9522 | (49.9%-40%) | -42.91% | -42.91% | 1
-42.83% | Air Receivers Condition Assessment and Upgrades - Holyrood | 336.5 | 192.3849 | (49.9%-40%) | -42.83% | -42.83% | 1
-42.76% | Install Fault Recorders - HVY (2020-21) | 687.951 | 393.8016 | (49.9%-40%) | -42.76% | -42.76% | 1
-42.71% | Install Fire Protection in 230 kV Stations - STB (2020-21) | 681.195 | 390.2868 | (49.9%-40%) | -42.71% | -42.71% | 1
-42.54% | Replace Control Cable PH1 - BDE (2019) | 415.6 | 238.7892 | (49.9%-40%) | -42.54% | -42.54% | 1
-42.26% | Replace Diesel Plant Roof - LAL/STA | 2313.5555 | 1335.8991 | (49.9%-40%) | -42.26% | -42.26% | 1
-42.08% | Install Power Canal Public Safety Boom (2025) - Upper Salmon | 463.8 | 268.6314 | (49.9%-40%) | -42.08% | -42.08% | 1
-41.78% | Replace Recloser - Wabush | 199.2 | 115.9747 | (49.9%-40%) | -41.78% | -41.78% | 1
-41.63% | Install Hydrometeorological Equipment - Various Sites | 314.1 | 183.3448 | (49.9%-40%) | -41.63% | -41.63% | 1
-41.48% | Install Pole Storage Ramps - Various Sites | 816.4 | 477.7208 | (49.9%-40%) | -41.48% | -41.48% | 1
-41.07% | Replace Instrument Transformers - Various Sites | 1345.3 | 792.7631 | (49.9%-40%) | -41.07% | -41.07% | 1
-40.88% | Replace Interior and Exterior Coating on Surge Tank 1 - BDE | 3564.1 | 2107.1363 | (49.9%-40%) | -40.88% | -40.88% | 1
-40.7% | Install Recloser Remote Control (2021-2022) - Various | 360.4826 | 213.7629 | (49.9%-40%) | -40.7% | -40.7% | 1
-40.6% | Upgrade Cables - Various (2019) | 500 | 297.006 | (49.9%-40%) | -40.6% | -40.6% | 1
-40.15% | Upper Salmon -Overhaul Turbine/Gen. Unit | 729.1 | 436.349 | (49.9%-40%) | -40.15% | -40.15% | 1
-39.92% | Security Improvements - Hydro Place | 47.1 | 28.2976 | (39.9%-30%) | -39.92% | -39.92% | 1
-39.42% | Install Infrared Scanning Ports - Happy Valley Gas Turbine | 87.5574 | 53.0414 | (39.9%-30%) | -39.42% | -39.42% | 1
-39.35% | Additions for Load Growth - Postville - Black Tickle | 1453.8 | 881.7762 | (39.9%-30%) | -39.35% | -39.35% | 1
-39.27% | Replace Protective Relays - Various (2019-20) | 4579.4 | 2781.0307 | (39.9%-30%) | -39.27% | -39.27% | 1
-38.78% | Refurbish 230 kV Terminal Station Part 2 - WAB (2020-21) | 2465.576 | 1509.4403 | (39.9%-30%) | -38.78% | -38.78% | 1
-38.57% | Install Pole Storage Ramps - Wabush | 301.7 | 185.3397 | (39.9%-30%) | -38.57% | -38.57% | 1
-38.16% | Replace Timber Crib and Insulation (2024) - Burnt Dam Spillway | 161.8 | 100.0608 | (39.9%-30%) | -38.16% | -38.16% | 1
-37.97% | Upgrade Fault Recorder System for 2018- Various Sites | 1026.9 | 636.9772 | (39.9%-30%) | -37.97% | -37.97% | 1
-37.9% | Refurbish Wabush Terminal Station | 5548.5 | 3445.6882 | (39.9%-30%) | -37.9% | -37.9% | 1
-37.8% | Upgrade Warehouse Lighting - Bishop's Falls | 195.6 | 121.6659 | (39.9%-30%) | -37.8% | -37.8% | 1
-37.52% | Replace Protective Relays - Various (2022-23) | 2253.2078 | 1407.7079 | (39.9%-30%) | -37.52% | -37.52% | 1
-37.36% | Upgrade Power Transformers - Various Sites | 14559 | 9119.2081 | (39.9%-30%) | -37.36% | -37.36% | 1
-36.96% | Upgrade Equipment Foundations - Various Sites | 389.2 | 245.336 | (39.9%-30%) | -36.96% | -36.96% | 1
-36.7% | Upgrade Power Transformers - Various (2019-20) | 9102.7 | 5761.9806 | (39.9%-30%) | -36.7% | -36.7% | 1
-36.64% | Replace Surge Arrestors - Various Sites | 373.4 | 236.5843 | (39.9%-30%) | -36.64% | -36.64% | 1
-36.63% | Upgrade Fault Recorders - Various (2021) | 692.816 | 439.025 | (39.9%-30%) | -36.63% | -36.63% | 1
-36.5% | Unit 7 Condition Assessment (2023) - Bay d'Espoir | 597.5 | 379.4053 | (39.9%-30%) | -36.5% | -36.5% | 1
-36.23% | Replace Slip Rings Units 1-6 - Bay d'Espoir | 472.3 | 301.1664 | (39.9%-30%) | -36.23% | -36.23% | 1
-36.1% | Replace Transfer Switches and Associated Hardware - Hydro Place | 2324.6091 | 1485.3389 | (39.9%-30%) | -36.1% | -36.1% | 1
-35.89% | Overhaul Diesel Units - Various | 1232.9 | 790.3924 | (39.9%-30%) | -35.89% | -35.89% | 1
-35.87% | Upgrade Public Safety, Dams | 728.514 | 467.1982 | (39.9%-30%) | -35.87% | -35.87% | 1
-34.98% | Replace Network Communications Equipment (2022) | 312.5964 | 203.258 | (39.9%-30%) | -34.98% | -34.98% | 1
-34.97% | Install Diesel Fuel Metering Devices - BDE, PRV, VIC, GCL | 406.6 | 264.3975 | (39.9%-30%) | -34.97% | -34.97% | 1
-34.55% | Terminal Station In-Service Failures | 1800 | 1178.0273 | (39.9%-30%) | -34.55% | -34.55% | 1
-34.35% | Diesel Genset Replacements - Port Hope Simpson | 4374.3 | 2871.8409 | (39.9%-30%) | -34.35% | -34.35% | 1
-34.23% | Inspect Fuel Storage Tanks - Postville | 532.6 | 350.282 | (39.9%-30%) | -34.23% | -34.23% | 1
-33.96% | Replace Substation - Holyrood | 1198 | 791.1895 | (39.9%-30%) | -33.96% | -33.96% | 1
-33.84% | Install Breaker Failure - Various Sites | 855.5 | 566.0153 | (39.9%-30%) | -33.84% | -33.84% | 1
-33.53% | Water System Replacements - Bay d'Espoir and Cat Arm | 2553.8 | 1697.4616 | (39.9%-30%) | -33.53% | -33.53% | 1
-33.5% | Upgrade Fuel Storage Tanks - Charlottetown | 467.169 | 310.6504 | (39.9%-30%) | -33.5% | -33.5% | 1
-33.3% | Purchase Tools and Equipment less than $50,000 | 46 | 30.6813 | (39.9%-30%) | -33.3% | -33.3% | 1
-33.17% | Replace Fuel Storage Tanks - PR | 350.3 | 234.0964 | (39.9%-30%) | -33.17% | -33.17% | 1
-32.85% | Replace Surface Air Coolers for Both Units - CAT | 869.0732 | 583.5549 | (39.9%-30%) | -32.85% | -32.85% | 1
-32.84% | Upgrade Circuit Breakers (2022-2023) - Various | 8402.5238 | 5643.3502 | (39.9%-30%) | -32.84% | -32.84% | 1
-32.33% | Penstock 3 Laser Scanning - Bay d'Espoir | 46.3 | 31.3326 | (39.9%-30%) | -32.33% | -32.33% | 1
-32.26% | Inspect Fuel Storage Tanks - Various Sites | 1058.8 | 717.2581 | (39.9%-30%) | -32.26% | -32.26% | 1
-32% | Upgrade Circuit Breakers (2021-2022) - Various | 12048.6929 | 8193.3203 | (39.9%-30%) | -32% | -32% | 1
-31.9% | Purchase Mobile DC Power Systems | 966.5 | 658.2083 | (39.9%-30%) | -31.9% | -31.9% | 1
-31.85% | Refurbish Turbine Unit 2- BDE | 2520.7 | 1717.8404 | (39.9%-30%) | -31.85% | -31.85% | 1
-31.53% | Condition Monitoring Equipment - BDE | 340.4 | 233.0878 | (39.9%-30%) | -31.53% | -31.53% | 1
-31.4% | Turbine Valve Overhaul Unit 3 - Holyrood | 3623.5 | 2485.5916 | (39.9%-30%) | -31.4% | -31.4% | 1
-31.29% | Upgrade Ventilation in Powerhouse 1 and 2 - Bay d'Espoir | 997.9 | 685.6245 | (39.9%-30%) | -31.29% | -31.29% | 1
-31.21% | Transmission Line Upgrades - TL212 and TL218 | 2511.5 | 1727.6704 | (39.9%-30%) | -31.21% | -31.21% | 1
-30.94% | Overhaul Pumps - Holyrood | 438.3 | 302.6828 | (39.9%-30%) | -30.94% | -30.94% | 1
-30.91% | Refurbish Accommodation - USL | 74.5 | 51.4691 | (39.9%-30%) | -30.91% | -30.91% | 1
-30.89% | Implement Terminal Station Flood Mitigation - Springdale | 974 | 673.1173 | (39.9%-30%) | -30.89% | -30.89% | 1
-30.89% | Overhaul Unit 3 Boiler Feed Pump - Holyrood | 373 | 257.7866 | (39.9%-30%) | -30.89% | -30.89% | 1
-30.69% | Upgrade Terminal Station Equipment Foundations - Various (2020) | 349.9 | 242.5254 | (39.9%-30%) | -30.69% | -30.69% | 1
-30.66% | Replace Radomes (2022) - Various | 179.9 | 124.7468 | (39.9%-30%) | -30.66% | -30.66% | 1
-30.44% | Replace Fuel Tank 22E - St. Anthony | 199.8 | 138.973 | (39.9%-30%) | -30.44% | -30.44% | 1
-29.99% | Replace Exciter Controls Units 1 to 6 - Bay d'Espoir | 3347 | 2343.2927 | (29.9%-20%) | -29.99% | -29.99% | 1
-29.69% | Upgrade Power Transformers - Various (2022-23) | 3758.9072 | 2642.7505 | (29.9%-20%) | -29.69% | -29.69% | 1
-29.26% | Tanks 3 & 4 Life Expectancy Study - Holyrood | 48.3172 | 34.18 | (29.9%-20%) | -29.26% | -29.26% | 1
-28.98% | Upgrade Holyrood Access Road - Holyrood | 1162.6 | 825.6932 | (29.9%-20%) | -28.98% | -28.98% | 1
-28.87% | Overhaul Diesel Units - Various Sites | 2852.4 | 2028.9873 | (29.9%-20%) | -28.87% | -28.87% | 1
-28.76% | Upgrade Power Transformers - Various (2021-22) | 4312.318 | 3072.2791 | (29.9%-20%) | -28.76% | -28.76% | 1
-28.69% | Cable Upgrades - Various Sites | 932.1 | 664.7091 | (29.9%-20%) | -28.69% | -28.69% | 1
-28.18% | Replace Insulators - TL227 | 416.9 | 299.4214 | (29.9%-20%) | -28.18% | -28.18% | 1
-28% | Upgrade HMI and AVR - Hardwoods | 685.9 | 493.8231 | (29.9%-20%) | -28% | -28% | 1
-27.93% | Terminal Station In-Service Failures | 1500.046 | 1081.0307 | (29.9%-20%) | -27.93% | -27.93% | 1
-27.9% | Upgrade Circuit Breakers - Various Sites | 61460.4 | 44310.9252 | (29.9%-20%) | -27.9% | -27.9% | 1
-27.85% | Replace TS Battery Banks and Chargers - Various | 123.543 | 89.1301 | (29.9%-20%) | -27.85% | -27.85% | 1
-27.75% | Replace Disconnect Switches - Various Sites | 1967.8 | 1421.6373 | (29.9%-20%) | -27.75% | -27.75% | 1
-27.61% | Upgrade Station Lighting - Various (2021) | 278.9 | 201.905 | (29.9%-20%) | -27.61% | -27.61% | 1
-27.51% | Install Remote Operation of Salmon Spillway - Bay d'Espoir | 2508.4 | 1818.4012 | (29.9%-20%) | -27.51% | -27.51% | 1
-27.51% | Replace Main Fuel Valves - Hardwoods | 404.2 | 293.0207 | (29.9%-20%) | -27.51% | -27.51% | 1
-27.39% | Replace Circuit Breaker Reclosing Controllers (2024–2025) - TL247 | 328.2 | 238.2979 | (29.9%-20%) | -27.39% | -27.39% | 1
-27.3% | Upgrade Public Safety Around Dams and Waterways - Bay d'Espoir | 489 | 355.4848 | (29.9%-20%) | -27.3% | -27.3% | 1
-27.23% | Replace Fire Supression System - Happy Valley Gas Turbine | 2642.45 | 1923.0097 | (29.9%-20%) | -27.23% | -27.23% | 1
-27% | Replace Surge Arrestors - Various (2019) | 163.6 | 119.4258 | (29.9%-20%) | -27% | -27% | 1
-26.81% | Replace Battery Banks and Chargers - Various Sites | 881.6 | 645.2465 | (29.9%-20%) | -26.81% | -26.81% | 1
-26.65% | Control System Replacement - Holyrood Gas Turbine | 262.1713 | 192.3079 | (29.9%-20%) | -26.65% | -26.65% | 1
-26.33% | Purchase Office Equipment Less Than $50,000 (2023) | 75.6 | 55.6933 | (29.9%-20%) | -26.33% | -26.33% | 1
-26.22% | Replace Drainage Pumps - HLK, PRV | 774 | 571.0445 | (29.9%-20%) | -26.22% | -26.22% | 1
-26.05% | Purchase Meters and Metering Equipment - Various | 244.214 | 180.6076 | (29.9%-20%) | -26.05% | -26.05% | 1
-25.52% | Refurbish Control Building - WAV (2020) | 333.7298 | 248.5773 | (29.9%-20%) | -25.52% | -25.52% | 1
-25.25% | Install Level 2 Chargers for Electric Vehicles | 478.005 | 357.2934 | (29.9%-20%) | -25.25% | -25.25% | 1
-24.8% | Purchase SF6 Multi Analyzer - Various | 207.049 | 155.7007 | (29.9%-20%) | -24.8% | -24.8% | 1
-24.48% | Upgrade Hydro ECC Wall Infrastructure - Hydro Place | 188.476 | 142.3349 | (29.9%-20%) | -24.48% | -24.48% | 1
-24.46% | Perform Minor Enhancements - Hydro Place | 372.1 | 281.1013 | (29.9%-20%) | -24.46% | -24.46% | 1
-24.25% | Building Vestibule Powerhouse - Holyrood | 49.3 | 37.3438 | (29.9%-20%) | -24.25% | -24.25% | 1
-23.9% | Refurbish Sump Level System for Powerhouse 2 - Bay d'Espoir | 303.2 | 230.7473 | (29.9%-20%) | -23.9% | -23.9% | 1
-23.82% | Upgrade Station Lighting - HRD | 414.833 | 316.0256 | (29.9%-20%) | -23.82% | -23.82% | 1
-23.44% | Diesel Plant Ventilation Upgrade - Nain | 853.076 | 653.1224 | (29.9%-20%) | -23.44% | -23.44% | 1
-23.07% | Upgrade Distributed Control System Hardware - Holyrood | 1122.6141 | 863.5919 | (29.9%-20%) | -23.07% | -23.07% | 1
-22.91% | Upgrade Transformer Paralleling - WAV | 301.8 | 232.6507 | (29.9%-20%) | -22.91% | -22.91% | 1
-22.84% | Upgrade Diesel Plant Building - Ramea | 352.5 | 272.0043 | (29.9%-20%) | -22.84% | -22.84% | 1
-22.74% | Install Fire Protection in 230 kV Stations (2024–2025) - Voisey's Bay | 652.8 | 504.362 | (29.9%-20%) | -22.74% | -22.74% | 1
-22.74% | Replace Surge Arrestors - Various (2020) | 132.28 | 102.2014 | (29.9%-20%) | -22.74% | -22.74% | 1
-22.72% | Overhaul Diesel Engines - Various Sites | 2095.9 | 1619.7798 | (29.9%-20%) | -22.72% | -22.72% | 1
-22.6% | Install Fire Protection in 230 kV Stations - Bay d'Espoir | 766 | 592.8697 | (29.9%-20%) | -22.6% | -22.6% | 1
-22.43% | Refurbish Unit 6 Generator Stator - BDE | 9160.879 | 7106.4588 | (29.9%-20%) | -22.43% | -22.43% | 1
-21.84% | Upgrade Terminal Station Equipment Foundations - Various Sites | 367 | 286.8618 | (29.9%-20%) | -21.84% | -21.84% | 1
-21.42% | Install Fire Protection in Diesel Plants (2022-2023) - Ramea | 1928.8 | 1515.6301 | (29.9%-20%) | -21.42% | -21.42% | 1
-20.98% | Purchase Backup Diesel For Station Service - Grand Falls and Buchans | 188.9 | 149.274 | (29.9%-20%) | -20.98% | -20.98% | 1
-20.92% | Install Recloser Remote Control - English Harbour West and Barachoix | 338.7 | 267.8528 | (29.9%-20%) | -20.92% | -20.92% | 1
-20.84% | Upgrade Terminal Station Equipment Foundations - Various (2019) | 306.2 | 242.3876 | (29.9%-20%) | -20.84% | -20.84% | 1
-20.81% | Perform Software Upgrades and Minor Enhancements (2023) | 451.2 | 357.3164 | (29.9%-20%) | -20.81% | -20.81% | 1
-20.68% | Install Fire Protection in 230 kV Stations - BUC (2022-23) | 492.8023 | 390.8944 | (29.9%-20%) | -20.68% | -20.68% | 1
-20.59% | Perform Software Upgrades and Minor Enhancements - Hydro Place | 621.7 | 493.687 | (29.9%-20%) | -20.59% | -20.59% | 1
-20.23% | Diesel Genset Replacement Unit 2039 - St. Lewis | 1980.8 | 1580.0628 | (29.9%-20%) | -20.23% | -20.23% | 1
-20.23% | Replace Instrument Transformers - Various (2019-20) | 1100.1 | 877.5705 | (29.9%-20%) | -20.23% | -20.23% | 1
-20.15% | Install Fire Detection in Outbuildings - Holyrood | 198.6 | 158.5842 | (29.9%-20%) | -20.15% | -20.15% | 1
-20.09% | Upgrade Terminal Station for Mobile Substation - Cow Head | 484.7 | 387.3143 | (29.9%-20%) | -20.09% | -20.09% | 1
-20.03% | Refurbish Hydraulic Structures - Burnt Dam (2022-23) | 3756.277 | 3003.7782 | (29.9%-20%) | -20.03% | -20.03% | 1
-19.91% | Install Frequency Monitors - Various Sites | 157.8 | 126.3804 | (19.9%-10%) | -19.91% | -19.91% | 1
-19.76% | Purchase Capital Spares - Terminal Stations | 495.8 | 397.8449 | (19.9%-10%) | -19.76% | -19.76% | 1
-19.63% | Install CCTV Systems (2025) | 440.1 | 353.6907 | (19.9%-10%) | -19.63% | -19.63% | 1
-19.04% | Upgrade Office Facilities and Control Buildings - Various | 1180.6 | 955.8677 | (19.9%-10%) | -19.04% | -19.04% | 1
-18.9% | Purchase Tools and Equipment Less than $50,000 (2022) - Hydraulic Plants | 187.3 | 151.9023 | (19.9%-10%) | -18.9% | -18.9% | 1
-18.88% | Replace Disconnect Switches - Various (2022-23) | 1235.7013 | 1002.3861 | (19.9%-10%) | -18.88% | -18.88% | 1
-18.46% | Overhaul Unit 3 Turbine Valve - Holyrood | 3290.5 | 2682.9733 | (19.9%-10%) | -18.46% | -18.46% | 1
-18.44% | Line Depot Condition Assessment and Refurbishment - Various | 1233 | 1005.6007 | (19.9%-10%) | -18.44% | -18.44% | 1
-18.43% | Perform Level 2 Condition Assessment - Powerhouse Slope (2025) - Cat Arm | 169.4 | 138.1864 | (19.9%-10%) | -18.43% | -18.43% | 1
-18.27% | Replace Battery Banks and Chargers - Various Sites (2017-2018) | 945.5 | 772.7428 | (19.9%-10%) | -18.27% | -18.27% | 1
-18.17% | Install Demand Metering - Various Sites | 89.7 | 73.4013 | (19.9%-10%) | -18.17% | -18.17% | 1
-18.02% | Purchase Tools and Equipment Less than $ 50,000 - HRD GT | 45.6 | 37.3845 | (19.9%-10%) | -18.02% | -18.02% | 1
-17.88% | Replace Condition Monitoring Equipment - BDE (2019) | 382.7 | 314.2607 | (19.9%-10%) | -17.88% | -17.88% | 1
-17.8% | Perform Grounding Upgrades - Various Sites (2021-22) | 2107.3 | 1732.1113 | (19.9%-10%) | -17.8% | -17.8% | 1
-17.76% | Replace Control Cable PH1 - BDE | 515.1 | 423.6075 | (19.9%-10%) | -17.76% | -17.76% | 1
-17.69% | Makkovik Diesel Generating Station Roof Replacement - Supplemental | 891.6241 | 733.8948 | (19.9%-10%) | -17.69% | -17.69% | 1
-17.67% | Upgrade Telecontrol Facilities - Mary March Hill and Blue Grass Hill | 757.1 | 623.2868 | (19.9%-10%) | -17.67% | -17.67% | 1
-17.57% | Replace Powerhouse Lighting - Paradise River | 43.9 | 36.1856 | (19.9%-10%) | -17.57% | -17.57% | 1
-17.39% | Upgrade Office Facilities & Control Buildings - Various Sites | 2197.3 | 1815.2033 | (19.9%-10%) | -17.39% | -17.39% | 1
-17.27% | Replace Voltage Regulator - Happy Valley Gas Turbine | 342.3 | 283.1753 | (19.9%-10%) | -17.27% | -17.27% | 1
-17.17% | Install Fall Protection Equipment - Various Sites | 194.7 | 161.2649 | (19.9%-10%) | -17.17% | -17.17% | 1
-17.13% | Install Fire Protection Systems - Cartwright and Nain | 4407.1 | 3652.201 | (19.9%-10%) | -17.13% | -17.13% | 1
-16.97% | Upgrade Wastewater Treatment Plant 600 V Variable Frequency Drives - Holyrood | 70.1 | 58.2025 | (19.9%-10%) | -16.97% | -16.97% | 1
-16.83% | Distribution Upgrades - Various Sites | 1195.1 | 994.0176 | (19.9%-10%) | -16.83% | -16.83% | 1
-16.82% | Replace Coolers - Hinds Lake | 516.8 | 429.8845 | (19.9%-10%) | -16.82% | -16.82% | 1
-16.81% | Construct Storage Building - Makkovik and Charelottetown | 639.7 | 532.1648 | (19.9%-10%) | -16.81% | -16.81% | 1
-16.78% | Overhaul Diesel Units - Various | 2310.915 | 1923.2427 | (19.9%-10%) | -16.78% | -16.78% | 1
-16.58% | Remove Safety Hazards - Various | 199.4 | 166.3368 | (19.9%-10%) | -16.58% | -16.58% | 1
-16.43% | Upgrade Work Protection Code Application (2025-2026) | 708.64 | 592.214 | (19.9%-10%) | -16.43% | -16.43% | 1
-16.11% | Gas Turbine Equipment Replacement and Refurbishment - Hardwoods and Stephenville | 1427.2 | 1197.2788 | (19.9%-10%) | -16.11% | -16.11% | 1
-15.8% | TL 227 Distribution Line Sally's Cove L1 | 2250 | 1894.4776 | (19.9%-10%) | -15.8% | -15.8% | 1
-15% | Purchase Tools and Equipment less than $50,000 | 40 | 34.0015 | (19.9%-10%) | -15% | -15% | 1
-14.94% | Replace Battery Banks and Chargers (2022) - Various | 226.6 | 192.7347 | (19.9%-10%) | -14.94% | -14.94% | 1
-14.92% | Install Partial Discharge Monitoring - Holyrood Gas Turbine | 612.755 | 521.333 | (19.9%-10%) | -14.92% | -14.92% | 1
-14.71% | Purchase Capital Spares - Gas Turbines | 626.9 | 534.6717 | (19.9%-10%) | -14.71% | -14.71% | 1
-14.56% | Unit 3 Electrical Testing - Holyrood | 39.1131 | 33.4188 | (19.9%-10%) | -14.56% | -14.56% | 1
-14.54% | Remove Safety Hazards (2022) - Various | 199.6 | 170.5701 | (19.9%-10%) | -14.54% | -14.54% | 1
-14.23% | Install Fall Protection Equipment - Various | 46.7 | 40.0556 | (19.9%-10%) | -14.23% | -14.23% | 1
-14.21% | Install Fire Protection - Various Sites | 926.7 | 794.994 | (19.9%-10%) | -14.21% | -14.21% | 1
-14.21% | Overhaul Diesel Units - Various | 2511.3 | 2154.4067 | (19.9%-10%) | -14.21% | -14.21% | 1
-14.09% | Replace Fuel Piping - Hardwoods and Stephenville | 311.8 | 267.8725 | (19.9%-10%) | -14.09% | -14.09% | 1
-14.07% | Holyrood Tank Farm Underground Firewater System Replacment - Supplemental | 1469.6289 | 1262.9116 | (19.9%-10%) | -14.07% | -14.07% | 1
-13.63% | Replace Human Machine Interface - St. Lewis | 280.8 | 242.5202 | (19.9%-10%) | -13.63% | -13.63% | 1
-13.5% | Level II Condition Assessment - SRS | 556.808 | 481.6585 | (19.9%-10%) | -13.5% | -13.5% | 1
-13.12% | Purchase Tools and Equipment Less than $ 50,000 | 194.3 | 168.8137 | (19.9%-10%) | -13.12% | -13.12% | 1
-13.03% | Install Fire Protection in 230 kV Stations (2023-2024) - Deer Lake | 614.5 | 534.4027 | (19.9%-10%) | -13.03% | -13.03% | 1
-13.01% | Upgrade Exterior of Building - Hydro Place | 665.9 | 579.2426 | (19.9%-10%) | -13.01% | -13.01% | 1
-12.92% | Upgrade Powerhouse Building Envelope - Holyrood | 6477.8 | 5640.8877 | (19.9%-10%) | -12.92% | -12.92% | 1
-12.89% | Three Phase Construction - Bishop's Falls | 49.6 | 43.2043 | (19.9%-10%) | -12.89% | -12.89% | 1
-12.89% | Energy Efficiency Improvements - Various Sites | 445.1 | 387.7348 | (19.9%-10%) | -12.89% | -12.89% | 1
-12.86% | Purchase Capital Spares - Gas Turbines | 185 | 161.2058 | (19.9%-10%) | -12.86% | -12.86% | 1
-12.8% | Public Safety Dams/Waterways - Bay d'Espoir | 394.7 | 344.1715 | (19.9%-10%) | -12.8% | -12.8% | 1
-12.74% | Upgrade Public Safety Around Dams and Waterways - BDE | 436.28 | 380.6985 | (19.9%-10%) | -12.74% | -12.74% | 1
-12.58% | Diesel Genset Replacement Program (2023-2025) | 543 | 474.6987 | (19.9%-10%) | -12.58% | -12.58% | 1
-12.5% | Parking Lot Access Improvements - Hydro Place | 47.4 | 41.4768 | (19.9%-10%) | -12.5% | -12.5% | 1
-12.49% | Thermal In-Service Failures (2023) | 3300 | 2887.8278 | (19.9%-10%) | -12.49% | -12.49% | 1
-12.05% | Replace Protective Relays - Various Sites (2021-22) | 2007 | 1765.0953 | (19.9%-10%) | -12.05% | -12.05% | 1
-11.91% | Replace Surge Arresters - Various (2021) | 61.649 | 54.3044 | (19.9%-10%) | -11.91% | -11.91% | 1
-11.91% | Control Structure Refurbishments | 2188.2 | 1927.5433 | (19.9%-10%) | -11.91% | -11.91% | 1
-11.83% | Install L-1 Blades Unit 1 (2024) Holyrood | 581.263 | 512.496 | (19.9%-10%) | -11.83% | -11.83% | 1
-11.81% | Turbine Hot Gas Path Level 2 Inspection and Overhaul - Holyrood Gas Turbine | 11146.5 | 9829.5611 | (19.9%-10%) | -11.81% | -11.81% | 1
-11.75% | Replace TS Battery Banks and Chargers - Various | 354.8 | 313.0977 | (19.9%-10%) | -11.75% | -11.75% | 1
-11.48% | Install Breaker Failure Protection - Various Sites | 622.9 | 551.4077 | (19.9%-10%) | -11.48% | -11.48% | 1
-11.31% | Replace Surge Arrestors - Various Sites | 197.4 | 175.0706 | (19.9%-10%) | -11.31% | -11.31% | 1
-11.24% | Purchase 85' Material Handler Aerial Device on Track Unit | 1353.9 | 1201.724 | (19.9%-10%) | -11.24% | -11.24% | 1
-11.13% | Additions for Load Growth - L'anse au Loup | 4175.6 | 3710.7617 | (19.9%-10%) | -11.13% | -11.13% | 1
-10.55% | Overhaul Diesel Units (2022) - Various | 1360.5 | 1216.9338 | (19.9%-10%) | -10.55% | -10.55% | 1
-10.48% | Upgrade Remote Terminal Units (2022) - Various | 171.1 | 153.1715 | (19.9%-10%) | -10.48% | -10.48% | 1
-10.43% | Purchase Meters and Metering Equipment (2023) | 226.6 | 202.9578 | (19.9%-10%) | -10.43% | -10.43% | 1
-10.42% | Overhaul Turbine/Generator Unit - GCL | 562.2 | 503.6457 | (19.9%-10%) | -10.42% | -10.42% | 1
-10.3% | Overhaul Diesel Units (2023) | 1502 | 1347.2625 | (19.9%-10%) | -10.3% | -10.3% | 1
-10.17% | Upgrade Sump Level System Powerhouse 1 - BDE | 131.6 | 118.2189 | (19.9%-10%) | -10.17% | -10.17% | 1
-10.09% | Upgrade Terminal Station Foundations - BCX/LLK | 614.5 | 552.4733 | (19.9%-10%) | -10.09% | -10.09% | 1
-9.83% | Wood Pole Line Management Program - Various Sites | 3532.9 | 3185.6229 | (9.9%-0.01%) | -9.83% | -9.83% | 1
-9.603% | Refurbish Main Generator Breaker - Upper Salmon | 271.1 | 245.0667 | (9.9%-0.01%) | -9.603% | -9.603% | 1
-9.573% | Overhaul Unit 1 Turbine Valves - Holyrood | 2485.7 | 2247.747 | (9.9%-0.01%) | -9.573% | -9.573% | 1
-9.555% | Diesel Genset Replacements - Mary's Harbour | 3900.714 | 3527.9937 | (9.9%-0.01%) | -9.555% | -9.555% | 1
-9.398% | Purchase Surveying Software and Equipment (2025) | 316.4 | 286.6651 | (9.9%-0.01%) | -9.398% | -9.398% | 1
-9.321% | Upgrade Cranes and Hoists - Holyrood | 380.6 | 345.1238 | (9.9%-0.01%) | -9.321% | -9.321% | 1
-9.276% | Purchase Meters and Metering Equipment - Various | 196.4 | 178.181 | (9.9%-0.01%) | -9.276% | -9.276% | 1
-9.121% | Install Automated Meter Reading - Happy Valley | 1970.2 | 1790.4916 | (9.9%-0.01%) | -9.121% | -9.121% | 1
-9.102% | Refurbish Powerhouse Station Services - Bay d'Espoir | 4347.1 | 3951.4134 | (9.9%-0.01%) | -9.102% | -9.102% | 1
-9.056% | Upgrade Line Depots - Roddickton | 344.7 | 313.4826 | (9.9%-0.01%) | -9.056% | -9.056% | 1
-9.013% | Replace Light-Duty Mobile Equipment (2022) - Various | 775.2853 | 705.4096 | (9.9%-0.01%) | -9.013% | -9.013% | 1
-8.974% | Purchase Tools and Equipment Less than $50,000 (2023) - Gas Turbine | 18.3 | 16.6577 | (9.9%-0.01%) | -8.974% | -8.974% | 1
-8.926% | Replace Powerline Carrier - Various Sites | 836.8 | 762.11 | (9.9%-0.01%) | -8.926% | -8.926% | 1
-8.439% | Upgrade HVAC Supervisory Controllers (2024) - Hydro Place | 149.6 | 136.9756 | (9.9%-0.01%) | -8.439% | -8.439% | 1
-8.356% | Overhaul Marine Terminal Loading Arms (2024) - Holyrood | 511 | 468.3003 | (9.9%-0.01%) | -8.356% | -8.356% | 1
-8.271% | Replace RTUs - Various | 118.3 | 108.5157 | (9.9%-0.01%) | -8.271% | -8.271% | 1
-8.248% | Replace Automation Equipment - Mary's Harbour | 1142 | 1047.8081 | (9.9%-0.01%) | -8.248% | -8.248% | 1
-8.204% | BDE-Replace Annunciators | 384.9684 | 353.3838 | (9.9%-0.01%) | -8.204% | -8.204% | 1
-8.173% | Replace Power Line Carrier (2023–2024) - TL223 and TL224 | 957.7 | 879.4252 | (9.9%-0.01%) | -8.173% | -8.173% | 1
-8.168% | Thermal In-Service Failures | 2000.042 | 1836.6861 | (9.9%-0.01%) | -8.168% | -8.168% | 1
-8.166% | Diesel Genset Replacements - Charlottetown | 1432.5 | 1315.5202 | (9.9%-0.01%) | -8.166% | -8.166% | 1
-8.101% | Replace Radomes - Various | 360.3 | 331.1138 | (9.9%-0.01%) | -8.101% | -8.101% | 1
-7.642% | Purchase Tools and Equipment less than $50,000 | 45.6 | 42.1151 | (9.9%-0.01%) | -7.642% | -7.642% | 1
-7.522% | Generator Overhaul - PRV | 341.906 | 316.1892 | (9.9%-0.01%) | -7.522% | -7.522% | 1
-7.366% | Replace SONET Multiplexors (2024) | 430.4 | 398.6951 | (9.9%-0.01%) | -7.366% | -7.366% | 1
-7.003% | HRD - Major Overhaul: Unit 3 Cooling Water Pump West | 210.8 | 196.0386 | (9.9%-0.01%) | -7.003% | -7.003% | 1
-6.913% | Replacement of Short-Term Load Forecasting Software | 439.5 | 409.1187 | (9.9%-0.01%) | -6.913% | -6.913% | 1
-6.802% | Purchase Tools and Equipment Less than $ 50,000 | 133.5 | 124.42 | (9.9%-0.01%) | -6.802% | -6.802% | 1
-6.783% | Replace Insulators - Various (2020-21) | 243.106 | 226.6151 | (9.9%-0.01%) | -6.783% | -6.783% | 1
-6.748% | Upgrade Terminal Station Equipment Foundations - Various (2021) | 175.4 | 163.5641 | (9.9%-0.01%) | -6.748% | -6.748% | 1
-6.682% | Widen Rights-of-Way of Transmission Lines TL239 & TL259 (2024) | 668.914 | 624.2195 | (9.9%-0.01%) | -6.682% | -6.682% | 1
-6.649% | Diesel Plant Engine Auxiliary Upgrades - Various Sites | 1206.9 | 1126.6529 | (9.9%-0.01%) | -6.649% | -6.649% | 1
-6.441% | Perform Combustor Inspection - Holyrood Gas Turbine | 5473.5432 | 5120.9907 | (9.9%-0.01%) | -6.441% | -6.441% | 1
-6.419% | Hampden New Line from TS | 443.8 | 415.3142 | (9.9%-0.01%) | -6.419% | -6.419% | 1
-6.389% | Remove Safety Hazards - Various Sites | 198.6 | 185.9109 | (9.9%-0.01%) | -6.389% | -6.389% | 1
-6.327% | Upgrade Data Alarm Management - Sunnyside | 611.4 | 572.7145 | (9.9%-0.01%) | -6.327% | -6.327% | 1
-6.084% | Purchase Capital Spares - Holyrood Gas Turbine | 213.8 | 200.7921 | (9.9%-0.01%) | -6.084% | -6.084% | 1
-5.344% | Inspect Fuel Tanks (2025) - Holyrood | 608 | 575.507 | (9.9%-0.01%) | -5.344% | -5.344% | 1
-5.204% | Refurbish Control Building - HRD, CBC | 650.3 | 616.4578 | (9.9%-0.01%) | -5.204% | -5.204% | 1
-5.196% | Replace Aircraft Markers at Grand Lake Crossing - TL228 | 1567.9 | 1486.4391 | (9.9%-0.01%) | -5.196% | -5.196% | 1
-4.937% | Refurbish Station Water System - Upper Salmon | 294.2 | 279.6762 | (9.9%-0.01%) | -4.937% | -4.937% | 1
-4.891% | Main Breaker Replacement-HYP | 18.4 | 17.5 | (9.9%-0.01%) | -4.891% | -4.891% | 1
-4.797% | Replace Network Communications Equipment - Various | 189.5 | 180.4093 | (9.9%-0.01%) | -4.797% | -4.797% | 1
-4.718% | Replace Teleprotection - TL261 | 517.4 | 492.987 | (9.9%-0.01%) | -4.718% | -4.718% | 1
-4.716% | Replace 48 V Battery Banks and Chargers (2023) | 439.7 | 418.9626 | (9.9%-0.01%) | -4.716% | -4.716% | 1
-4.434% | Upgrade Site Facilities - Various | 49 | 46.8273 | (9.9%-0.01%) | -4.434% | -4.434% | 1
-4.028% | Major Condition Assessment and Miscellaneous Refurbishments Synchronous Condenser 1 and 2 (2023-2024) - Wabush Terminal Station | 1093.3 | 1049.263 | (9.9%-0.01%) | -4.028% | -4.028% | 1
-3.929% | Replace Radomes - Various | 263.5 | 253.1481 | (9.9%-0.01%) | -3.929% | -3.929% | 1
-3.878% | Replace Powerhouse #2 Lighting - Bay d'Espoir | 48 | 46.1384 | (9.9%-0.01%) | -3.878% | -3.878% | 1
-3.757% | Replace Instrument Transformers - Various Sites | 3668 | 3530.2062 | (9.9%-0.01%) | -3.757% | -3.757% | 1
-3.703% | Replace Battery Banks and Chargers - Various | 937.9 | 903.1731 | (9.9%-0.01%) | -3.703% | -3.703% | 1
-3.689% | Overhaul Olympus Gas Generator - Stephenville | 1666.8 | 1605.3137 | (9.9%-0.01%) | -3.689% | -3.689% | 1
-3.533% | Replace Radomes - Various | 240.4 | 231.9067 | (9.9%-0.01%) | -3.533% | -3.533% | 1
-3.463% | Reburbish Hydraulic Structures VAR | 5368.415 | 5182.5133 | (9.9%-0.01%) | -3.463% | -3.463% | 1
-3.432% | Upgrade Distribution Systems - Various Sites | 6635.9 | 6408.156 | (9.9%-0.01%) | -3.432% | -3.432% | 1
-3.326% | Replace Transformer T1 - Buchans | 2335.1 | 2257.4354 | (9.9%-0.01%) | -3.326% | -3.326% | 1
-3.144% | Install Line Monitoring System (2024) - TL201 | 469.902 | 455.1293 | (9.9%-0.01%) | -3.144% | -3.144% | 1
-2.886% | Refresh Cyber Security Infrastructure - Hydro Place | 217.494 | 211.2176 | (9.9%-0.01%) | -2.886% | -2.886% | 1
-2.792% | Replace Floor Annunciator Panels - Bay d'Espoir | 46.8 | 45.4934 | (9.9%-0.01%) | -2.792% | -2.792% | 1
-2.683% | Install Energy Efficiency Lighting in Diesel Plants - Various | 345.2 | 335.9397 | (9.9%-0.01%) | -2.683% | -2.683% | 1
-2.682% | Rplc Sump Pump-Upper Salmon | 407.153 | 396.2344 | (9.9%-0.01%) | -2.682% | -2.682% | 1
-2.607% | Additions for Load - Distribution System - Makkovik and Hopedale | 846.113 | 824.0509 | (9.9%-0.01%) | -2.607% | -2.607% | 1
-2.587% | Refurbish Gas Generator Engines - Hardwoods and Stephenville | 3047.1 | 2968.2856 | (9.9%-0.01%) | -2.587% | -2.587% | 1
-2.513% | Penstock Level 2 Condition Assessment - CAT | 261.216 | 254.6524 | (9.9%-0.01%) | -2.513% | -2.513% | 1
-2.44% | Refurbish Workshop Roof (2023) - Holyrood | 243.7 | 237.7527 | (9.9%-0.01%) | -2.44% | -2.44% | 1
-2.254% | Purchase 46' Material Handler Aerial Device on Track Unit | 758 | 740.9146 | (9.9%-0.01%) | -2.254% | -2.254% | 1
-2.189% | Hydro - Mobile Devices | 48.2 | 47.1449 | (9.9%-0.01%) | -2.189% | -2.189% | 1
-2.091% | Purchase Meters and Metering Equipment - Various | 233.4 | 228.5207 | (9.9%-0.01%) | -2.091% | -2.091% | 1
-2.077% | Purchase Tools and Equipment Less than $50,000 (2022) - Thermal Plants | 18.9 | 18.5074 | (9.9%-0.01%) | -2.077% | -2.077% | 1
-2.038% | Replace MDR8000 Microwave Radios (2024-2025) | 1453.8 | 1424.1702 | (9.9%-0.01%) | -2.038% | -2.038% | 1
-1.99% | Upgrade Core IT Infrastructure - Hydro Place | 262.776 | 257.5458 | (9.9%-0.01%) | -1.99% | -1.99% | 1
-1.933% | HRD - Major Overhaul Unit 2 Boiler Feed Pump West | 279.3 | 273.901 | (9.9%-0.01%) | -1.933% | -1.933% | 1
-1.744% | Supply & Install Replacement Waterline - St. Anthony | 47.4 | 46.5735 | (9.9%-0.01%) | -1.744% | -1.744% | 1
-1.66% | 230 kV Transmission Line - Bay d'Espoir to Western Avalon | 291658 | 286817.7549 | (9.9%-0.01%) | -1.66% | -1.66% | 1
-1.625% | Replace Mobile Devices | 49.7 | 48.8921 | (9.9%-0.01%) | -1.625% | -1.625% | 1
-1.599% | Upgrade Remote Terminal Units - Various | 167.7 | 165.0186 | (9.9%-0.01%) | -1.599% | -1.599% | 1
-1.389% | Upgrade Power Transformers - Various (2020-21) | 1245.723 | 1228.4232 | (9.9%-0.01%) | -1.389% | -1.389% | 1
-1.372% | Replace MDR 4000 Microwave Radio East - Various Sites | 1170.5 | 1154.4371 | (9.9%-0.01%) | -1.372% | -1.372% | 1
-1.215% | Valentine Gold Interconnection - Supplemental | 16347.4 | 16148.7257 | (9.9%-0.01%) | -1.215% | -1.215% | 1
-1.191% | Purchase Tools and Equipment Less than $ 50,000 | 113.4 | 112.0489 | (9.9%-0.01%) | -1.191% | -1.191% | 1
-1.161% | Upgrade Site Facilities - Various | 48.943 | 48.375 | (9.9%-0.01%) | -1.161% | -1.161% | 1
-0.7011% | Addition for Load Growth - Happy Valley L7 | 617.6 | 613.2703 | (9.9%-0.01%) | -0.7011% | -0.7011% | 1
-0.6751% | Update Cyber Security Infrastructure (2023) | 232.1 | 230.5331 | (9.9%-0.01%) | -0.6751% | -0.6751% | 1
-0.6699% | Upgrade Remote Terminal Units - Various | 157.054 | 156.0019 | (9.9%-0.01%) | -0.6699% | -0.6699% | 1
-0.6237% | Replace Rotary Strainer - USL | 239.9966 | 238.4998 | (9.9%-0.01%) | -0.6237% | -0.6237% | 1
-0.3376% | Purchase SF6 Reclaim Units - Various | 142.722 | 142.2401 | (9.9%-0.01%) | -0.3376% | -0.3376% | 1
-0.1333% | Replace Human Machine Interface - Cartwright | 306.9 | 306.491 | (9.9%-0.01%) | -0.1333% | -0.1333% | 1
-0.03447% | Replace Fuel Oil, Lube Oil, and Glycol Pumps - Happy Valley Gas Turbine | 405.2 | 405.0603 | (9.9%-0.01%) | -0.03447% | -0.03447% | 1
-0.00239% | Upgrade Transformer Systems - Postville and Cartwright | 465.2 | 465.1889 | (9.9%-0.01%) | -0.00239% | -0.00239% | 1
0.02493% | Upgrade Core IT/OT Infrastructure (2022) - Hydro Place | 308.2 | 308.2768 | 0%-9.9% | 0.02493% | 0.02493% | 1
0.1458% | Refurbish Access Road to Ebbegunbaeg | 803.142 | 804.3129 | 0%-9.9% | 0.1458% | 0.1458% | 1
0.2933% | Replace Control Cables BDE | 311.291 | 312.2041 | 0%-9.9% | 0.2933% | 0.2933% | 1
0.5506% | Construct 230 kV Transmission Line - Soldiers Pond to Hardwoods | 26560.9 | 26707.1371 | 0%-9.9% | 0.5506% | 0.5506% | 1
0.5778% | Replace Roof on Service Building - Bishop's Falls | 612.8 | 616.3406 | 0%-9.9% | 0.5778% | 0.5778% | 1
0.6975% | Replace Powerhouse 1 Air Conditioning Unit (2024-2025) - Bay d'Espoir | 289 | 291.0157 | 0%-9.9% | 0.6975% | 0.6975% | 1
1.096% | Install Wind Monitoring Station North Salmon Dam SD-2 - Bay d'Espoir | 165.5 | 167.3131 | 0%-9.9% | 1.096% | 1.096% | 1
1.246% | Replace Protective Relays - Various Sites | 1816.7 | 1839.3336 | 0%-9.9% | 1.246% | 1.246% | 1
1.424% | Upgrade Site Facilities (2022) - Various | 49.6 | 50.3063 | 0%-9.9% | 1.424% | 1.424% | 1
1.437% | Replace Air Conditioners - Various | 74.4 | 75.4694 | 0%-9.9% | 1.437% | 1.437% | 1
1.538% | Replace Washroom Fixtures - Hydro Place | 49.5 | 50.2615 | 0%-9.9% | 1.538% | 1.538% | 1
1.732% | Upgrade Site Facilities - Various | 49.4 | 50.2554 | 0%-9.9% | 1.732% | 1.732% | 1
1.865% | Upgrade Site Facilities | 49 | 49.9137 | 0%-9.9% | 1.865% | 1.865% | 1
1.884% | Upgrade Site Facilities - Various | 45.522 | 46.3798 | 0%-9.9% | 1.884% | 1.884% | 1
2.005% | Purchase Tools and Equipment less than $50,000 | 26 | 26.5213 | 0%-9.9% | 2.005% | 2.005% | 1
2.048% | Distribution System Upgrades - Various Sites | 3155 | 3219.6105 | 0%-9.9% | 2.048% | 2.048% | 1
2.195% | Purchase Tools and Equipment Less than $50,000 (2022) - Gas Turbine | 19.6 | 20.0301 | 0%-9.9% | 2.195% | 2.195% | 1
2.233% | Refurbish Intake 1 (2024-2025) - Bay d'Espoir | 3344 | 3418.668 | 0%-9.9% | 2.233% | 2.233% | 1
2.245% | Replace Control Room/Communications Room Air Conditioning - Hinds Lake | 94.3 | 96.4168 | 0%-9.9% | 2.245% | 2.245% | 1
2.272% | Replace Air Conditioners - Various Sites | 191.9 | 196.2608 | 0%-9.9% | 2.272% | 2.272% | 1
2.31% | Upgrade Access Roads to Microwave Sites - Various Sites | 118.4 | 121.1352 | 0%-9.9% | 2.31% | 2.31% | 1
2.345% | IOC SCADA Data Link | 28.218 | 28.8798 | 0%-9.9% | 2.345% | 2.345% | 1
2.349% | Wood Pole Line Management Program - Various Sites | 2896.9 | 2964.946 | 0%-9.9% | 2.349% | 2.349% | 1
2.481% | Refurbish Turbine Unit 7 - BDE | 4179 | 4282.6782 | 0%-9.9% | 2.481% | 2.481% | 1
2.57% | Purchase Office Equipment Less Than $50,000 (2022) | 67.1 | 68.8243 | 0%-9.9% | 2.57% | 2.57% | 1
2.671% | Replace MDR 6000 Microwave Radio - Various | 1201 | 1233.0772 | 0%-9.9% | 2.671% | 2.671% | 1
2.827% | Replace Station Service Breakers - Cat Arm | 1008.3 | 1036.8004 | 0%-9.9% | 2.827% | 2.827% | 1
2.847% | Upgrade Diesel Plant Production Data Collection Equipment-Various | 819.4 | 842.7319 | 0%-9.9% | 2.847% | 2.847% | 1
2.979% | Hydraulic In-Service Failures | 1250 | 1287.2367 | 0%-9.9% | 2.979% | 2.979% | 1
3.219% | Wood Pole Line Management Program - Various Sites | 2792.724 | 2882.6142 | 0%-9.9% | 3.219% | 3.219% | 1
3.505% | Replace Network Communications Equipment - Various | 186.797 | 193.3442 | 0%-9.9% | 3.505% | 3.505% | 1
3.505% | Purchase Tools and Equipment Less than $50,000 (2023) - Hydraulic Plants | 144.9 | 149.9791 | 0%-9.9% | 3.505% | 3.505% | 1
3.572% | Diesel Plant Fire Protection - Postville | 842 | 872.0761 | 0%-9.9% | 3.572% | 3.572% | 1
3.603% | Holyrood Upgrade Turbine Control System Unit 2 - Supplemental | 726 | 752.1551 | 0%-9.9% | 3.603% | 3.603% | 1
3.951% | Stage 1 Pumphouse Siding Replacement - Holyrood | 49.9 | 51.8717 | 0%-9.9% | 3.951% | 3.951% | 1
3.962% | Upgrade Ventilation - Cartwright | 465.7 | 484.1515 | 0%-9.9% | 3.962% | 3.962% | 1
4.125% | Holyrood Thermal Generating Station Unit 1 and Unit 2 Turbine Last Stage Blades - Supplemental | 6408.7 | 6673.0654 | 0%-9.9% | 4.125% | 4.125% | 1
4.232% | Upgrade Site Facilities (2023) | 45.2 | 47.1129 | 0%-9.9% | 4.232% | 4.232% | 1
4.331% | Replace Grader Unit V9829 (2024) - Bay d'Espoir | 836.7 | 872.9393 | 0%-9.9% | 4.331% | 4.331% | 1
4.457% | Remove Safety Hazards (2023) | 198.2 | 207.0342 | 0%-9.9% | 4.457% | 4.457% | 1
4.53% | Upgrades XFMR Parallel | 176.2 | 184.1815 | 0%-9.9% | 4.53% | 4.53% | 1
4.666% | Replace Air Conditioning Units 8 and 14 - Hydro Place | 264.1 | 276.4231 | 0%-9.9% | 4.666% | 4.666% | 1
4.896% | Rewind Unit 3 Stator - Holyrood | 6945.6 | 7285.6551 | 0%-9.9% | 4.896% | 4.896% | 1
5.04% | Install Recloser Remote Control - Bottom Waters | 465.7 | 489.1726 | 0%-9.9% | 5.04% | 5.04% | 1
5.232% | Purchase Capital Spares Holyrood | 321.5 | 338.322 | 0%-9.9% | 5.232% | 5.232% | 1
5.239% | Perform Level 2 Condition Assessment - Stage I & II Cooling Water Sump Structures (2025) - Holyrood | 1747.033 | 1838.5639 | 0%-9.9% | 5.239% | 5.239% | 1
5.485% | Diesel Genset Replacements (2019-2020) | 3947.4 | 4163.9017 | 0%-9.9% | 5.485% | 5.485% | 1
5.53% | Overhaul Unit 1 Generator - Holyrood | 1005 | 1060.5755 | 0%-9.9% | 5.53% | 5.53% | 1
5.532% | Upgrade Human Machine Interface - Various Sites | 434 | 458.0087 | 0%-9.9% | 5.532% | 5.532% | 1
6.207% | Distribution System Upgrades - Various Sites | 5880.9 | 6245.9032 | 0%-9.9% | 6.207% | 6.207% | 1
6.264% | Replace 258VDC Battery Banks - Holyrood | 330 | 350.6723 | 0%-9.9% | 6.264% | 6.264% | 1
6.335% | Purchase New Meter Calibration Test Console - Hydro Place | 196.9 | 209.3736 | 0%-9.9% | 6.335% | 6.335% | 1
6.451% | Install Breaker Failure Protection (2021-22) | 451.472 | 480.5956 | 0%-9.9% | 6.451% | 6.451% | 1
6.684% | Overhaul Unit 3 Generator - Holyrood | 572.7 | 610.9818 | 0%-9.9% | 6.684% | 6.684% | 1
6.741% | Remove Safety Hazards - Various | 197.5 | 210.8144 | 0%-9.9% | 6.741% | 6.741% | 1
7.013% | Distribution System Upgrades (2020-2021) - Various | 3257.1 | 3485.513 | 0%-9.9% | 7.013% | 7.013% | 1
7.094% | Replace Battery Banks and Chargers - Various | 327.2 | 350.4117 | 0%-9.9% | 7.094% | 7.094% | 1
7.199% | Refurbish Meteorological Stations (2025) | 167.8 | 179.8792 | 0%-9.9% | 7.199% | 7.199% | 1
7.664% | Purchase Tools and Equipment less than $50,000 | 45.2 | 48.664 | 0%-9.9% | 7.664% | 7.664% | 1
8.14% | Refurbish Outbuilding and Powerhouse Building Envelopes (2024-2025) - Holyrood | 1195.6 | 1292.9245 | 0%-9.9% | 8.14% | 8.14% | 1
8.449% | Overhaul Turbine Valves Unit 2 - Holyrood | 2302.1 | 2496.5952 | 0%-9.9% | 8.449% | 8.449% | 1
8.609% | Upgrade Remote Terminal Units - Various | 183.4 | 199.1898 | 0%-9.9% | 8.609% | 8.609% | 1
8.673% | Hydro Generation Tools & Equip | 235.2 | 255.5992 | 0%-9.9% | 8.673% | 8.673% | 1
8.689% | Upgrade Public Safety Around Dams and Waterways - BDE | 678.5 | 737.4564 | 0%-9.9% | 8.689% | 8.689% | 1
8.81% | BDE Unit 6 Replace Control Cables | 304.8 | 331.6525 | 0%-9.9% | 8.81% | 8.81% | 1
9.087% | Upgrade Telecontrol Facilities - Sandy Brook Hill | 564 | 615.2495 | 0%-9.9% | 9.087% | 9.087% | 1
9.158% | Replace Air Conditioning - BDE | 162.9 | 177.8179 | 0%-9.9% | 9.158% | 9.158% | 1
9.266% | Replace Elevator Motors and Controls Equipment - HYP | 882.8477 | 964.652 | 0%-9.9% | 9.266% | 9.266% | 1
9.367% | Replace Light Duty Mobile Equipment - Various Sites | 549.6 | 601.0809 | 0%-9.9% | 9.367% | 9.367% | 1
9.401% | Overhaul Turbine/Generators - Cat Arm | 305.4 | 334.111 | 0%-9.9% | 9.401% | 9.401% | 1
9.46% | Upgrade Digital Fault Recorders - Various Sites | 502.5 | 550.0368 | 0%-9.9% | 9.46% | 9.46% | 1
9.52% | Replace Site Facilities - Bay d'Espoir | 11981.3 | 13121.8682 | 0%-9.9% | 9.52% | 9.52% | 1
9.735% | Diesel Plant Engine Cooling System Upgrades - Various Sites | 1310 | 1437.5344 | 0%-9.9% | 9.735% | 9.735% | 1
9.809% | Install Partial Discharge Monitoring System - HLK,CAT,GCL | 451.417 | 495.6979 | 0%-9.9% | 9.809% | 9.809% | 1
9.821% | Replace T/G Cooling Water Pump and Strainer - HLK | 408.5 | 448.6202 | 0%-9.9% | 9.821% | 9.821% | 1
9.882% | Upgrade Reclosing Circuit Breakers - SSD B1L03 & HRD B1L65 (2022-23) | 210.9698 | 231.818 | 0%-9.9% | 9.882% | 9.882% | 1
9.951% | Hydraulic In-Service Failures | 1250 | 1374.3921 | 0%-9.9% | 9.951% | 9.951% | 1
9.972% | Replace UPS Systems - Hydro Place | 889.8 | 978.5309 | 0%-9.9% | 9.972% | 9.972% | 1
10% | Remove Safety Hazards - Various | 198.552 | 218.4151 | 10%-19.9% | 10% | 10% | 1
10.16% | Replace Diesel Genset 1 (2023-2024) - Ebbegunbaeg | 1026.3 | 1130.5443 | 10%-19.9% | 10.16% | 10.16% | 1
10.55% | Upgrade of Worst-Performing Distribution Feeders (2022-2023) | 2761.098 | 3052.5192 | 10%-19.9% | 10.55% | 10.55% | 1
11.05% | Install Recloser Remote Control (2020-2021) - Hampden and Upper Salmon | 256.647 | 285.012 | 10%-19.9% | 11.05% | 11.05% | 1
11.05% | Replace PBX Phone Systems - Various | 1242.3 | 1379.6253 | 10%-19.9% | 11.05% | 11.05% | 1
11.19% | Upgrade Telecontrol Facilities - Gull Pond Hill and Bay d’Espoir Hill | 673.9 | 749.3001 | 10%-19.9% | 11.19% | 11.19% | 1
11.26% | Holyrood Inspect and Refurbish Day Tank - Supplemental | 846.7719 | 942.1432 | 10%-19.9% | 11.26% | 11.26% | 1
11.33% | Generator Assessment - Happy Valley Gas Turbine | 1097.604 | 1221.9491 | 10%-19.9% | 11.33% | 11.33% | 1
11.37% | Purchase Turbine Last Stage Blades - Holyrood - Supplemental | 1432.6215 | 1595.5372 | 10%-19.9% | 11.37% | 11.37% | 1
11.62% | Overhaul Unit 4 - BDE | 225 | 251.1359 | 10%-19.9% | 11.62% | 11.62% | 1
11.7% | Upgrade Line Depots - Various | 648.3 | 724.178 | 10%-19.9% | 11.7% | 11.7% | 1
12.02% | Refurbish Fuel Oil Storage Tank 4 (2024) - Holyrood | 1920 | 2150.8605 | 10%-19.9% | 12.02% | 12.02% | 1
12.25% | Upgrade Unit 1 Control System (2024-2025) - Holyrood | 652.6 | 732.5407 | 10%-19.9% | 12.25% | 12.25% | 1
12.71% | Replace Diesel Genset-VCS | 944.028 | 1064.0392 | 10%-19.9% | 12.71% | 12.71% | 1
12.75% | Construct Maintenance Platform (2024-2025) - Holyrood Gas Turbine | 359.2 | 404.9963 | 10%-19.9% | 12.75% | 12.75% | 1
12.88% | Remove Safety Hazards - Various | 199.1 | 224.7445 | 10%-19.9% | 12.88% | 12.88% | 1
13.04% | Upgrade Waste Water Equalization System - Holyrood | 2361.1 | 2668.957 | 10%-19.9% | 13.04% | 13.04% | 1
13.4% | Replace Spherical By-Pass Valves Units 1 and 2 - Bay d'Espoir | 351.5 | 398.6093 | 10%-19.9% | 13.4% | 13.4% | 1
14.16% | Upgrade UPS 1 & 2 (2024-2025) - Holyrood | 370.6 | 423.0747 | 10%-19.9% | 14.16% | 14.16% | 1
14.38% | Replace Disconnects - Various (2020-21) | 1069.847 | 1223.7236 | 10%-19.9% | 14.38% | 14.38% | 1
14.72% | Replace Teleprotection - TL202 & TL206 | 196.8 | 225.7597 | 10%-19.9% | 14.72% | 14.72% | 1
14.73% | Replace Network Communications Equipment - Various Sites | 199.3 | 228.6491 | 10%-19.9% | 14.73% | 14.73% | 1
15.26% | Refurbish Generator Rotor - HLK | 1340.299 | 1544.8498 | 10%-19.9% | 15.26% | 15.26% | 1
16.16% | Replace Turbine and Generator Control & Vibration Monitoring System - PRV | 238.571 | 277.1194 | 10%-19.9% | 16.16% | 16.16% | 1
16.37% | Overhaul Hydraulic Units (2024) | 323.8 | 376.8143 | 10%-19.9% | 16.37% | 16.37% | 1
16.41% | Replace CCTV Cameras (2024) | 317.6 | 369.7161 | 10%-19.9% | 16.41% | 16.41% | 1
16.47% | Wood Pole Line Management Program - Various Sites | 2467 | 2873.4173 | 10%-19.9% | 16.47% | 16.47% | 1
16.51% | Upgrade Data Alarm Systems - MDR (2020-21) | 326.499 | 380.4052 | 10%-19.9% | 16.51% | 16.51% | 1
16.6% | Phase 2 - EV charging Network | 1581.501 | 1844.0956 | 10%-19.9% | 16.6% | 16.6% | 1
17.08% | Replace TS Battery Banks and Chargers - EHW, HWD, SDP, SHE, SOK | 315.2393 | 369.0905 | 10%-19.9% | 17.08% | 17.08% | 1
17.15% | Upgrade Data Alarm Systems - Various Sites | 308.5 | 361.4071 | 10%-19.9% | 17.15% | 17.15% | 1
17.33% | Purchase Tools and Equipment Less than $50,000 (2023) - Telecontrol | 40.4 | 47.4011 | 10%-19.9% | 17.33% | 17.33% | 1
17.35% | Purchase Tools and Equipment Less than $ 50,000 | 15.4 | 18.0717 | 10%-19.9% | 17.35% | 17.35% | 1
17.49% | Diesel Genset Replacements - Makkovik | 8900.2 | 10456.444 | 10%-19.9% | 17.49% | 17.49% | 1
17.56% | Diesel Genset Replacements (2021-2022) | 2846.8 | 3346.7633 | 10%-19.9% | 17.56% | 17.56% | 1
18.05% | SSL communication Link Upgrade - CAT | 163.1583 | 192.6158 | 10%-19.9% | 18.05% | 18.05% | 1
18.13% | Additions for Load - Isolated Generation Systems | 2182.5 | 2578.1254 | 10%-19.9% | 18.13% | 18.13% | 1
18.44% | Upgrade Equipment Doors - Various Sites | 348.5 | 412.7652 | 10%-19.9% | 18.44% | 18.44% | 1
19.02% | Overhaul Unit 2 - Cat Arm | 326.492 | 388.5783 | 10%-19.9% | 19.02% | 19.02% | 1
19.07% | Replace Standalone PBX Phone Systems (2023) | 175.5 | 208.9658 | 10%-19.9% | 19.07% | 19.07% | 1
19.21% | Purchase Metering and Metering Equipment - Various Sites | 198.5 | 236.6416 | 10%-19.9% | 19.21% | 19.21% | 1
19.83% | Replace Network Communications Equipment - Various | 199.5 | 239.053 | 10%-19.9% | 19.83% | 19.83% | 1
19.93% | Replace Human Machine Interface (2023) - Happy Valley Gas Turbine | 138.6 | 166.2288 | 10%-19.9% | 19.93% | 19.93% | 1
20.27% | Replace Disconnect Switches - Various (2021-22) | 1292.7 | 1554.6703 | 20%-29.9% | 20.27% | 20.27% | 1
20.66% | Upgrade Terminal Station for Mobile Substation - St. Anthony | 492 | 593.6632 | 20%-29.9% | 20.66% | 20.66% | 1
21.26% | Replace Instrument Transformers - Various (2022-23) | 402.3595 | 487.9087 | 20%-29.9% | 21.26% | 21.26% | 1
21.66% | Overhaul Unit 1 Turbine / Valve - Holyrood | 8026.6 | 9765.0063 | 20%-29.9% | 21.66% | 21.66% | 1
21.75% | Refurbish U5 Generatpr Stator -BDE | 5630 | 6854.3221 | 20%-29.9% | 21.75% | 21.75% | 1
22.03% | Install Raw Water Line - Holyrood | 1252.6 | 1528.5458 | 20%-29.9% | 22.03% | 22.03% | 1
22.83% | Replace Unit 2090/2044 - Charlottetown and Mary's Harbour | 401.022 | 492.5594 | 20%-29.9% | 22.83% | 22.83% | 1
23.88% | Wood Pole Line Management Program (2022) | 1603.5 | 1986.4668 | 20%-29.9% | 23.88% | 23.88% | 1
23.95% | Upgrade Data Alarm Systems - HRD (2019-20) | 636.8 | 789.3047 | 20%-29.9% | 23.95% | 23.95% | 1
24.43% | Construct Heated Storage for Spare Parts and Lube Oil - Hardwoods and Happy Valley | 49.8 | 61.9637 | 20%-29.9% | 24.43% | 24.43% | 1
24.76% | Upgrade Fuel Storage Tanks (2022) - Mary's Harbour | 499.1 | 622.6749 | 20%-29.9% | 24.76% | 24.76% | 1
25.13% | Upgrade Public Safety Around Dams and Waterways - BDE | 469.5 | 587.4774 | 20%-29.9% | 25.13% | 25.13% | 1
25.17% | Replace Network Communications Equipment - Various | 194 | 242.8356 | 20%-29.9% | 25.17% | 25.17% | 1
25.47% | Condition Assessment and Miscellaneous Upgrades - Holyrood | 2437.3 | 3058.1091 | 20%-29.9% | 25.47% | 25.47% | 1
26.29% | Replace Network Communications Equipment (2023) | 189 | 238.6899 | 20%-29.9% | 26.29% | 26.29% | 1
26.29% | Replace Automation Equipment - Rigolet | 363.8 | 459.4468 | 20%-29.9% | 26.29% | 26.29% | 1
27.29% | Perform Grounding Upgrades - Various Sites | 293.8 | 373.9864 | 20%-29.9% | 27.29% | 27.29% | 1
27.57% | Inspect Fuel Storage Tanks - Black Tickle | 818.7 | 1044.4445 | 20%-29.9% | 27.57% | 27.57% | 1
27.61% | Transmission In-Service Failures (2023) | 151.7 | 193.5891 | 20%-29.9% | 27.61% | 27.61% | 1
27.99% | Upgrade Compressed Air System - Happy Valley Gas Turbine | 145.8 | 186.6058 | 20%-29.9% | 27.99% | 27.99% | 1
29.07% | Unit 3 Generator Components Condition Assessment and Miscellaneous Upgrades | 422.0236 | 544.6956 | 20%-29.9% | 29.07% | 29.07% | 1
29.17% | Purchase Capital Spares - Hydraulic | 487.4 | 629.5901 | 20%-29.9% | 29.17% | 29.17% | 1
29.37% | Boiler Condition Assessment and Miscellaneous Upgrades - Holyrood | 3014.2 | 3899.3703 | 20%-29.9% | 29.37% | 29.37% | 1
29.64% | Boiler Condition Assessment/Upgrade - Holyrood | 3000 | 3889.2474 | 20%-29.9% | 29.64% | 29.64% | 1
30.06% | Install Frazil Ice Forecast - UPS | 176.987 | 230.1898 | 30%-39.9% | 30.06% | 30.06% | 1
30.32% | HLK-Annunciator Replacement | 371.1331 | 483.6696 | 30%-39.9% | 30.32% | 30.32% | 1
30.46% | Penstock Level II Condition Assessment - PRV | 196.8 | 256.7393 | 30%-39.9% | 30.46% | 30.46% | 1
30.46% | Replace Remote Terminal Units (2023) | 179.7 | 234.4336 | 30%-39.9% | 30.46% | 30.46% | 1
30.64% | Upgrade Station Lighting (2024-2025) - Bottom Waters, Deer Lake, Doyles, Indian River, and Western Avalon Terminal Stations | 520.6 | 680.1284 | 30%-39.9% | 30.64% | 30.64% | 1
31.24% | Refurbish Draft Tube Deck Phase 1 - BDE | 1032.4 | 1354.8981 | 30%-39.9% | 31.24% | 31.24% | 1
31.77% | Replace Accommodations and Septic System - Ebbegunbaeg | 1550.8 | 2043.4628 | 30%-39.9% | 31.77% | 31.77% | 1
32.15% | Hydraulic Unit Overhauls Program (2023) | 975.7 | 1289.4118 | 30%-39.9% | 32.15% | 32.15% | 1
32.74% | Overhaul Unit 1 - BDE | 202 | 268.1303 | 30%-39.9% | 32.74% | 32.74% | 1
32.88% | Replace PH1 Station Service Transformer - Bay d'Espoir | 401.2 | 533.1079 | 30%-39.9% | 32.88% | 32.88% | 1
33% | Replace Roof (2025) - Grey River | 390.8 | 519.7822 | 30%-39.9% | 33% | 33% | 1
33.02% | Upgrade Energy Management System (2022) - Hydro Place | 335.5683 | 446.3595 | 30%-39.9% | 33.02% | 33.02% | 1
33.07% | Replace Electromechanical Timers - Various Sites | 197.8 | 263.2126 | 30%-39.9% | 33.07% | 33.07% | 1
33.4% | Purchase Tools and Equipment Less than $50,000 (2022) | 42 | 56.0279 | 30%-39.9% | 33.4% | 33.4% | 1
33.92% | HRD - Major Overhaul: Unit 3 Extraction Pump North | 142.9 | 191.3764 | 30%-39.9% | 33.92% | 33.92% | 1
34.51% | Upgrade Work - Cat Arm | 1911.3 | 2570.9537 | 30%-39.9% | 34.51% | 34.51% | 1
34.55% | Wood Pole Line Management Program - Various Sites | 2404.1 | 3234.6081 | 30%-39.9% | 34.55% | 34.55% | 1
34.55% | Replace Battery Banks and Chargers - Various | 195.955 | 263.6608 | 30%-39.9% | 34.55% | 34.55% | 1
35.9% | CHT Winterize Unit 2102 and Install Mobile - Supplemental | 1314.7 | 1786.7325 | 30%-39.9% | 35.9% | 35.9% | 1
36.98% | Purchase Tools and Equipment less than $50,000 | 15.7 | 21.5057 | 30%-39.9% | 36.98% | 36.98% | 1
37.48% | Install Sub-Surface Drainage System - Paradise River | 524.9 | 721.6131 | 30%-39.9% | 37.48% | 37.48% | 1
37.56% | Unit 5 Generator Overhaul - BDE | 220.427 | 303.222 | 30%-39.9% | 37.56% | 37.56% | 1
37.76% | Purchase Meters and Metering Equipment - Various Sites | 198.8 | 273.866 | 30%-39.9% | 37.76% | 37.76% | 1
39.51% | Purchase Mobile Devices (2023) | 83.4 | 116.3509 | 30%-39.9% | 39.51% | 39.51% | 1
41.78% | Construction and Installation of an Electric Vehcile Fast Track Network | 259.4 | 367.7847 | 40%-49.9% | 41.78% | 41.78% | 1
41.95% | Replace Programmable Logic Controllers - Various Sites | 958 | 1359.9236 | 40%-49.9% | 41.95% | 41.95% | 1
42.09% | Condition Assessment and Miscellaneous Upgrades - Holyrood | 2749.6 | 3906.9442 | 40%-49.9% | 42.09% | 42.09% | 1
43.72% | In-Service Failures - Various Sites | 1000 | 1437.207 | 40%-49.9% | 43.72% | 43.72% | 1
45.61% | Install Automated Meter Reading - Labrador West | 967.2 | 1408.3221 | 40%-49.9% | 45.61% | 45.61% | 1
45.9% | Labrador City L22 Voltage Conversion (2022-2023) | 1491.2 | 2175.6355 | 40%-49.9% | 45.9% | 45.9% | 1
46.85% | Install Anemometer (2024) - Cat Arm | 68.6 | 100.7424 | 40%-49.9% | 46.85% | 46.85% | 1
46.99% | Replace Holyrood Thermal Generating Station T2 | 1393.157 | 2047.8321 | 40%-49.9% | 46.99% | 46.99% | 1
47.04% | Upgrade Uninterruptible Power Supply 3 & 4 - Holyrood | 348.7 | 512.7327 | 40%-49.9% | 47.04% | 47.04% | 1
47.52% | Replace Monorail Beams & Associated Mounts SRS - BDE | 592.8804 | 874.5932 | 40%-49.9% | 47.52% | 47.52% | 1
48.17% | Boiler Condition Assessment and Miscellaneous Upgrades (2023) - Holyrood | 2926.6 | 4336.3612 | 40%-49.9% | 48.17% | 48.17% | 1
48.67% | Upgrade Core OT Infrastructure (2023) | 171.7 | 255.2619 | 40%-49.9% | 48.67% | 48.67% | 1
49.42% | Condition Assessment and Miscellaneous Upgrades - Holyrood | 1968.8 | 2941.7036 | 40%-49.9% | 49.42% | 49.42% | 1
49.92% | Inspect Fuel Tanks (2024) - Hardwoods Gas Turbines | 692.9 | 1038.7661 | 40%-49.9% | 49.92% | 49.92% | 1
50.24% | Install Oil Spill Containment Transformer T1S (2023-2024) - Cat Arm | 581.6 | 873.8137 | 50%-59.9% | 50.24% | 50.24% | 1
50.38% | Refresh Cyber Security Infrastructure (2022) - Hydro Place | 221.7 | 333.3953 | 50%-59.9% | 50.38% | 50.38% | 1
51.37% | Diesel In-Service Failures (2023) | 480.4 | 727.1768 | 50%-59.9% | 51.37% | 51.37% | 1
51.54% | Install Variable Frequency Drives - Grey River | 169.9 | 257.4728 | 50%-59.9% | 51.54% | 51.54% | 1
52.4% | Refurbish Surge Tank 1 (2024-2025) - Bay d'Espoir | 2287.2 | 3485.6652 | 50%-59.9% | 52.4% | 52.4% | 1
52.71% | Penstock 3 Press Transducer - Bay d'Espoir | 29.5 | 45.0508 | 50%-59.9% | 52.71% | 52.71% | 1
52.75% | Perform Grounding Upgrades - Various Sites | 1719.4 | 2626.3449 | 50%-59.9% | 52.75% | 52.75% | 1
54.85% | Inspect Fuel Tanks (2025) - Stephenville | 676.9 | 1048.1662 | 50%-59.9% | 54.85% | 54.85% | 1
55.42% | Upgrade Station Lighting - BUCTS and HWDTS (2022-23) | 202.6364 | 314.9315 | 50%-59.9% | 55.42% | 55.42% | 1
55.54% | Upgrade Fault Recorders - WABTS (2022-2023) | 422.4 | 656.9887 | 50%-59.9% | 55.54% | 55.54% | 1
56.09% | Inspect Fuel Storage Tanks - Gray River | 203.1 | 317.0214 | 50%-59.9% | 56.09% | 56.09% | 1
56.11% | Replace Terminal Station Lighting (2023-2024) | 917.4 | 1432.1492 | 50%-59.9% | 56.11% | 56.11% | 1
58.2% | Replace Metering System | 5875.8 | 9295.4733 | 50%-59.9% | 58.2% | 58.2% | 1
58.32% | Replace Instrument Transformers - Various (2021-22) | 460.9 | 729.6884 | 50%-59.9% | 58.32% | 58.32% | 1
58.77% | Replace Sewage Lift System - Rigolet | 127.926 | 203.1138 | 50%-59.9% | 58.77% | 58.77% | 1
58.95% | Upgrade Data Alarm Management - OPD (2021-22) | 353.309 | 561.5813 | 50%-59.9% | 58.95% | 58.95% | 1
59.38% | Replace HVAC System (2023-2024) - Bishop's Falls | 172.2 | 274.4595 | 50%-59.9% | 59.38% | 59.38% | 1
61.09% | Replace Powerhouse Station Service Panel (2023-2024) - Upper Salmon | 1568.5 | 2526.6794 | 60%-69.9% | 61.09% | 61.09% | 1
63.8% | Upgrade of Worst-Performing Distribution Feeders (2021-2022) | 1124.5 | 1841.9017 | 60%-69.9% | 63.8% | 63.8% | 0
64.73% | Hydraulic In-Service Failures | 1250 | 2059.1178 | 60%-69.9% | 64.73% | 64.73% | 0
64.94% | Upgrade Bear Brook Crossing | 435.354 | 718.0934 | 60%-69.9% | 64.94% | 64.94% | 0
65% | Upgrade Public Safety Around Dams and Waterways (2023) | 482.1 | 795.4595 | 60%-69.9% | 65% | 65% | 0
67.68% | Replace Secondary Containment System Liner - Nain | 3089.6 | 5180.7068 | 60%-69.9% | 67.68% | 67.68% | 0
68.78% | Replace Frazil Ice Monitor System - HLK | 199.5 | 336.7249 | 60%-69.9% | 68.78% | 68.78% | 0
71.57% | General Property Rehabilitation (2024) - Hydro Place | 234 | 401.482 | 70%-79.9% | 71.57% | 71.57% | 0
71.63% | Replace Annunciator Panels (2024-2025) - Cat Arm | 351.4 | 603.0922 | 70%-79.9% | 71.63% | 71.63% | 0
71.98% | Purchase Tools and Equipment Less than $ 50,000 | 21 | 36.1166 | 70%-79.9% | 71.98% | 71.98% | 0
74.46% | Terminal Station In-Service Failures | 1000 | 1744.6067 | 70%-79.9% | 74.46% | 74.46% | 0
75.53% | Replace Transformer T7 - HRD | 2678.14 | 4701.0658 | 70%-79.9% | 75.53% | 75.53% | 0
75.74% | Replace Building Exterior (2023-2024) - Postville | 683.3 | 1200.8386 | 70%-79.9% | 75.74% | 75.74% | 0
76.35% | Construct LO Cooler Hood - Holyrood Gas Turbine | 318.8 | 562.2037 | 70%-79.9% | 76.35% | 76.35% | 0
78.5% | Replace Protective Relays - Various Sites | 1857 | 3314.7093 | 70%-79.9% | 78.5% | 78.5% | 0
80.07% | Wood Pole Line Management Program (2023) | 2824.4 | 5085.8377 | 80%-89.9% | 80.07% | 80.07% | 0
80.53% | Replace Underground Fire Water Distribution System - Holyrood | 1706.3 | 3080.4524 | 80%-89.9% | 80.53% | 80.53% | 0
82.2% | Replace Intermediate Fuel Storage Tanks (2023-2024) - Nain | 721.1 | 1313.8397 | 80%-89.9% | 82.2% | 82.2% | 0
82.21% | Replace Emergency Lift (2023) - Salmon River Spillway | 49.8 | 90.7418 | 80%-89.9% | 82.21% | 82.21% | 0
84.76% | Major Pumps Overhaul - Holyrood | 491.3 | 907.7166 | 80%-89.9% | 84.76% | 84.76% | 0
86.19% | Thermal In-Service Failures | 1250 | 2327.4256 | 80%-89.9% | 86.19% | 86.19% | 0
87.95% | Upgrade Breaker Failure Protection (2020-2021) | 510.169 | 958.8475 | 80%-89.9% | 87.95% | 87.95% | 0
92.6% | Overhaul Pumps (2023) - Holyrood | 742.4 | 1429.8882 | 90%-99.9% | 92.6% | 92.6% | 0
92.78% | Replace Pump House and Associated Equipment - Bay d'Espoir | 545.2 | 1051.0373 | 90%-99.9% | 92.78% | 92.78% | 0
96.78% | Refurbish BioGreen Sewage System (2023) - Holyrood | 256.6 | 504.9448 | 90%-99.9% | 96.78% | 96.78% | 0
103.6% | Replace Instrument Transformers - Various (2020-21) | 339.054 | 690.3462 | >100% | 103.6% | 103.6% | 0
104.8% | Upgrade Underground Plant Drainage System - Holyrood | 923.1 | 1890.807 | >100% | 104.8% | 104.8% | 0
108.3% | Water System Condition Assessment and Upgrades (2023) - Bay d'Espoir | 665.9 | 1387.0284 | >100% | 108.3% | 108.3% | 0
109.7% | Upgrade SCADA Network (2024) | 402.3 | 843.668 | >100% | 109.7% | 109.7% | 0
115.9% | Upper Salmon Hydroelectric Generating Station Rotor Rim Shrink and Stator Recentering - Supplemental | 4236.3289 | 9146.6379 | >100% | 115.9% | 115.9% | 0
116% | Thermal In-Service Failures | 1250 | 2699.9082 | >100% | 116% | 116% | 0
119% | Terminal Station In-Service Failures (2023) | 1300 | 2846.6948 | >100% | 119% | 119% | 0
120.1% | Perform Grounding Upgrades - Various (2019-20) | 1845.5 | 4061.3314 | >100% | 120.1% | 120.1% | 0
122.8% | Purchase Tools and Equipment Less than $50,000 (2023) - Thermal Plants | 55.1 | 122.782 | >100% | 122.8% | 122.8% | 0
126.9% | Terminal Station In-Service Failures | 1000 | 2268.9446 | >100% | 126.9% | 126.9% | 0
150.4% | Overhaul Unit 6 - BDE | 225.4 | 564.4001 | >100% | 150.4% | 150.4% | 0
151.6% | Refurbish Sump Level Control System - Cat Arm | 355.923 | 895.6326 | >100% | 151.6% | 151.6% | 0
156.5% | Replace Data Alarm System Annunciators (2023) - Buchans | 166 | 425.808 | >100% | 156.5% | 156.5% | 0
172.1% | Hydraulic In-Service Failures (2023) | 1500 | 4081.0911 | >100% | 172.1% | 172.1% | 0
186.3% | Install Breaker Failure Protection - Various Sites | 277 | 793.1427 | >100% | 186.3% | 186.3% | 0
186.7% | Draft Tube Deck Substructure Level 2 Condition Assessment | 343.6 | 984.9386 | >100% | 186.7% | 186.7% | 0
190.4% | Thermal In-Service Failure - Holyrood | 2000 | 5807.515 | >100% | 190.4% | 190.4% | 0
219.4% | Install Remote Seepage Monitoring System - BDE | 394.7 | 1260.66 | >100% | 219.4% | 219.4% | 0
410% | Install Breaker Failure Protection (2023-2024) - Sunnyside | 289.7 | 1477.4993 | >100% | 410% | 410% | 0
947.9% | Gas Turbine In-Service Failures (2023) | 344.2 | 3606.7459 | >500% | 947.9% | 947.9% | 0
Grand Total |  | 1055746.0316 | 999209.8798

## Exclusions
Project # | Year Started | Year Closed | Project Description | CBA / CAPEX Title | Budget | Actual Cost |  | Var $ | Var %
13501791 | 2017 | 2017 | BWT-Additions for Load Growth | Additions for Load Growth - Bottom Waters | 3045 | 3024.8317 |  | -20.1683 | -0.6623%
12961791 | 2017 | 2017 | HRD-Exciter Controls Replcmnt | Exciter Controls Replacement - Holyrood | 1349.2 | 1339.8812 |  | -9.3188 | -0.6907%
12931791 | 2017 | 2017 | BDE Unit 3 Turb Rehabilitation | Unit 3 Turbine Rehabilitation - Bay d'Espoir | 2361.5 | 1905.3701 |  | -456.1299 | -19.32%
12931792 | 2017 | 2017 | BDE Penstock #2 Refurbishment | Penstock #2 Refurbishment - Bay d'Espoir | 9063.7 | 3586.3227 |  | -5477.3773 | -60.43%
21841791 | 2017 | 2017 | HVY GT Engine Refurbishments | Repair and Advanced Overhaul of the Happy Valley Gas Turbine | 3714.8 | 2049.2883 |  | -1665.5117 | -44.83%
12961792 | 2017 | 2018 | HRD-Reliability & Perform Upgr | Reliability Improvements - Holyrood | 2610 | 3883.9136 |  | 1273.9136 | 48.81%
12961693 | 2016 | 2018 | HRD-12MW Diesel Generation | Purchase of 12 MW Diesel Generation - Holyrood | 4700 | 4959.3215 |  | 259.3215 | 5.517%
13881791 | 2017 | 2018 | Wabush TS Upgrades (Twinco) | Terminal Station Upgrades - Wabush | 2912.5 | 1962.0603 |  | -950.4397 | -32.63%
13501891 | 2018 | 2018 | WRSB-HampdenWasteTransferSite | Provide Service to Western Regional Servce Board's Waste Transfer Site - Hampden | 748.4 | 644.5 |  | -103.9 | -13.88%
13961891 | 2018 | 2018 | Smokey Mountain-Line Upgrade | Perform Voltage Conversion of the Distribution Feeder VA26 - Labrador City | 719.4 | 705.1371 |  | -14.2629 | -1.983%
12961891 | 2018 | 2018 | HRD-Improve Boiler Capacity | Improve Boiler Capacity - Holyrood | 2560.5 | 1665.9473 |  | -894.5527 | -34.94%
13961892 | 2018 | 2018 | HVY - Gang Switch | Gang Switch - Happy Valley-Goose Bay | 195.4 | 85.1934 |  | -110.2066 | -56.4%
12811991 | 2019 | 2019 | HLK-Overhaul Unit 1 | Hinds Lake Unit Major Overhaul | 259.5 | 422.9321 |  | 163.4321 | 62.98%
12931991 | 2019 | 2019 | Penstock InspectionBDE,HLK,GCL | Level II Condition Assessments for Bay d'espoir Penstock 4, Granite Canal Penstock, and Hinds Lake Penstock | 414.3 | 294.4446 |  | -119.8554 | -28.93%
14281891 | 2018 | 2019 | TL226/TL239 ReRoute-Northern | TL226 and TL239 Reroute | 932.4 | 994.0751 |  | 61.6751 | 6.615%
12931892 | 2018 | 2019 | BDE-Penstock Cond Assessments | Penstock Condition Assessments - Bay d'Espoir | 1120.6 | 1832.673 |  | 712.073 | 63.54%
14111891 | 2018 | 2019 | Mary's Harbour Hydro Intergrat | Mary's Harbour Hydro Integration - CIAC | 195.5 | 242.67 |  | 47.17 | 24.13%
13882092 | 2020 | 2020 | Interconn BlockLab Data Center | Construction of a line extension and the installation of power usage monitoring and control equipment at the BlockLab site | 244 | 295.0094 |  | 51.0094 | 20.91%
12962091 | 2020 | 2020 | SUP OH U2 Turbine Valves -HRD | Overhaul Unit 2 Turbine Valves - Holyrood | 2919.5 | 3159.2509 |  | 239.7509 | 8.212%
12962092 | 2020 | 2020 | SUP Overhaul Unit 2 Genera HRD | Overhaul Unit 2 Generator - Holyrood | 1294.1 | 1410.2104 |  | 116.1104 | 8.972%
12962093 | 2020 | 2020 | SUP Overh.U3 Boiler FeedPu HRD | Overhaul Unit 3 Boiler Feed Pump West - Holyrood | 367.9 | 369.4504 |  | 1.5505 | 0.4214%
12972094 | 2020 | 2020 | SUP BoilerCon.Asses.MiscUpgHRD | Boiler Condition Assessment and Miscellaneous Upgrades - Holyrood | 3056.7 | 3221.1775 |  | 164.4775 | 5.381%
12422011 | 2020 | 2020 | Nain Diesel Plant Fibre Upgrad | Diesel Plant Fibre Upgrade - Nain | 44.773 | 37.1142 |  | -7.6588 | -17.11%
12962106 | 2021 | 2021 | Overhaul Unit 1 bolier Pump | Holyrood Overhaul Unit 1 boiler feed pump | 443.022 | 554.6588 |  | 111.6368 | 25.2%
14112102 | 2021 | 2021 | CHT Purchase Diesel Gen U 2102 | CHT Purchase Diesel | 350 | 350 |  | 0 | 0%
13401801 | 2018 | 2022 | Inc Fuel & Water Treatment Cap | Increase Fuel and Water Treatment System Capacity - Holyrood Gas Turbine | 11842.6 | 7625.4773 |  | -4217.1227 | -35.61%
14101802 | 2018 | 2022 | STA-Rplc Automation Eqmt-18/19 | Replace Automation Equipment - St. Anthony | 1873.3 | 2516.4073 |  | 643.1073 | 34.33%
13851901 | 2019 | 2022 | MF-HV Interconnect | Muskrat Falls to Happy Valley Interconnection | 19978.5 | 22693.8395 |  | 2715.3395 | 13.59%
13252201 | 2022 | 2022 | Terminal Stat In-Serv Failures | Terminal Station In-Service Failures (2022) | 900 | 3626.0948 |  | 2726.0948 | 302.9%
12932208 | 2022 | 2022 | Hydraulic In-Service Failures | Hydraulic Generation In-Service Failures (2022) | 1000 | 1425.7794 |  | 425.7794 | 42.58%
12962201 | 2022 | 2022 | Thermal In-Service Failures 22 | Thermal In-Service Failures (2022) | 2000 | 2893.7743 |  | 893.7743 | 44.69%
13252118 | 2021 | 2024 | Upgrd Retire SVLGT-BBK T4 | Upgrades for Future Retirement of Stephenville Gas Turbine | 6874.9 | 5115.5786 |  | -1759.3214 | -25.59%
13462304 | 2023 | 2024 | Rpl Diesel Shop Building BIF | Replace Diesel Shop Building (2023-2025) - Bishop's Falls | 1422.1 | 241.8687 |  | -1180.2313 | -82.99%
12982401 | 2024 | 2024 | Remove Safety Hazards - Var | Remove Safety Hazards (2024) | 198.3 | 322.4833 |  | 124.1833 | 62.62%
13332401 | 2024 | 2024 | Diesel In-Service Failures 24 | Diesel In-Service Failures (2024) | 488.3 | 1984.5096 |  | 1496.2096 | 306.4%
21882401 | 2024 | 2024 | Gas Turbine In-Service Fail 24 | Gas Turbine In-Service Failures (2024) | 358 | 7101.6794 |  | 6743.6794 | 1884%
12932401 | 2024 | 2024 | Hydraulic In-Serv Failures 24 | Hydraulic In-Service Failures (2024) | 1500 | 2973.945 |  | 1473.945 | 98.26%
20682406 | 2024 | 2024 | Upgr Energy MGMT System 24 | Upgrade Energy Management System (2024) | 366.4 | 4.6125 |  | -361.7875 | -98.74%
12422403 | 2024 | 2024 | Telecom ISFs 24 | Telecommunications In-Service Failure (2024) | 91.4 | 253.8086 |  | 162.4086 | 177.7%
13252402 | 2024 | 2024 | Terminal Station ISFs 24 | Terminal Station In-Service Failures (2024) | 1300 | 2459.2469 |  | 1159.2469 | 89.17%
13492403 | 2024 | 2024 | Transmission ISFs 2024 | Transmission In-Service Failures (2024) | 158.5 | 162.2437 |  | 3.7437 | 2.362%
12962401 | 2024 | 2024 | Thermal In-Service Failures 24 | Thermal In-Service Failures (2024) | 3508.7 | 4587.7513 |  | 1079.0513 | 30.75%
13462204 | 2022 | 2024 | Replace Vehicles and Aerial | Replace Light- and Heavy-Duty Vehicles (2022-2024) | 3481.8 | 2975.6269 |  | -506.1731 | -14.54%
13252308 | 2023 | 2024 | Rpl Instr Transforms VAR 23/24 | Replace Instrument Transformers VAR 23/24 | 508.2 | 685.8358 |  | 177.6358 | 34.95%
13252307 | 2023 | 2024 | Replace Disconnects 23/24 | Replace Disconnects 23/24 | 652.8 | 1081.3524 |  | 428.5524 | 65.65%
14302301 | 2023 | 2024 | Rpl TS Battery Banks/Chargers | Replace Terminal Station Battery Banks/Chargers | 218.2 | 207.23 |  | -10.97 | -5.028%
13502303 | 2023 | 2024 | Upg Distribution Feeders 23/24 | Upgrade of Worst-Performing Distribution Feeders (2023-2024) | 1446 | 2092.0239 |  | 646.0239 | 44.68%
13462302 | 2023 | 2024 | Rplc Mobile equipment 2023 | Replace Mobile Equipment (2023-2024) | 728.5 | 764.6125 |  | 36.1125 | 4.957%
13252304 | 2023 | 2024 | Upgr Power Transformers 23/24 | Upgrade Power Transformers 23/24 | 3979.3 | 4872.9742 |  | 893.6742 | 22.46%
13252303 | 2023 | 2024 | Circuit Breakers Ren prg 23/24 | Circuit Breakers Renewal Program 23/24 | 3812 | 5578.6897 |  | 1766.6897 | 46.35%
13252306 | 2023 | 2024 | Replace Protective Relays-M24 | Replace Protective Relays - M24 | 1959.7 | 2889.149 |  | 929.449 | 47.43%
13332402 | 2024 | 2024 | Overhaul Diesel Units-Var 24 | Overhaul Diesel Units -Var 24 | 829.2 | 1300.3095 |  | 471.1095 | 56.81%
13492401 | 2024 | 2024 | Wood Pole Line Management Prgm | Wood Pole Line Management (2024) | 3765.2 | 5122.7667 |  | 1357.5667 | 36.06%
20682405 | 2024 | 2024 | Prfm soft upgrs/minor echan 24 | Perform Software Upgrades and Minor Enhancements (2024) | 864.2 | 337.0688 |  | -527.1312 | -61%
20682403 | 2024 | 2024 | Upgrade Core IT/OT Infrast 24 | Upgrade Core OT Infrastructure (2024) | 174.7 | 148.1279 |  | -26.5721 | -15.21%
20682404 | 2024 | 2024 | Upde Cyber Security Software24 | Update Cyber Security Infrastructure (2024) | 281.3 | 409.501 |  | 128.201 | 45.57%
12422402 | 2024 | 2024 | Rplc Network Comms EQ 2024 | Replace Network Communications Equipment (2024) | 180.7 | 235.1952 |  | 54.4952 | 30.16%
12422409 | 2024 | 2024 | Minor Telecomm Enhancements 24 | Minor Telecommunications Enhancements (2024) | 96.9 | 87.5957 |  | -9.3043 | -9.602%
12422408 | 2024 | 2024 | Pur Mobile Devices Hydro 24 | Purchase Mobile Devices (2024) | 155.6 | 166.5659 |  | 10.9659 | 7.048%
12972402 | 2024 | 2024 | HRD-Boiler Cond Asst Upgr 24 | Boiler Condition Assessment and Miscellaneous Upgrades (2024) - Holyrood | 3957.8 | 7864.5455 |  | 3906.7455 | 98.71%
12962404 | 2024 | 2024 | Overhaul Pumps Holyrood 24 | Overhaul Pumps (2024) - Holyrood | 661 | 134.7362 |  | -526.2638 | -79.62%
12422411 | 2024 | 2024 | Rplc 48VDC Batt/Charg VAR 24 | Replace 48 V Battery Banks and Chargers (2024) | 422.2 | 253.2494 |  | -168.9506 | -40.02%
13072402 | 2024 | 2024 | Meters and Metering Equipment | Purchase Meters and Metering Equipment (2024) | 470.7 | 443.0241 |  | -27.6759 | -5.88%
12422414 | 2024 | 2024 | Upgr Remote Terminals Units 24 | Upgrade Remote Terminal Units (2024) | 165.9 | 200.5309 |  | 34.6309 | 20.87%
12972293 | 2022 | 2024 | HRD SUPP Refurb Tank 1 (2022) | Holyrood Fuel Tank #1 Fuel Inspection And Refurbishment - Supplemental | 2052.1 | 5793.7505 |  | 3741.6505 | 182.3%
12932403 | 2024 | 2024 | Pur Tools/Eq under 50k Hydra24 | Purchase Tools and Equipment Less than $50,000 (2024) - Hydraulic Plants | 209.4 | 177.7685 |  | -31.6315 | -15.11%
12422405 | 2024 | 2024 | Purchase Tools and Equipment | Purchase Tools and Equipment Less than $50,000 (2024) - Telecontrol | 45.6 | 44.5092 |  | -1.0908 | -2.392%
13402401 | 2024 | 2024 | Purchase Tools & Equipment -GT | Purchase Tools and Equipment Less than $50,000 (2024) - Gas Turbine | 18.6 | 19.4235 |  | 0.82355 | 4.428%
12962407 | 2024 | 2024 | Tools and Equip. Thermal 24 | Purchase Tools and Equipment Less than $50,000 (2024) - Thermal Plants | 167.1 | 152.2695 |  | -14.8305 | -8.875%
20082402 | 2024 | 2024 | Purchase office equipment <50k | Purchase Office Equipment Less Than $50,000 (2024) | 50 | 55.0579 |  | 5.0579 | 10.12%
20082491 | 2024 | 2024 | HYP Office Retrofits | Perform Office Modifications (2024) - Hydro Place | 249.809 | 96.367 |  | -153.442 | -61.42%
13252504 | 2025 | 2025 | Terminal Station ISFs 25 | Terminal Station In-Service Failures (2025) | 2500 | 516.0051 |  | -1983.9949 | -79.36%
12962501 | 2025 | 2025 | Thermal In-Service Failures 25 | Thermal In-Service Failures (2025) | 3900 | 3058.7405 |  | -841.2595 | -21.57%
12422503 | 2025 | 2025 | Telecom ISFs 25 | Telecommunications In-Service Failures (2025) | 94.1 | 76.9914 |  | -17.1086 | -18.18%
13492501 | 2025 | 2025 | Transmission ISFs 2025 | Transmission In-Service Failures (2025) | 184.3 | 162.3248 |  | -21.9752 | -11.92%
14012502 | 2025 | 2025 | Diesel In-Service Failures 25 | Diesel In-Service Failures (2025) | 800 | 758.4302 |  | -41.5698 | -5.196%
21882501 | 2025 | 2025 | Gas Turbine In-Service Fail 25 | Gas Turbine In-Service Failures (2025) | 500 | 1868.1898 |  | 1368.1898 | 273.6%
20082590 | 2025 | 2025 | Inst Work Stations LVL 3&4 HYP | Supply & Install New Work Stations Level 4 Hydro Place (2025) | 747.767 | 707.3335 |  | -40.4335 | -5.407%
14272490 | 2024 | 2025 | Main Brook L1 Recon 24/25 | Additions for Load - Distribution Systems (2024-2026) - Main Brook | 353.02 | 483.5244 |  | 130.5044 | 36.97%
12942590 | 2025 | 2025 | Procure Stop Logs BDE unit 1-7 | Procure Stop Logs for Bay D'Espoir Units 1-7 | 740 | 728.584 |  | -11.416 | -1.543%
12422490 | 2024 | 2025 | Inst site-wide Radio Sys HRD | Purchase & Install Site Radio System (2024) - Holyrood | 412.2 | 425.2118 |  | 13.0118 | 3.157%
20082492 | 2024 | 2025 | HYP 4th fl fire restore | Completion of Fire Restoration – Fourth Floor Hydro Place | 1067.9 | 1151.9531 |  | 84.0531 | 7.871%
13332592 | 2025 | 2025 | Install Add Fuel Tank Ram 25 | Install Additional Fuel Tank Ramea (2025) | 232.5 | 179.1124 |  | -53.3876 | -22.96%
12962402 | 2024 | 2025 | Upgr DCS Hware Unit 1/3 BMS 3 | Upgrade DCS Hardware - Units 1 and 2 (2024-2025) - Holyrood | 472.5 | 616.5842 |  | 144.0842 | 30.49%
13972403 | 2024 | 2025 | Upg Distribution Feeders 24/25 | Upgrade Worst-Performing Distribution Feeders (2024-2025) | 3291.7 | 5505.7124 |  | 2214.0124 | 67.26%
13502404 | 2024 | 2025 | Distr Feeders Refurb 24/25 | Renew Distribution Feeders (2024-2025) | 2532.4 | 2433.3572 |  | -99.0428 | -3.911%
14112201 | 2022 | 2025 | Add Load 22 - MSH SER CON | Additions for Load (2022) - Mary's Harbour Service Conductor | 359.1 | 183.1224 |  | -175.9776 | -49.01%
13882101 | 2021 | 2025 | WAB Substation Ugrde-M23 | Additions for Load - Wabush Substation Upgrades | 10694.1 | 8995.2589 |  | -1698.8411 | -15.89%
20682504 | 2025 | 2025 | Upde Cyber Security Infrast25 | Update Cyber Security Infrastructure (2025) | 115.6 | 68.185 |  | -47.415 | -41.02%
12422502 | 2025 | 2025 | Rplc Network Comms EQ 2025 | Replace Network Communications Equipment (2025) | 413.2 | 246.0502 |  | -167.1498 | -40.45%
13402503 | 2025 | 2025 | Purchase Tools & Equipment -GT | Purchase Tools and Equipment (2025) - Gas Turbines | 46.6 | 30.3801 |  | -16.2199 | -34.81%
20682505 | 2025 | 2025 | Prfm soft upgrs/minor echan 25 | Perform Software Upgrades and Minor Enhancements (2025) | 808.7 | 565.4577 |  | -243.2423 | -30.08%
12962505 | 2025 | 2025 | Tools and Equip. Thermal 25 | Purchase Tools and Equipment (2025) - Thermal Plants | 127.3 | 100.6117 |  | -26.6883 | -20.96%
13252403 | 2024 | 2025 | Upgr Power Transformers 24/25 | Upgrade Power Transformers (2024-2025) | 3575.9 | 5209.2209 |  | 1633.3209 | 45.68%
12422508 | 2025 | 2025 | Pur Mobile Devices Hydro 25 | Purchase Mobile Devices (2025) | 160.2 | 132.4761 |  | -27.7239 | -17.31%
13252401 | 2024 | 2025 | Circuit Breakers Ren prg 24/25 | Renew Circuit Breakers (2024–2025) | 2304 | 2271.086 |  | -32.914 | -1.429%
14112204 | 2022 | 2025 | Diesel Genset RplcUnit2012 LAL | Diesel Genset Replacement Unit 2012 - L'Anse-Au-Loup | 3063.3 | 2699.8056 |  | -363.4944 | -11.87%
20682503 | 2025 | 2025 | Upgrade Core IT/OT Infrast 25 | Upgrade Core OT Infrastructure (2025) | 674.3 | 621.8872 |  | -52.4128 | -7.773%
20082502 | 2025 | 2025 | Perf Security Improvements 25 | Perform Security Improvements (2025) | 160.7 | 150.6949 |  | -10.0051 | -6.226%
12422509 | 2025 | 2025 | Minor Telecomm Enhancements 25 | Perform Minor Telecommunications Enhancements (2025) | 99.8 | 96.904 |  | -2.896 | -2.902%
12962405 | 2024 | 2025 | Overhaul unit 1 turb/valves 24 | Overhaul Unit 1 Turbine Valves and Generator (2024) - Holyrood | 5181.4 | 11724.3023 |  | 6542.9023 | 126.3%
12962304 | 2023 | 2025 | Overhaul unit 2 turb/valves 23 | Overhaul Unit 2 Turbine and Valves (2023) - Holyrood | 9701.8 | 12628.3989 |  | 2926.5989 | 30.17%
12422506 | 2025 | 2025 | Upgr Remote Terminals Units 25 | Upgrade Remote Terminal Units (2025) | 238.4 | 240.9255 |  | 2.5255 | 1.059%
12422501 | 2025 | 2025 | Rplc 48V Batt Banks/Chargers25 | Replace 48 V Battery Banks and Chargers (2025) | 559.1 | 566.6032 |  | 7.5032 | 1.342%
12422505 | 2025 | 2025 | Purchase Tools and Equipment | Purchase Tools and Equipment (2025) - Telecontrol | 45.3 | 46.029 |  | 0.72897 | 1.609%
14012501 | 2025 | 2025 | Overhaul Diesel Units 25 | Overhaul Diesel Units (2025) | 1000 | 1102.2838 |  | 102.2838 | 10.23%
13252408 | 2024 | 2025 | Replace Protective Relays-M25 | Replace Protective Relays (2024–2025) | 3439.1 | 5120.0159 |  | 1680.916 | 48.88%
20082501 | 2025 | 2025 | Mod Office Bldg Procure Eq 25 | Modify Office Buildings and Procure Furniture, Fixtures, & Equipment (2025) | 178.5 | 214.4658 |  | 35.9658 | 20.15%
12932503 | 2025 | 2025 | Pur Tools & Eq. Hydraulic | Purchase Tools and Equipment (2025) - Hydraulic Plants | 154.9 | 191.8962 |  | 36.9962 | 23.88%
13462401 | 2024 | 2025 | Rplc Mobile equipment 2024 | Replace Mobile Equipment (2024-2025) | 816.6 | 884.8293 |  | 68.2293 | 8.355%
12932501 | 2025 | 2025 | Hydraulic In-Serv Failures 25 | Hydraulic In-Service Failures (2025) | 2000 | 2723.2428 |  | 723.2428 | 36.16%
13492502 | 2025 | 2025 | Wood Pole Line Management Prgm | Wood Pole Line Management (2025) | 4281.3 | 5877.517 |  | 1596.2169 | 37.28%
13252409 | 2024 | 2025 | Replace Disconnects 24/25 | Replace Disconnects (2024–2025) | 1485.5 | 2233.1765 |  | 747.6765 | 50.33%
13462301 | 2023 | 2025 | Rplc Light/Heavy Duty Mbl Equi | Replace Light- and Heavy-Duty Vehicles (2023-2025) | 4566 | 5443.1925 |  | 877.1925 | 19.21%
12972502 | 2025 | 2025 | Boiler CA/Misc Upgr 25 HRD | Perform Boiler Condition Assessment and Miscellaneous Upgrades (2025) - Holyrood | 4905.8 | 8085.6781 |  | 3179.8781 | 64.82%
12982501 | 2025 | 2025 | Remove Safety Hazards 25 | Remove Safety Hazards (2025) | 203.3 | 340.2559 |  | 136.9559 | 67.37%
13252406 | 2024 | 2025 | Rpl Instr Transforms VAR 24/25 | Replace Instrument Transformers (2024–2025) | 869.7 | 1344.0434 |  | 474.3434 | 54.54%
13252404 | 2024 | 2025 | Repl TS Batt Banks/Chargers24 | Replace Terminal Station Battery Banks and Chargers (2024–2025) | 192.7 | 301.8753 |  | 109.1753 | 56.66%
12962502 | 2025 | 2025 | Overhaul Pumps Holyrood 25 | Overhaul Major Pumps (2025) - Holyrood | 1101.9 | 2826.12 |  | 1724.22 | 156.5%
119 |  |  |  |  | 212440.6909 | 251112.4379 | 0 | 38671.747 | 18.2%
Allowance for Unforeseen Projects Excluded from RFI Response (Revised Statistical Analysis Tab)
By nature of these projects, they do not have a set budget to compare the actuals against. | [5 empty] | Actuals
12931793 | 2017 | 2017 | Emerg Repairs BDE Penstock 1 | Emergency Repairs Penstock #1 - Bay d'Espoir |  | 4598.7573
13491791 | 2017 | 2017 | Trans.Line Emergency Refurb | Transmission Line Emergency Refurbishments |  | 506.1766
12931891 | 2018 | 2018 | BDE Penstock Refurbishment | Penstock #3 Refurbishment - Bay d'Espoir |  | 4743.1787
14011891 | 2018 | 2019 | RIG-Replace Engine 2051 | Replace Engine #2051 - Rigolet |  | 537.5907
14111991 | 2019 | 2020 | CHT Diesel Plant Restore Servi | Charlottetown Diesel Plant Restore Service Following Fire |  | 882.2377

## REVISED Analysis Data
Project # | Year Started | Year Closed | JDE Title | CBA / CAPEX Title | Budget | Actual Cost | Var $ | Var % | Included/ Excluded in Original Analysis | Reason for Exclusion
13251602 | 2016 | 2017 | Replace Surge Arrestors | Replace Surge Arrestors - Various Sites | 197.4 | 175.0706 | -22.3294 | -11.31% | Included in Original Analysis | N/A
13251606 | 2016 | 2017 | Upgrd Digital Fault Recorders | Upgrade Digital Fault Recorders - Various Sites | 502.5 | 550.0368 | 47.5368 | 9.46% | Included in Original Analysis | N/A
13251613 | 2016 | 2017 | Upgrade Warehouse Lighting-BIF | Upgrade Warehouse Lighting - Bishop's Falls | 195.6 | 121.6659 | -73.9341 | -37.8% | Included in Original Analysis | N/A
14301601 | 2016 | 2017 | CHD-Upgrd TS Mobile Substation | Upgrade Terminal Station for Mobile Substation - Cow Head | 484.7 | 387.3143 | -97.3857 | -20.09% | Included in Original Analysis | N/A |  | Values
13251708 | 2017 | 2017 | HRD-Upgrd Alum Supp Structures | Upgrade Aluminum Support Structures - Holyrood | 352.9 | 190.8158 | -162.0842 | -45.93% | Included in Original Analysis | N/A | Year Closed | Sum of Budget | Sum of Actual Cost | Sum of Var $
13251715 | 2017 | 2017 | VAR-Upgr Equipment Foundations | Upgrade Equipment Foundations - Various Sites | 389.2 | 245.336 | -143.864 | -36.96% | Included in Original Analysis | N/A | 2017 | 51531.3 | 48135.7016 | -3395.5984 | -6.589%
12421614 | 2016 | 2017 | Hydrometeorological Equipment | Install Hydrometeorological Equipment - Various Sites | 314.1 | 183.3448 | -130.7553 | -41.63% | Included in Original Analysis | N/A | 2018 | 128434.9 | 114703.0601 | -13731.8399 | -10.69%
12811603 | 2016 | 2017 | HLK-Rplc Cntrl/Comm Room A/C | Replace Control Room/Communications Room Air Conditioning - Hinds Lake | 94.3 | 96.4168 | 2.1168 | 2.245% | Included in Original Analysis | N/A | 2019 | 391099.1293 | 381220.7395 | -9878.3898 | -2.526%
12901501 | 2015 | 2017 | CAT-Stat.Serv BRKR Replacement | Replace Station Service Breakers - Cat Arm | 1008.3 | 1036.8004 | 28.5004 | 2.827% | Included in Original Analysis | N/A | 2020 | 87133.8628 | 65911.4278 | -21222.435 | -24.36%
12931509 | 2015 | 2017 | BDE-Upgrade Equipment Doors | Upgrade Equipment Doors - Various Sites | 348.5 | 412.7652 | 64.2652 | 18.44% | Included in Original Analysis | N/A | 2021 | 146289.126 | 133293.9097 | -12995.2163 | -8.883%
12931514 | 2015 | 2017 | EBBE-Accommodations/SepticSyst | Replace Accommodations and Septic System - Ebbegunbaeg | 1550.8 | 2043.4628 | 492.6628 | 31.77% | Included in Original Analysis | N/A | 2022 | 62943.075 | 59177.8435 | -3765.2315 | -5.982%
12931606 | 2016 | 2017 | BDE-Rplc Station Service XFMR | Replace PH1 Station Service Transformer - Bay d'Espoir | 401.2 | 533.1079 | 131.9079 | 32.88% | Included in Original Analysis | N/A | 2023 | 93835.5952 | 89924.7251 | -3910.8701 | -4.168%
12971702 | 2017 | 2017 | HRD-Upgrade Access Roads | Upgrade Holyrood Access Road - Holyrood | 1162.6 | 825.6932 | -336.9068 | -28.98% | Included in Original Analysis | N/A | 2024 | 56323.1703 | 61026.144 | 4702.9737 | 8.35%
12421601 | 2016 | 2017 | Rplc Battery Banks & Chargers | Replace Battery Banks and Chargers - Various Sites | 881.6 | 645.2465 | -236.3535 | -26.81% | Included in Original Analysis | N/A | 2025 | 38155.873 | 45816.3285 | 7660.4555 | 20.08%
12421602 | 2016 | 2017 | Rpl MDR4000 MicrowaveRadioEast | Replace MDR 4000 Microwave Radio East - Various Sites | 1170.5 | 1154.4371 | -16.0629 | -1.372% | Included in Original Analysis | N/A | Grand Total | 1055746.0316 | 999209.8798 | -56536.1518 | -5.355%
12421603 | 2016 | 2017 | Replace UPS Systems-HydroPlace | Replace UPS Systems - Hydro Place | 889.8 | 978.5309 | 88.7309 | 9.972% | Included in Original Analysis | N/A
12421608 | 2016 | 2017 | MDR,HVY-Terminal Station A/C's | Replace Air Conditioners - Various Sites | 191.9 | 196.2608 | 4.3608 | 2.272% | Included in Original Analysis | N/A
12421613 | 2016 | 2017 | Powerline Carrier-TL214/TL239 | Replace Powerline Carrier - Various Sites | 836.8 | 762.11 | -74.69 | -8.926% | Included in Original Analysis | N/A | Groupings
12421615 | 2016 | 2017 | SBH-Upgrd Telecontrol Facility | Upgrade Telecontrol Facilities - Sandy Brook Hill | 564 | 615.2495 | 51.2495 | 9.087% | Included in Original Analysis | N/A
13321601 | 2016 | 2017 | HWD/SVL-Replace Fuel Piping | Replace Fuel Piping - Hardwoods and Stephenville | 311.8 | 267.8725 | -43.9275 | -14.09% | Included in Original Analysis | N/A | -99.9% | -90%
13321691 | 2016 | 2017 | HWD&SVL GasGen EngineRefurbish | Refurbish Gas Generator Engines - Hardwoods and Stephenville | 3047.1 | 2968.2856 | -78.8144 | -2.587% | Included in Original Analysis | N/A | -89.9% | -80%
13331405 | 2014 | 2017 | Ugd D.Plt ProdDataCollectEqt | Upgrade Diesel Plant Production Data Collection Equipment-Various | 819.4 | 842.7319 | 23.3319 | 2.847% | Included in Original Analysis | N/A | -79.9% | -70%
13331603 | 2016 | 2017 | GYR-Instl Variable Freq.Drives | Install Variable Frequency Drives - Grey River | 169.9 | 257.4728 | 87.5728 | 51.54% | Included in Original Analysis | N/A | -69.9% | -60%
13461605 | 2016 | 2017 | BIF-Replace Service Bldg Roof | Replace Roof on Service Building - Bishop's Falls | 612.8 | 616.3406 | 3.5406 | 0.5778% | Included in Original Analysis | N/A | -59.9% | -50%
14011604 | 2016 | 2017 | NAN,CTW-Fire Suppression Systm | Install Fire Protection Systems - Cartwright and Nain | 4407.1 | 3652.201 | -754.899 | -17.13% | Included in Original Analysis | N/A | -49.9% | -40%
14011606 | 2016 | 2017 | Upgrade Transformers POV & CTW | Upgrade Transformer Systems - Postville and Cartwright | 465.2 | 465.1889 | -0.01112 | -0.00239% | Included in Original Analysis | N/A | -39.9% | -30%
14361601 | 2016 | 2017 | LAL-Additions for Load Growth | Additions for Load Growth - L'anse au Loup | 4175.6 | 3710.7617 | -464.8383 | -11.13% | Included in Original Analysis | N/A | -29.9% | -20%
13491603 | 2016 | 2017 | Replace Aircraft Makers-TL228 | Replace Aircraft Markers at Grand Lake Crossing - TL228 | 1567.9 | 1486.4391 | -81.4609 | -5.196% | Included in Original Analysis | N/A | -19.9% | -10%
14281692 | 2016 | 2017 | TL227 & L1 Upgrds Sally's Cove | TL 227 Distribution Line Sally's Cove L1 | 2250 | 1894.4776 | -355.5224 | -15.8% | Included in Original Analysis | N/A | -9.9% | -0.1%
13331701 | 2017 | 2017 | Overhaul Diesel Engines | Overhaul Diesel Engines - Various Sites | 2095.9 | 1619.7798 | -476.1202 | -22.72% | Included in Original Analysis | N/A | 0% | 9.9%
12961701 | 2017 | 2017 | HRD-Overhaul Turb.Valves Unt2 | Overhaul Turbine Valves Unit 2 - Holyrood | 2302.1 | 2496.5952 | 194.4952 | 8.449% | Included in Original Analysis | N/A | 10% | 19.9%
12961706 | 2017 | 2017 | Purch Capital Spares-Holyrood | Purchase Capital Spares Holyrood | 321.5 | 338.322 | 16.822 | 5.232% | Included in Original Analysis | N/A | 20% | 29.9%
12961707 | 2017 | 2017 | HRD-Cond.Asses.& Misc.Upgrds | Condition Assessment and Miscellaneous Upgrades - Holyrood | 2437.3 | 3058.1091 | 620.809 | 25.47% | Included in Original Analysis | N/A | 30% | 39.9%
12961702 | 2017 | 2017 | HRD-O/H U3 CoolWaterPump-West | HRD - Major Overhaul: Unit 3 Cooling Water Pump West | 210.8 | 196.0386 | -14.7614 | -7.003% | Included in Original Analysis | N/A | 40% | 49.9%
12961703 | 2017 | 2017 | HRD-O/H U3 ExtractPump North | HRD - Major Overhaul: Unit 3 Extraction Pump North | 142.9 | 191.3764 | 48.4764 | 33.92% | Included in Original Analysis | N/A | 50% | 59.9%
12961704 | 2017 | 2017 | HRD-O/HU2 BoilerFeedPump-West | HRD - Major Overhaul Unit 2 Boiler Feed Pump West | 279.3 | 273.901 | -5.399 | -1.933% | Included in Original Analysis | N/A | 60% | 69.9%
13251718 | 2017 | 2017 | Replace Surge Arrestors | Replace Surge Arrestors - Various Sites | 373.4 | 236.5843 | -136.8157 | -36.64% | Included in Original Analysis | N/A | 70% | 79.9%
14111702 | 2017 | 2017 | STA-Replace Fuel Tank 22E | Replace Fuel Tank 22E - St. Anthony | 199.8 | 138.973 | -60.827 | -30.44% | Included in Original Analysis | N/A | 80% | 89.9%
13251710 | 2017 | 2017 | Upgrd Off.Facil/Cntrl Bldgs | Upgrade Office Facilities & Control Buildings - Various Sites | 2197.3 | 1815.2033 | -382.0967 | -17.39% | Included in Original Analysis | N/A | 90% | 99.9%
13251711 | 2017 | 2017 | Upgrade Line Depots-Various | Line Depot Condition Assessment and Refurbishment Program - Various Sites | 1458.8 | 689.3875 | -769.4125 | -52.74% | Included in Original Analysis | N/A
13461706 | 2017 | 2017 | Install Fall Protection Equip | Install Fall Protection Equipment - Various Sites | 194.7 | 161.2649 | -33.435 | -17.17% | Included in Original Analysis | N/A
13331703 | 2017 | 2017 | VAR-Inspect Fuel Storage Tanks | Inspect Fuel Storage Tanks - Various Sites | 1058.8 | 717.2581 | -341.5419 | -32.26% | Included in Original Analysis | N/A
14011602 | 2016 | 2017 | POV-Additions for Load Growth | Additions for Load Growth - Postville - Black Tickle | 1453.8 | 881.7762 | -572.0238 | -39.35% | Included in Original Analysis | N/A
13251709 | 2017 | 2017 | GFL,BUC-Purch Backup Diesel SS | Purchase Backup Diesel For Station Service - Grand Falls and Buchans | 188.9 | 149.274 | -39.626 | -20.98% | Included in Original Analysis | N/A
20081710 | 2017 | 2017 | Replace Roof - Hydro Place | Replace Roof - Hydro Place | 923.4 | 503.5026 | -419.8974 | -45.47% | Included in Original Analysis | N/A
13501705 | 2017 | 2017 | Var-Install Demand Metering | Install Demand Metering - Various Sites | 89.7 | 73.4013 | -16.2987 | -18.17% | Included in Original Analysis | N/A
12931704 | 2017 | 2017 | BDE-PublicSafetyDams/Waterways | Upgrade Public Safety Around Dams and Waterways - Bay d'Espoir | 489 | 355.4848 | -133.5152 | -27.3% | Included in Original Analysis | N/A
12421704 | 2017 | 2017 | Rplc Network Communications Eq | Replace Network Communications Equipment - Various Sites | 199.3 | 228.6491 | 29.3491 | 14.73% | Included in Original Analysis | N/A
12421705 | 2017 | 2017 | Upgrade Site Facilities | Upgrade Site Facilities | 49 | 49.9137 | 0.9137 | 1.865% | Included in Original Analysis | N/A
13491708 | 2017 | 2017 | Perform WPLM Program | Wood Pole Line Management Program - Various Sites | 2404.1 | 3234.6081 | 830.5081 | 34.55% | Included in Original Analysis | N/A
13071701 | 2017 | 2017 | Purch Meters, Equip & Tanks | Purchase Meters and Metering Equipment - Various Sites | 198.8 | 273.866 | 75.066 | 37.76% | Included in Original Analysis | N/A
13251706 | 2017 | 2017 | Rplcmnt Due to In-Serv Failure | In-Service Failures - Various Sites | 1000 | 1437.207 | 437.207 | 43.72% | Included in Original Analysis | N/A
12421710 | 2017 | 2017 | Upgrd Access Roads-Microw Site | Upgrade Access Roads to Microwave Sites - Various Sites | 118.4 | 121.1352 | 2.7352 | 2.31% | Included in Original Analysis | N/A
12931709 | 2017 | 2017 | BDE-Rplc Floor Annunciators | Replace Floor Annunciator Panels - Bay d'Espoir | 46.8 | 45.4934 | -1.3066 | -2.792% | Included in Original Analysis | N/A
13251707 | 2017 | 2017 | Purch Capital Spares-Term Stns | Purchase Capital Spares - Terminal Stations | 495.8 | 397.8449 | -97.9551 | -19.76% | Included in Original Analysis | N/A
12901702 | 2017 | 2017 | CAT-Major OHaul.Inspection-U1 | Overhaul Turbine/Generators - Cat Arm | 305.4 | 334.111 | 28.711 | 9.401% | Included in Original Analysis | N/A
12791701 | 2017 | 2017 | Hydro Generation Tools & Equip | Purchase Tools and Equipment Less than $ 50,000 | 113.4 | 112.0489 | -1.3511 | -1.191% | Included in Original Analysis | N/A
13961703 | 2017 | 2017 | WAB-Replace Recloser | Replace Recloser - Wabush | 199.2 | 115.9747 | -83.2253 | -41.78% | Included in Original Analysis | N/A
13321703 | 2017 | 2017 | Purch Capital Spares-Gas Turb | Purchase Capital Spares - Gas Turbines | 185 | 161.2058 | -23.7942 | -12.86% | Included in Original Analysis | N/A
12981701 | 2017 | 2017 | Remove Safety Hazards-2017 | Remove Safety Hazards - Various Sites | 198.6 | 185.9109 | -12.6891 | -6.389% | Included in Original Analysis | N/A
12421707 | 2017 | 2017 | Purchase Test Equipment | Purchase Tools and Equipment less than $50,000 | 45.2 | 48.664 | 3.464 | 7.664% | Included in Original Analysis | N/A
13461711 | 2017 | 2017 | BF-Three Phase Construction | Three Phase Construction - Bishop's Falls | 49.6 | 43.2043 | -6.3957 | -12.89% | Included in Original Analysis | N/A
12851701 | 2017 | 2017 | BDE-Repl Powerhouse Lighting | Replace Powerhouse Lighting - Paradise River | 43.9 | 36.1856 | -7.7144 | -17.57% | Included in Original Analysis | N/A
12931712 | 2017 | 2017 | BDE-Repl Powerhouse#2 Lightin | Replace Powerhouse #2 Lighting - Bay d'Espoir | 48 | 46.1384 | -1.8616 | -3.878% | Included in Original Analysis | N/A
12971706 | 2017 | 2017 | Stage 1 Pumphouse Siding Repla | Stage 1 Pumphouse Siding Replacement - Holyrood | 49.9 | 51.8717 | 1.9717 | 3.951% | Included in Original Analysis | N/A
13491701 | 2017 | 2018 | Trans Line Upgrds-TL212& TL218 | Transmission Line Upgrades - TL212 and TL218 | 2511.5 | 1727.6704 | -783.8296 | -31.21% | Included in Original Analysis | N/A
12971601 | 2016 | 2018 | HRD-Powerhouse Envelope Upgrd | Upgrade Powerhouse Building Envelope - Holyrood | 6477.8 | 5640.8877 | -836.9123 | -12.92% | Included in Original Analysis | N/A
13251605 | 2016 | 2018 | Replace Disconnects 2016/2017 | Replace Disconnect Switches - Various Sites | 1967.8 | 1421.6373 | -546.1627 | -27.75% | Included in Original Analysis | N/A
13251716 | 2017 | 2018 | VAR-Repl Instrum Transformers | Replace Instrument Transformers - Various Sites | 1345.3 | 792.7631 | -552.5368 | -41.07% | Included in Original Analysis | N/A
14111703 | 2017 | 2018 | PHS-Replace Diesel Unit 2042 | Diesel Genset Replacements - Port Hope Simpson | 4374.3 | 2871.8409 | -1502.4591 | -34.35% | Included in Original Analysis | N/A
12931705 | 2017 | 2018 | Purch Capital Spares-Hydraulic | Purchase Capital Spares - Hydraulic | 487.4 | 629.5901 | 142.1902 | 29.17% | Included in Original Analysis | N/A
13251722 | 2017 | 2018 | VAR-Upgrade Power Transformers | Upgrade Power Transformers - Various Sites | 14559 | 9119.2081 | -5439.7919 | -37.36% | Included in Original Analysis | N/A
13321701 | 2017 | 2018 | SVL-Upgrd GasTurb Plt Life Ext | Gas Turbine Life Extension - Stephenville | 1353.2 | 593.922 | -759.278 | -56.11% | Included in Original Analysis | N/A
12841701 | 2017 | 2018 | USL-Inst Asset Health Mon Syst | Install Asset Health Monitoring System - Upper Salmon | 641.4 | 356.4498 | -284.9502 | -44.43% | Included in Original Analysis | N/A
13071702 | 2017 | 2018 | Purch Meter Calib Test Console | Purchase New Meter Calibration Test Console - Hydro Place | 196.9 | 209.3736 | 12.4736 | 6.335% | Included in Original Analysis | N/A
13251705 | 2017 | 2018 | OPD-Replace Power Transformers | Replace Power Transformers - Oxen Pond | 1147.6 | 648.3048 | -499.2952 | -43.51% | Included in Original Analysis | N/A
12421701 | 2017 | 2018 | Rplc Battery Banks & Chargers | Replace Battery Banks and Chargers - Various Sites (2017-2018) | 945.5 | 772.7428 | -172.7572 | -18.27% | Included in Original Analysis | N/A
12841702 | 2017 | 2018 | USL-Overhaul Main Gen Breaker | Refurbish Main Generator Breaker - Upper Salmon | 271.1 | 245.0667 | -26.0333 | -9.603% | Included in Original Analysis | N/A
13331702 | 2017 | 2018 | Auxiliary Upgrades | Diesel Plant Engine Auxiliary Upgrades - Various Sites | 1206.9 | 1126.6529 | -80.2471 | -6.649% | Included in Original Analysis | N/A
13491702 | 2017 | 2018 | Replace Insulators - TL227 | Replace Insulators - TL227 | 416.9 | 299.4214 | -117.4785 | -28.18% | Included in Original Analysis | N/A
12931708 | 2017 | 2018 | BDE-Inst Wind Mon Stn NSD SD-2 | Install Wind Monitoring Station North Salmon Dam SD-2 - Bay d'Espoir | 165.5 | 167.3131 | 1.8131 | 1.096% | Included in Original Analysis | N/A
12841601 | 2016 | 2018 | USL-Refurb Stat.Serv.WaterSyst | Refurbish Station Water System - Upper Salmon | 294.2 | 279.6762 | -14.5238 | -4.937% | Included in Original Analysis | N/A
12901701 | 2017 | 2018 | Water System Replacements | Water System Replacements - Bay d'Espoir and Cat Arm | 2553.8 | 1697.4616 | -856.3384 | -33.53% | Included in Original Analysis | N/A
13251303 | 2013 | 2018 | Rplace Instrument Transformers | Replace Instrument Transformers - Various Sites | 3668 | 3530.2062 | -137.7938 | -3.757% | Included in Original Analysis | N/A
13251714 | 2017 | 2018 | VAR-Install Frequency Monitors | Install Frequency Monitors - Various Sites | 157.8 | 126.3804 | -31.4196 | -19.91% | Included in Original Analysis | N/A
14011705 | 2017 | 2018 | CHT-Replace Diesel Unit 2034 | Diesel Genset Replacements - Charlottetown | 1432.5 | 1315.5202 | -116.9798 | -8.166% | Included in Original Analysis | N/A
13461705 | 2017 | 2018 | VAR-Install Pole Storage Ramps | Install Pole Storage Ramps - Various Sites | 816.4 | 477.7208 | -338.6791 | -41.48% | Included in Original Analysis | N/A
13251720 | 2017 | 2018 | VAR-Replace Insulators | Replace Insulators - Various Sites | 971.9 | 196.665 | -775.235 | -79.76% | Included in Original Analysis | N/A
14111701 | 2017 | 2018 | MSH-Rplc Automation Equipment | Replace Automation Equipment - Mary's Harbour | 1142 | 1047.8081 | -94.1919 | -8.248% | Included in Original Analysis | N/A
12931707 | 2017 | 2018 | BDE-Refurb Sump Lvl System PH2 | Refurbish Sump Level System for Powerhouse 2 - Bay d'Espoir | 303.2 | 230.7473 | -72.4527 | -23.9% | Included in Original Analysis | N/A
13321702 | 2017 | 2018 | HWD-Upgrd GasTurb Plt Life Ext | Gas Turbine Life Extension - Hardwoods | 956.7 | 469.2565 | -487.4435 | -50.95% | Included in Original Analysis | N/A
13251719 | 2017 | 2018 | VAR-Install Fire Protection | Install Fire Protection - Various Sites | 926.7 | 794.994 | -131.706 | -14.21% | Included in Original Analysis | N/A
12931703 | 2017 | 2018 | BDE-Upgrd Ventilation PH1&2 | Upgrade Ventilation in Powerhouse 1 and 2 - Bay d'Espoir | 997.9 | 685.6245 | -312.2755 | -31.29% | Included in Original Analysis | N/A
20081611 | 2016 | 2018 | Replace A/C Units 8 & 14-HYP | Replace Air Conditioning Units 8 and 14 - Hydro Place | 264.1 | 276.4231 | 12.3231 | 4.666% | Included in Original Analysis | N/A
13331602 | 2016 | 2018 | Replc Human Machine Interfaces | Upgrade Human Machine Interface - Various Sites | 434 | 458.0087 | 24.0087 | 5.532% | Included in Original Analysis | N/A
13251612 | 2016 | 2018 | Fire Protection-230kV TS,BDE | Install Fire Protection in 230 kV Stations - Bay d'Espoir | 766 | 592.8697 | -173.1303 | -22.6% | Included in Original Analysis | N/A
12931608 | 2016 | 2018 | BDE-UG SV Bypass Valve Unit1&2 | Replace Spherical By-Pass Valves Units 1 and 2 - Bay d'Espoir | 351.5 | 398.6093 | 47.1093 | 13.4% | Included in Original Analysis | N/A
13501703 | 2017 | 2018 | 2017/18-Distribution Upgrades | Distribution Upgrades - Various Sites | 1195.1 | 994.0176 | -201.0824 | -16.83% | Included in Original Analysis | N/A
13251723 | 2017 | 2018 | VAR-Cable Upgrades | Cable Upgrades - Various Sites | 932.1 | 664.7091 | -267.3909 | -28.69% | Included in Original Analysis | N/A
13501704 | 2017 | 2018 | BWT-Instl RecloserRemote Cntrl | Install Recloser Remote Control - Bottom Waters | 465.7 | 489.1726 | 23.4726 | 5.04% | Included in Original Analysis | N/A
13251713 | 2017 | 2018 | Replc Electromechanical Timers | Replace Electromechanical Timers - Various Sites | 197.8 | 263.2126 | 65.4126 | 33.07% | Included in Original Analysis | N/A
13491601 | 2016 | 2018 | 230kV TL266 Constr-SOP to HWDs | Construct 230 kV Transmission Line - Soldiers Pond to Hardwoods | 26560.9 | 26707.1371 | 146.2371 | 0.5506% | Included in Original Analysis | N/A
12421715 | 2017 | 2018 | MMH-Upgrd Telecontrol Facility | Upgrade Telecontrol Facilities - Mary March Hill and Blue Grass Hill | 757.1 | 623.2868 | -133.8132 | -17.67% | Included in Original Analysis | N/A
14111504 | 2015 | 2018 | Rplc Programmable Logic Cntrlr | Replace Programmable Logic Controllers - Various Sites | 958 | 1359.9236 | 401.9236 | 41.95% | Included in Original Analysis | N/A
12091701 | 2017 | 2018 | Inst AutoMeterReading-HVY | Install Automated Meter Reading - Happy Valley | 1970.2 | 1790.4916 | -179.7084 | -9.121% | Included in Original Analysis | N/A
13501603 | 2016 | 2018 | 2016/17-Distribution Upgrades | Upgrade Distribution Systems - Various Sites | 6635.9 | 6408.156 | -227.744 | -3.432% | Included in Original Analysis | N/A
12091601 | 2016 | 2018 | Inst AutoMeterReading-Lab.West | Install Automated Meter Reading - Labrador West | 967.2 | 1408.3221 | 441.1221 | 45.61% | Included in Original Analysis | N/A
13251603 | 2016 | 2018 | Replace Protection Relays-VAR | Replace Protective Relays - Various Sites | 1857 | 3314.7093 | 1457.7093 | 78.5% | Included in Original Analysis | N/A
12971703 | 2017 | 2018 | HRD-Upgrd UndrGrnd Plnt Drnage | Upgrade Underground Plant Drainage System - Holyrood | 923.1 | 1890.807 | 967.707 | 104.8% | Included in Original Analysis | N/A
13961803 | 2018 | 2018 | HVY-Additons for Load Growth | Additions for Load Growth - Happy Valley | 505 | 222.4552 | -282.5448 | -55.95% | Included in Original Analysis | N/A
13321801 | 2018 | 2018 | Purch Capital Spares-Gas Turb | Purchase Capital Spares - Gas Turbines | 626.9 | 534.6717 | -92.2283 | -14.71% | Included in Original Analysis | N/A
12981801 | 2018 | 2018 | Remove Safety Hazards-2018 | Remove Safety Hazards - Various | 199.4 | 166.3368 | -33.0632 | -16.58% | Included in Original Analysis | N/A
13461806 | 2018 | 2018 | Install Fall Protection Equip | Install Fall Protection Equipment - Various | 46.7 | 40.0556 | -6.6444 | -14.23% | Included in Original Analysis | N/A
13331801 | 2018 | 2018 | Overhaul Diesel Engines | Overhaul Diesel Units - Various Sites | 2852.4 | 2028.9873 | -823.4127 | -28.87% | Included in Original Analysis | N/A
13071801 | 2018 | 2018 | Meters and Metering Equipment | Purchase Metering and Metering Equipment - Various Sites | 198.5 | 236.6416 | 38.1416 | 19.21% | Included in Original Analysis | N/A
14011801 | 2018 | 2018 | Additions Load Growth-MAK,RIG | Additions for Load Growth - Makkovik and Rigolet | 730.1 | 301.9776 | -428.1224 | -58.64% | Included in Original Analysis | N/A
13251801 | 2018 | 2018 | Rplcmnt Due to In-Serv Failure | Terminal Station In-Service Failures | 1000 | 2268.9446 | 1268.9446 | 126.9% | Included in Original Analysis | N/A
13251802 | 2018 | 2018 | Var-Replace Surge Arrestors | Replace Surge Arrestors - Various Sites | 361.8 | 94.7661 | -267.0339 | -73.81% | Included in Original Analysis | N/A
13251803 | 2018 | 2018 | HRD-Upgrd Alum Supp Structures | Upgrade Aluminum Support Structures - Holyrood | 287.6 | 143.188 | -144.412 | -50.21% | Included in Original Analysis | N/A
13251805 | 2018 | 2018 | VAR-Upgr Equipment Foundations | Upgrade Terminal Station Equipment Foundations - Various Sites | 367 | 286.8618 | -80.1382 | -21.84% | Included in Original Analysis | N/A
12971802 | 2018 | 2018 | HRD-Install Raw Water Line | Install Raw Water Line - Holyrood | 1252.6 | 1528.5458 | 275.9458 | 22.03% | Included in Original Analysis | N/A
12961801 | 2018 | 2018 | HRD-In-Service Failures | Thermal In-Service Failures | 1250 | 2699.9082 | 1449.9082 | 116% | Included in Original Analysis | N/A
12961803 | 2018 | 2018 | HRD-Cond.Asses.& Misc.Upgrds | Condition Assessment and Miscellaneous Upgrades - Holyrood | 2749.6 | 3906.9442 | 1157.3442 | 42.09% | Included in Original Analysis | N/A
12421809 | 2018 | 2018 | Rplc TS Air Conditioner-BUC | Replace Air Conditioners - Various | 74.4 | 75.4694 | 1.0694 | 1.437% | Included in Original Analysis | N/A
13491808 | 2018 | 2018 | Perform WPLM Program | Wood Pole Line Management Program - Various Sites | 3532.9 | 3185.6229 | -347.2771 | -9.83% | Included in Original Analysis | N/A
13251806 | 2018 | 2018 | Upgrd Off.Facil/Cntrl Bldgs | Upgrade Office Facilities and Control Buildings - Various | 1180.6 | 955.8677 | -224.7323 | -19.04% | Included in Original Analysis | N/A
14111801 | 2018 | 2018 | Replc Human Machine Interfaces | Replace Human Machine Interface - St. Lewis | 280.8 | 242.5202 | -38.2798 | -13.63% | Included in Original Analysis | N/A
12421805 | 2018 | 2018 | Upgrade Site Facilities | Upgrade Site Facilities - Various | 49 | 46.8273 | -2.1727 | -4.434% | Included in Original Analysis | N/A
12421806 | 2018 | 2018 | Var-Replace Radomes | Replace Radomes - Various | 360.3 | 331.1138 | -29.1862 | -8.101% | Included in Original Analysis | N/A
12421808 | 2018 | 2018 | Upgrade RTUs | Replace RTUs - Various | 118.3 | 108.5157 | -9.7843 | -8.271% | Included in Original Analysis | N/A
12421804 | 2018 | 2018 | Rplc Network Communications Eq | Replace Network Communications Equipment - Various | 199.5 | 239.053 | 39.553 | 19.83% | Included in Original Analysis | N/A
12961802 | 2018 | 2018 | HRD-Pumps Overhaul | Overhaul Pumps - Holyrood | 438.3 | 302.6828 | -135.6172 | -30.94% | Included in Original Analysis | N/A
12961804 | 2018 | 2018 | HRD-U1 Generator Overhaul | Overhaul Unit 1 Generator - Holyrood | 1005 | 1060.5755 | 55.5755 | 5.53% | Included in Original Analysis | N/A
12961805 | 2018 | 2018 | HRD-U1 Turbine Valves O/Haul | Overhaul Unit 1 Turbine Valves - Holyrood | 2485.7 | 2247.747 | -237.953 | -9.573% | Included in Original Analysis | N/A
14011806 | 2018 | 2018 | PDR-Instl Sub-Surface Drainage | Install Sub-Surface Drainage System - Paradise River | 524.9 | 721.6131 | 196.7131 | 37.48% | Included in Original Analysis | N/A
12931803 | 2018 | 2018 | BDE-Hydraulic In-Serv Failures | Hydraulic In-Service Failures | 1251.1 | 452.4231 | -798.6769 | -63.84% | Included in Original Analysis | N/A
12931810 | 2018 | 2018 | BDE-PublicSafetyDams/Waterways | Public Safety Dams/Waterways - Bay d'Espoir | 394.7 | 344.1715 | -50.5285 | -12.8% | Included in Original Analysis | N/A
12791801 | 2018 | 2018 | Hydro Generation Tools & Equip | Hydro Generation Tools & Equip | 235.2 | 255.5992 | 20.3992 | 8.673% | Included in Original Analysis | N/A
12931815 | 2018 | 2018 | BDE-Refurbish Turbine Unit 2 | Refurbish Turbine Unit 2- BDE | 2520.7 | 1717.8404 | -802.8596 | -31.85% | Included in Original Analysis | N/A
12931816 | 2018 | 2018 | BDE-Cond.Monitoring Equipment | Condition Monitoring Equipment - BDE | 340.4 | 233.0878 | -107.3122 | -31.53% | Included in Original Analysis | N/A
13251809 | 2018 | 2018 | Upgrade Line Depots-Various | Line Depot Condition Assessment and Refurbishment - Various | 1233 | 1005.6007 | -227.3993 | -18.44% | Included in Original Analysis | N/A
12841801 | 2018 | 2018 | USL-O/Haul Turbine/Gen. Unit | Upper Salmon -Overhaul Turbine/Gen. Unit | 729.1 | 436.349 | -292.751 | -40.15% | Included in Original Analysis | N/A
12811801 | 2018 | 2018 | HLK-Replace Coolers | Replace Coolers - Hinds Lake | 516.8 | 429.8845 | -86.9155 | -16.82% | Included in Original Analysis | N/A
20081801 | 2018 | 2018 | Purchase Office Equipment-HYP | Replace Office Desk Chairs - Hydro Place | 90 | 26.2783 | -63.7217 | -70.8% | Included in Original Analysis | N/A
12931813 | 2018 | 2018 | BDE-Replace Control Cable PH1 | Replace Control Cable PH1 - BDE | 515.1 | 423.6075 | -91.4925 | -17.76% | Included in Original Analysis | N/A
12841802 | 2018 | 2018 | USL-Refurbish Accommodation | Refurbish Accommodation - USL | 74.5 | 51.4691 | -23.0309 | -30.91% | Included in Original Analysis | N/A
20081803 | 2018 | 2018 | Rplc Washroom Fixtures - HYP | Replace Washroom Fixtures - Hydro Place | 49.5 | 50.2615 | 0.76149 | 1.538% | Included in Original Analysis | N/A
12971804 | 2018 | 2018 | Stage 2 Emerg Diesel Gen Refur | Stage 2 Emergency Diesel Generator Refurbishment - Holyrood | 49.5 | 9.3213 | -40.1787 | -81.17% | Included in Original Analysis | N/A
12421807 | 2018 | 2018 | Purchase Test Equipment | Purchase Tools and Equipment less than $50,000 | 46 | 30.6813 | -15.3187 | -33.3% | Included in Original Analysis | N/A
20081804 | 2018 | 2018 | Security Improvements | Security Improvements - Hydro Place | 45.5 | 8.47 | -37.03 | -81.38% | Included in Original Analysis | N/A
12931817 | 2018 | 2018 | BDE - Penstock 3 Laser Scanning | Penstock 3 Laser Scanning - Bay d'Espoir | 46.3 | 31.3326 | -14.9674 | -32.33% | Included in Original Analysis | N/A
12931818 | 2018 | 2018 | BDE - Penstock 3 PressTransducer | Penstock 3 Press Transducer - Bay d'Espoir | 29.5 | 45.0508 | 15.5508 | 52.71% | Included in Original Analysis | N/A
20081805 | 2018 | 2018 | ParkingLot Access Imprvmts-HYP | Parking Lot Access Improvements - Hydro Place | 47.4 | 41.4768 | -5.9231 | -12.5% | Included in Original Analysis | N/A
20081806 | 2018 | 2018 | Main Breaker Replacement - HYP | Main Breaker Replacement-HYP | 18.4 | 17.5 | -0.9 | -4.891% | Included in Original Analysis | N/A
12421801 | 2018 | 2019 | Rplc PBX Telephone Systems | Replace PBX Phone Systems - Various | 1242.3 | 1379.6253 | 137.3253 | 11.05% | Included in Original Analysis | N/A
12421802 | 2018 | 2019 | Rplc MDR6000 Microwave Radios | Replace MDR 6000 Microwave Radio - Various | 1201 | 1233.0772 | 32.0772 | 2.671% | Included in Original Analysis | N/A
12421803 | 2018 | 2019 | Replace Tele-Protection TL261 | Replace Teleprotection - TL261 | 517.4 | 492.987 | -24.413 | -4.718% | Included in Original Analysis | N/A
12421810 | 2018 | 2019 | Rplc Battery Banks & Chargers | Replace Battery Banks and Chargers - Various | 937.9 | 903.1731 | -34.7269 | -3.703% | Included in Original Analysis | N/A
12931801 | 2018 | 2019 | InstlRemoteOper-SalmonR.Spillw | Install Remote Operation of Salmon Spillway - Bay d'Espoir | 2508.4 | 1818.4012 | -689.9988 | -27.51% | Included in Original Analysis | N/A
12931806 | 2018 | 2019 | Energy Efficiency Improvements | Energy Efficiency Improvements - Various Sites | 445.1 | 387.7348 | -57.3652 | -12.89% | Included in Original Analysis | N/A
12931811 | 2018 | 2019 | BDE-Instl Infrared Viewports | Install Infrared Viewports - VAR | 257.5 | 100.4698 | -157.0302 | -60.98% | Included in Original Analysis | N/A
12931814 | 2018 | 2019 | Instl Diesel Fuel Metering Dev | Install Diesel Fuel Metering Devices - BDE, PRV, VIC, GCL | 406.6 | 264.3975 | -142.2025 | -34.97% | Included in Original Analysis | N/A
12971801 | 2018 | 2019 | HRD-Upgrade Cranes and Hoists | Upgrade Cranes and Hoists - Holyrood | 380.6 | 345.1238 | -35.4762 | -9.321% | Included in Original Analysis | N/A
13251804 | 2018 | 2019 | VAR-Repl Instrum Transformers | Replace Instrument Transformers - Various Sites | 1181.1 | 670.5452 | -510.5548 | -43.23% | Included in Original Analysis | N/A
13251807 | 2018 | 2019 | Var-Upgrade Fault Recorders | Upgrade Fault Recorder System for 2018- Various Sites | 1026.9 | 636.9772 | -389.9228 | -37.97% | Included in Original Analysis | N/A
13251808 | 2018 | 2019 | Insulator Replacement -Var-M19 | Replace Insulators - Various Sites | 961.8 | 228.7218 | -733.0782 | -76.22% | Included in Original Analysis | N/A
13251811 | 2018 | 2019 | Perform Grounding Upgrades-HPD | Perform Grounding Upgrades - Various Sites | 293.8 | 373.9864 | 80.1864 | 27.29% | Included in Original Analysis | N/A
13251814 | 2018 | 2019 | Replc Disconnect Switches-M19 | Replace Disconnect Switches - Various Sites | 2458.5 | 1160.2887 | -1298.2113 | -52.81% | Included in Original Analysis | N/A
13251815 | 2018 | 2019 | Upgrade Power XFMR's (18-19) | Upgrade Power Transformers - Various Sites | 4829 | 2240.7098 | -2588.2902 | -53.6% | Included in Original Analysis | N/A
13251816 | 2018 | 2019 | Instl Fire Protection 230kV ST | Install Fire Protection in 230 kV Stations - Various Sites | 764.9 | 377.0449 | -387.8551 | -50.71% | Included in Original Analysis | N/A
13251817 | 2018 | 2019 | Rplc Transformer T1 - Buchans | Replace Transformer T1 - Buchans | 2335.1 | 2257.4354 | -77.6646 | -3.326% | Included in Original Analysis | N/A
13251820 | 2018 | 2019 | Purchase Mobile DC Power Systm | Purchase Mobile DC Power Systems | 966.5 | 658.2083 | -308.2917 | -31.9% | Included in Original Analysis | N/A
13321802 | 2018 | 2019 | HWD/SVL GT Equip Refurbishment | Gas Turbine Equipment Replacement and Refurbishment - Hardwoods and Stephenville | 1427.2 | 1197.2788 | -229.9212 | -16.11% | Included in Original Analysis | N/A
13501803 | 2018 | 2019 | 2018/19-Distribution Upgrades | Distribution System Upgrades - Various Sites | 3155 | 3219.6105 | 64.6105 | 2.048% | Included in Original Analysis | N/A
13501804 | 2018 | 2019 | EHW/BCX - RecloserRemote Cntrl | Install Recloser Remote Control - English Harbour West and Barachoix | 338.7 | 267.8528 | -70.8471 | -20.92% | Included in Original Analysis | N/A
14011807 | 2018 | 2019 | NAN-Rplc Second Contain Liner | Replace Secondary Containment System Liner - Nain | 3089.6 | 5180.7068 | 2091.1068 | 67.68% | Included in Original Analysis | N/A
20081802 | 2018 | 2019 | Upgrd Exterior Building - HYP | Upgrade Exterior of Building - Hydro Place | 665.9 | 579.2426 | -86.6574 | -13.01% | Included in Original Analysis | N/A
13401802 | 2018 | 2019 | Turbine Hot GasPath Inspection | Turbine Hot Gas Path Level 2 Inspection and Overhaul - Holyrood Gas Turbine | 11146.5 | 9829.5611 | -1316.9389 | -11.81% | Included in Original Analysis | N/A
12901601 | 2016 | 2019 | CAT-SpherValve/Def ServoMotors | Upgrade Work - Cat Arm | 1911.3 | 2570.9537 | 659.6537 | 34.51% | Included in Original Analysis | N/A
12931506 | 2015 | 2019 | BDE-Rplc PumpHouse/Equipment | Replace Pump House and Associated Equipment - Bay d'Espoir | 545.2 | 1051.0373 | 505.8373 | 92.78% | Included in Original Analysis | N/A
12931601 | 2016 | 2019 | BDE-Upgrade Site Facilities | Replace Site Facilities - Bay d'Espoir | 11981.3 | 13121.8682 | 1140.5682 | 9.52% | Included in Original Analysis | N/A
12931706 | 2017 | 2019 | BDE-Rplc Slip Rings Units 1-6 | Replace Slip Rings Units 1-6 - Bay d'Espoir | 472.3 | 301.1664 | -171.1336 | -36.23% | Included in Original Analysis | N/A
12931710 | 2017 | 2019 | Contr Structure Refurbishments | Control Structure Refurbishments | 2188.2 | 1927.5433 | -260.6567 | -11.91% | Included in Original Analysis | N/A
12931804 | 2018 | 2019 | BDE-Vent Chamber Replacement | Replace Vent Chambers - BDE | 380.7 | 199.3452 | -181.3548 | -47.64% | Included in Original Analysis | N/A
12971803 | 2018 | 2019 | HRD-Outbuilding Fire Detection | Install Fire Detection in Outbuildings - Holyrood | 198.6 | 158.5842 | -40.0158 | -20.15% | Included in Original Analysis | N/A
13251610 | 2016 | 2019 | Upgrade Data Alarm Mgmt-STB | Upgrade Data Alarm Systems - Various Sites | 308.5 | 361.4071 | 52.9071 | 17.15% | Included in Original Analysis | N/A
13251611 | 2016 | 2019 | Instl BRKR Fail Protection-TS | Install Breaker Failure Protection - Various Sites | 277 | 793.1427 | 516.1427 | 186.3% | Included in Original Analysis | N/A
13251701 | 2017 | 2019 | Replace Protective Relays-M18 | Replace Protective Relays - Various Sites | 1816.7 | 1839.3336 | 22.6336 | 1.246% | Included in Original Analysis | N/A
13251703 | 2017 | 2019 | HRD-Rplc Stn Serv Cable Feed | Replace 66 kV Station Service Feed - Holyrood | 1261.4 | 606.3337 | -655.0663 | -51.93% | Included in Original Analysis | N/A
13251704 | 2017 | 2019 | HRD-Replace Substation | Replace Substation - Holyrood | 1198 | 791.1895 | -406.8105 | -33.96% | Included in Original Analysis | N/A
13251712 | 2017 | 2019 | Instl BRKR Failure Protection | Install Breaker Failure Protection - Various Sites | 622.9 | 551.4077 | -71.4923 | -11.48% | Included in Original Analysis | N/A
13251717 | 2017 | 2019 | VAR-Replace Disconnects | Replace Disconnects - Various Sites | 3369.9 | 1188.4301 | -2181.4699 | -64.73% | Included in Original Analysis | N/A
13251721 | 2017 | 2019 | VAR-Perform Grounding Upgrades | Perform Grounding Upgrades - Various Sites | 1719.4 | 2626.3449 | 906.9449 | 52.75% | Included in Original Analysis | N/A
13461704 | 2017 | 2019 | Constr Storage Bldg MAK & CHT | Construct Storage Building - Makkovik and Charelottetown | 639.7 | 532.1648 | -107.5352 | -16.81% | Included in Original Analysis | N/A
14011802 | 2018 | 2019 | Upgd DieselPlt Ventilation-CTW | Upgrade Ventilation - Cartwright | 465.7 | 484.1515 | 18.4515 | 3.962% | Included in Original Analysis | N/A
14011805 | 2018 | 2019 | BKT-Inspect Fuel Storage Tanks | Inspect Fuel Storage Tanks - Black Tickle | 818.7 | 1044.4445 | 225.7445 | 27.57% | Included in Original Analysis | N/A
13491492 | 2014 | 2019 | 230kV TransmissionLine BDE-WAV | 230 kV Transmission Line - Bay d'Espoir to Western Avalon | 291658 | 286817.7549 | -4840.2451 | -1.66% | Included in Original Analysis | N/A
14011905 | 2019 | 2019 | Inspect Fuel Storage Tanks-GYR | Inspect Fuel Storage Tanks - Gray River | 203.1 | 317.0214 | 113.9214 | 56.09% | Included in Original Analysis | N/A
13881902 | 2019 | 2019 | Instl Pole Storage Ramps-WAB | Install Pole Storage Ramps - Wabush | 301.7 | 185.3397 | -116.3603 | -38.57% | Included in Original Analysis | N/A
13331901 | 2019 | 2019 | Overhaul Diesel Engines | Overhaul Diesel Units - Various | 2511.3 | 2154.4067 | -356.8933 | -14.21% | Included in Original Analysis | N/A
14011903 | 2019 | 2019 | Upgrd Diesel Plt Bldg-Ramea | Upgrade Diesel Plant Building - Ramea | 352.5 | 272.0043 | -80.4957 | -22.84% | Included in Original Analysis | N/A
14011906 | 2019 | 2019 | Upgrade Line Depots-Roddickton | Upgrade Line Depots - Roddickton | 344.7 | 313.4826 | -31.2174 | -9.056% | Included in Original Analysis | N/A
12981901 | 2019 | 2019 | Remove Safety Hazards-2019 | Remove Safety Hazards - Various | 197.5 | 210.8144 | 13.3144 | 6.741% | Included in Original Analysis | N/A
21881901 | 2019 | 2019 | HWD-Upgrade HMI and AVR | Upgrade HMI and AVR - Hardwoods | 685.9 | 493.8231 | -192.0769 | -28% | Included in Original Analysis | N/A
13071901 | 2019 | 2019 | Meters and Metering Equipment | Purchase Meters and Metering Equipment - Various | 196.4 | 178.181 | -18.219 | -9.276% | Included in Original Analysis | N/A
12421906 | 2019 | 2019 | Var-Replace Radomes | Replace Radomes - Various | 263.5 | 253.1481 | -10.3519 | -3.929% | Included in Original Analysis | N/A
12421903 | 2019 | 2019 | Rplc Tele-Protection TL202/206 | Replace Teleprotection - TL202 & TL206 | 196.8 | 225.7597 | 28.9597 | 14.72% | Included in Original Analysis | N/A
12421904 | 2019 | 2019 | Rplc Network Communications Eq | Replace Network Communications Equipment - Various | 189.5 | 180.4093 | -9.0907 | -4.797% | Included in Original Analysis | N/A
12421908 | 2019 | 2019 | Upgrade RTUs | Upgrade Remote Terminal Units - Various | 167.7 | 165.0186 | -2.6814 | -1.599% | Included in Original Analysis | N/A
12421905 | 2019 | 2019 | Upgrade Site Facilities | Upgrade Site Facilities - Various | 49.4 | 50.2554 | 0.85542 | 1.732% | Included in Original Analysis | N/A
12421907 | 2019 | 2019 | Purchase Test Equipment | Purchase Tools and Equipment less than $50,000 | 45.6 | 42.1151 | -3.4849 | -7.642% | Included in Original Analysis | N/A
13321902 | 2019 | 2019 | HWD/HVY-Constr Heated Storage | Construct Heated Storage for Spare Parts and Lube Oil - Hardwoods and Happy Valley | 49.8 | 61.9637 | 12.1638 | 24.43% | Included in Original Analysis | N/A
12951901 | 2019 | 2019 | GCL-Overhaul Turbine/Generator | Overhaul Turbine/Generator Unit - GCL | 562.2 | 503.6457 | -58.5543 | -10.42% | Included in Original Analysis | N/A
12791901 | 2019 | 2019 | Hydro Generation Tools & Equip | Purchase Tools and Equipment Less than $ 50,000 | 133.5 | 124.42 | -9.08 | -6.802% | Included in Original Analysis | N/A
12941901 | 2019 | 2019 | BDE-Refurbish Turbine Unit 7 | Refurbish Turbine Unit 7 - BDE | 4179 | 4282.6782 | 103.6782 | 2.481% | Included in Original Analysis | N/A
12931910 | 2019 | 2019 | BDE-Hydraulic In-Serv Failures | Hydraulic In-Service Failures | 1250 | 1374.3921 | 124.3921 | 9.951% | Included in Original Analysis | N/A
20081902 | 2019 | 2019 | Security Improvements - HYP | Security Improvements - Hydro Place | 47.1 | 28.2976 | -18.8024 | -39.92% | Included in Original Analysis | N/A
20081901 | 2019 | 2019 | Purchase Office Equipment-HYP | Purchase Office Equipment | 38 | 20.3895 | -17.6105 | -46.34% | Included in Original Analysis | N/A
12931909 | 2019 | 2019 | BDE-Upgrd SumpLevelSys PH1 | Upgrade Sump Level System Powerhouse 1 - BDE | 131.6 | 118.2189 | -13.3811 | -10.17% | Included in Original Analysis | N/A
12811903 | 2019 | 2019 | HLK-Refurbish Generator Rotor | Refurbish Generator Rotor - HLK | 1340.299 | 1544.8498 | 204.5508 | 15.26% | Included in Original Analysis | N/A
12961901 | 2019 | 2019 | HRD-Overhaul U3 Turbine Valve | Overhaul Unit 3 Turbine Valve - Holyrood | 3290.5 | 2682.9733 | -607.5267 | -18.46% | Included in Original Analysis | N/A
12961902 | 2019 | 2019 | HRD-Cond.Assessment/Misc Upgrd | Condition Assessment and Miscellaneous Upgrades - Holyrood | 1968.8 | 2941.7036 | 972.9036 | 49.42% | Included in Original Analysis | N/A
12961903 | 2019 | 2019 | HRD-Thermal In-Service Failure | Thermal In-Service Failures | 1250 | 2327.4256 | 1077.4256 | 86.19% | Included in Original Analysis | N/A
12971901 | 2019 | 2019 | HRD-Rplc 258VDC Battery Banks | Replace 258VDC Battery Banks - Holyrood | 330 | 350.6723 | 20.6723 | 6.264% | Included in Original Analysis | N/A
12681901 | 2019 | 2019 | Thermal Generation Tools&Equip | Purchase Tools and Equipment Less than $ 50,000 | 15.4 | 18.0717 | 2.6717 | 17.35% | Included in Original Analysis | N/A
12931901 | 2019 | 2019 | BDE-Upgrd Public Safety,Dams | Upgrade Public Safety Around Dams and Waterways - BDE | 678.5 | 737.4564 | 58.9564 | 8.689% | Included in Original Analysis | N/A
13501904 | 2019 | 2019 | Cond.Assess SubCable FHD-CHI | Condition Assessment for Submarine Cable - Farewell Head to Change Islands | 300.1 | 166.2941 | -133.8059 | -44.59% | Included in Original Analysis | N/A
13491908 | 2019 | 2019 | Perform WPLM Program | Wood Pole Line Management Program - Various Sites | 2467 | 2873.4173 | 406.4173 | 16.47% | Included in Original Analysis | N/A
13881901 | 2019 | 2019 | Additional Load Dist.Syst-WAB | Additions for Load - Distribution System | 186.7 | 80.9272 | -105.7728 | -56.65% | Included in Original Analysis | N/A
13251905 | 2019 | 2019 | VAR-Upgr TS Equip Foundations | Upgrade Terminal Station Equipment Foundations - Various (2019) | 306.2 | 242.3876 | -63.8124 | -20.84% | Included in Original Analysis | N/A
13251918 | 2019 | 2019 | Refurb Cntrl Building -HRD/CBC | Refurbish Control Building - HRD, CBC | 650.3 | 616.4578 | -33.8422 | -5.204% | Included in Original Analysis | N/A
13251901 | 2019 | 2019 | Terminal Stat In-Serv Failures | Terminal Station In-Service Failures | 1000 | 1744.6067 | 744.6067 | 74.46% | Included in Original Analysis | N/A
13251902 | 2019 | 2019 | Var-Replace Surge Arrestors | Replace Surge Arrestors - Various (2019) | 163.6 | 119.4258 | -44.1742 | -27% | Included in Original Analysis | N/A
13251903 | 2019 | 2019 | Var-Upgrade Cables | Upgrade Cables - Various (2019) | 500 | 297.006 | -202.994 | -40.6% | Included in Original Analysis | N/A
12971902 | 2019 | 2019 | HRD-Instl Vestibule Powerhouse | Building Vestibule Powerhouse - Holyrood | 49.3 | 37.3438 | -11.9562 | -24.25% | Included in Original Analysis | N/A
12971903 | 2019 | 2019 | HRD-Tank 3&4 Life Expect Study | Tanks 3 & 4 Life Expectancy Study - Holyrood | 48.3172 | 34.18 | -14.1372 | -29.26% | Included in Original Analysis | N/A
14101901 | 2019 | 2019 | STA-Supply/Install Waterline | Supply & Install Replacement Waterline - St. Anthony | 47.4 | 46.5735 | -0.82653 | -1.744% | Included in Original Analysis | N/A
12961904 | 2019 | 2019 | HRD-Unit 3 Electrical Testing | Unit 3 Electrical Testing - Holyrood | 39.1131 | 33.4188 | -5.6943 | -14.56% | Included in Original Analysis | N/A
13331802 | 2018 | 2020 | DieselPltEngine-CoolingSysUpgr | Diesel Plant Engine Cooling System Upgrades - Various Sites | 1310 | 1437.5344 | 127.5344 | 9.735% | Included in Original Analysis | N/A
14011803 | 2018 | 2020 | Diesel Plt Fire Protection-POV | Diesel Plant Fire Protection - Postville | 842 | 872.0761 | 30.0761 | 3.572% | Included in Original Analysis | N/A
14011804 | 2018 | 2020 | Energy Efficient Lighting-DPlt | Install Energy Efficiency Lighting in Diesel Plants - Various | 345.2 | 335.9397 | -9.2603 | -2.683% | Included in Original Analysis | N/A
13321901 | 2019 | 2020 | SVL-OHaul Olympus GasGenerator | Overhaul Olympus Gas Generator - Stephenville | 1666.8 | 1605.3137 | -61.4863 | -3.689% | Included in Original Analysis | N/A
21881902 | 2019 | 2020 | HWD-Replace Main Fuel Valves | Replace Main Fuel Valves - Hardwoods | 404.2 | 293.0207 | -111.1793 | -27.51% | Included in Original Analysis | N/A
13401901 | 2019 | 2020 | HRD GT-Upgrd CompressAirSystem | Upgrade Compressed Air System - Holyrood Gas Turbine | 388.4 | 203.315 | -185.085 | -47.65% | Included in Original Analysis | N/A
14271903 | 2019 | 2020 | Instl Reclosed RemoteCntrl-RHR | Install Recloser Remote Control (2019-2020) - Rocky Harbour | 386 | 131.4482 | -254.5518 | -65.95% | Included in Original Analysis | N/A
14011901 | 2019 | 2020 | Increase Fuel Storage - MAK | Additions for Load - Isolated Generation Systems | 2182.5 | 2578.1254 | 395.6254 | 18.13% | Included in Original Analysis | N/A
12421902 | 2019 | 2020 | Upgrd Telecontrol Facilities | Upgrade Telecontrol Facilities - Gull Pond Hill and Bay d’Espoir Hill | 673.9 | 749.3001 | 75.4001 | 11.19% | Included in Original Analysis | N/A
13501903 | 2019 | 2020 | 2019/20-Distribution Upgrades | Distribution System Upgrades - Various Sites | 5880.9 | 6245.9032 | 365.0032 | 6.207% | Included in Original Analysis | N/A
13251810 | 2018 | 2020 | Replace Protective Relays-M19 | Replace Protective Relays - Various Sites | 7535.5 | 4147.7088 | -3387.7912 | -44.96% | Included in Original Analysis | N/A
13251812 | 2018 | 2020 | Instl BRKR Failure Protection | Install Breaker Failure - Various Sites | 855.5 | 566.0153 | -289.4847 | -33.84% | Included in Original Analysis | N/A
13251819 | 2018 | 2020 | TS Flood Mitigation - SPL | Implement Terminal Station Flood Mitigation - Springdale | 974 | 673.1173 | -300.8827 | -30.89% | Included in Original Analysis | N/A
13881801 | 2018 | 2020 | Refurbish Wabush Terminal Stat | Refurbish Wabush Terminal Station | 5548.5 | 3445.6882 | -2102.8118 | -37.9% | Included in Original Analysis | N/A
13251904 | 2019 | 2020 | VAR-Repl Instrum Transformers | Replace Instrument Transformers - Various (2019-20) | 1100.1 | 877.5705 | -222.5295 | -20.23% | Included in Original Analysis | N/A
13251914 | 2019 | 2020 | Replc Disconnect Switches-M20 | Replace Disconnects - Various (2019-20) | 2350.7 | 1341.9522 | -1008.7478 | -42.91% | Included in Original Analysis | N/A
13251916 | 2019 | 2020 | Instl Fire Protect 230kVST-OPD | Install Fire Protection in 230 kV Stations - OPD (2019-20) | 883.3 | 399.6995 | -483.6004 | -54.75% | Included in Original Analysis | N/A
13251907 | 2019 | 2020 | Var-Upgrad Fault Recorders-BHL | Upgrade Fault Recorders - BHL (2019) | 623.5 | 278.1333 | -345.3667 | -55.39% | Included in Original Analysis | N/A
13251912 | 2019 | 2020 | Instl BRKRFailProtect-STB/STD | Install Breaker Failure Protection - STB, STD (2019-20) | 582.6 | 297.2845 | -285.3155 | -48.97% | Included in Original Analysis | N/A
13251908 | 2019 | 2020 | Insulator Replacement -Var-M20 | Replace Insulators - Various (2019-20) | 989 | 182.2252 | -806.7748 | -81.57% | Included in Original Analysis | N/A
13251911 | 2019 | 2020 | Perform Grounding Upgrades-M20 | Perform Grounding Upgrades - Various (2019-20) | 1845.5 | 4061.3314 | 2215.8314 | 120.1% | Included in Original Analysis | N/A
13251915 | 2019 | 2020 | Upgrade Power XFMR's (19-20) | Upgrade Power Transformers - Various (2019-20) | 9102.7 | 5761.9806 | -3340.7194 | -36.7% | Included in Original Analysis | N/A
13251906 | 2019 | 2020 | Upgrd XFMR Paralleling-WAV-M20 | Upgrade Transformer Paralleling - WAV | 301.8 | 232.6507 | -69.1493 | -22.91% | Included in Original Analysis | N/A
13251919 | 2019 | 2020 | Upgrd TS Mob.SubStation-STA | Upgrade Terminal Station for Mobile Substation - St. Anthony | 492 | 593.6632 | 101.6632 | 20.66% | Included in Original Analysis | N/A
13251813 | 2018 | 2020 | Upgrd Data Alarm ManagementM19 | Upgrade Data Alarm Management - Sunnyside | 611.4 | 572.7145 | -38.6855 | -6.327% | Included in Original Analysis | N/A
12931701 | 2017 | 2020 | BDE-Refurbish PH Station Serv | Refurbish Powerhouse Station Services - Bay d'Espoir | 4347.1 | 3951.4134 | -395.6866 | -9.102% | Included in Original Analysis | N/A
12931807 | 2018 | 2020 | Prot.Guards TurbPits BDE/USL | Install Protective Guards in Turbine Pits - BDE, USL | 541 | 245.8418 | -295.1582 | -54.56% | Included in Original Analysis | N/A
12931809 | 2018 | 2020 | Refurbish Hydraulic Structures | Refurbish Hydraulic Structures - Various | 4367.3 | 1929.5158 | -2437.7842 | -55.82% | Included in Original Analysis | N/A
12931812 | 2018 | 2020 | BDE-Rplc Int/Ext Coat SurgeTk1 | Replace Interior and Exterior Coating on Surge Tank 1 - BDE | 3564.1 | 2107.1363 | -1456.9637 | -40.88% | Included in Original Analysis | N/A
12931908 | 2019 | 2020 | BDE-Rplc Control Cable PH1 | Replace Control Cable PH1 - BDE (2019) | 415.6 | 238.7892 | -176.8108 | -42.54% | Included in Original Analysis | N/A
12931902 | 2019 | 2020 | BDE-Reburbish Hydraulic Struct | Refurbish Hydraulic Structures - BDE (2019-20) | 5036.5 | 401.279 | -4635.221 | -92.03% | Included in Original Analysis | N/A
12931904 | 2019 | 2020 | BDE-Refurbish Draft Tube Deck | Refurbish Draft Tube Deck Phase 1 - BDE | 1032.4 | 1354.8981 | 322.4981 | 31.24% | Included in Original Analysis | N/A
12931905 | 2019 | 2020 | BDE-Overhaul Unit 1 | Overhaul Unit 1 - BDE | 202 | 268.1303 | 66.1303 | 32.74% | Included in Original Analysis | N/A
12931903 | 2019 | 2020 | BDE-Rplc U 1-6 Gen.BearingSeal | Replace Units 1-6 Generator Bearing Cover Seals - BDE | 656.7 | 179.374 | -477.326 | -72.69% | Included in Original Analysis | N/A
12931906 | 2019 | 2020 | BDE-Rplc Condition Monitor Eqp | Replace Condition Monitoring Equipment - BDE (2019) | 382.7 | 314.2607 | -68.4393 | -17.88% | Included in Original Analysis | N/A
12811901 | 2019 | 2020 | HLK-Rplc T/G Cool Water Pump | Replace T/G Cooling Water Pump and Strainer - HLK | 408.5 | 448.6202 | 40.1202 | 9.821% | Included in Original Analysis | N/A
12811902 | 2019 | 2020 | HLK,PRV-Rplc Drainage Pumps | Replace Drainage Pumps - HLK, PRV | 774 | 571.0445 | -202.9555 | -26.22% | Included in Original Analysis | N/A
13332001 | 2020 | 2020 | Overhaul Diesel Units-Var | Overhaul Diesel Units - Various | 2310.915 | 1923.2427 | -387.6723 | -16.78% | Included in Original Analysis | N/A
13502006 | 2020 | 2020 | Upgrade Line Depots - BUR FOG | Upgrade Line Depots - Various | 648.3 | 724.178 | 75.878 | 11.7% | Included in Original Analysis | N/A
13072001 | 2020 | 2020 | Meters and Metering Equipment | Purchase Meters and Metering Equipment - Various | 244.214 | 180.6076 | -63.6064 | -26.05% | Included in Original Analysis | N/A
12422006 | 2020 | 2020 | Var-Replace Radomes | Replace Radomes - Various | 384.512 | 215.1132 | -169.3988 | -44.06% | Included in Original Analysis | N/A
12422008 | 2020 | 2020 | Upgrade RTUs | Upgrade Remote Terminal Units - Various | 157.054 | 156.0019 | -1.0521 | -0.6699% | Included in Original Analysis | N/A
12422010 | 2020 | 2020 | Rplc Batt Banks & Chargers-VAR | Replace Battery Banks and Chargers - Various | 195.955 | 263.6608 | 67.7058 | 34.55% | Included in Original Analysis | N/A
12422005 | 2020 | 2020 | Upgrade Site Facilities | Upgrade Site Facilities - Various | 45.522 | 46.3798 | 0.85776 | 1.884% | Included in Original Analysis | N/A
12422004 | 2020 | 2020 | Rplc Network Communications Eq | Replace Network Communications Equipment - Various | 186.797 | 193.3442 | 6.5472 | 3.505% | Included in Original Analysis | N/A
14012003 | 2020 | 2020 | Rplc Sewage Lift System-RIG | Replace Sewage Lift System - Rigolet | 127.926 | 203.1138 | 75.1878 | 58.77% | Included in Original Analysis | N/A
12932010 | 2020 | 2020 | Hydraulic In-Serv Failures | Hydraulic In-Service Failures | 1250 | 1287.2367 | 37.2367 | 2.979% | Included in Original Analysis | N/A
12922001 | 2020 | 2020 | Refurbish Access Road to Ebbeg | Refurbish Access Road to Ebbegunbaeg | 803.142 | 804.3129 | 1.1709 | 0.1458% | Included in Original Analysis | N/A
12902001 | 2020 | 2020 | Overhaul Unit 2 - Cat Arm | Overhaul Unit 2 - Cat Arm | 326.492 | 388.5783 | 62.0863 | 19.02% | Included in Original Analysis | N/A
12902004 | 2020 | 2020 | InstPartial DisMon-HLK,CAT,GCL | Install Partial Discharge Monitoring System - HLK,CAT,GCL | 451.417 | 495.6979 | 44.281 | 9.809% | Included in Original Analysis | N/A
12902003 | 2020 | 2020 | Penstock Lvl 2 Cond. As. CAT | Penstock Level 2 Condition Assessment - CAT | 261.216 | 254.6524 | -6.5636 | -2.513% | Included in Original Analysis | N/A
12932006 | 2020 | 2020 | Upgrade Bear Brook Crossing | Upgrade Bear Brook Crossing | 435.354 | 718.0934 | 282.7394 | 64.94% | Included in Original Analysis | N/A
12982001 | 2020 | 2020 | Remove Safety Hazards-2020 | Remove Safety Hazards - Various | 198.552 | 218.4151 | 19.8631 | 10% | Included in Original Analysis | N/A
12842002 | 2020 | 2020 | Instal Frazil Ice Forecas. UPS | Install Frazil Ice Forecast - UPS | 176.987 | 230.1898 | 53.2028 | 30.06% | Included in Original Analysis | N/A
12962003 | 2020 | 2020 | HRD-Thermal In-Service Failure | Thermal In-Service Failures | 2000.042 | 1836.6861 | -163.3559 | -8.168% | Included in Original Analysis | N/A
13252005 | 2020 | 2020 | Upg. Terminal St. Equip Founda | Upgrade Terminal Station Equipment Foundations - Various (2020) | 349.9 | 242.5254 | -107.3746 | -30.69% | Included in Original Analysis | N/A
13252018 | 2020 | 2020 | Upgrade Control Building - WAV | Refurbish Control Building - WAV (2020) | 333.7298 | 248.5773 | -85.1525 | -25.52% | Included in Original Analysis | N/A
13252001 | 2020 | 2020 | Terminal Stat In-Serv Failures | Terminal Station In-Service Failures | 1500.046 | 1081.0307 | -419.0153 | -27.93% | Included in Original Analysis | N/A
13252009 | 2020 | 2020 | Repl. TS Batt. Banks and Charg | Replace TS Battery Banks and Chargers - Various | 123.543 | 89.1301 | -34.4129 | -27.85% | Included in Original Analysis | N/A
13252002 | 2020 | 2020 | Replace Surge Arresters - VAR | Replace Surge Arrestors - Various (2020) | 132.28 | 102.2014 | -30.0786 | -22.74% | Included in Original Analysis | N/A
13252003 | 2020 | 2020 | Var-Upgrade Cables | Upgrade Cables - Various (2020) | 473.611 | 160.902 | -312.709 | -66.03% | Included in Original Analysis | N/A
13252011 | 2020 | 2020 | Purchase SF6 Multi Analyzer | Purchase SF6 Multi Analyzer - Various | 207.049 | 155.7007 | -51.3483 | -24.8% | Included in Original Analysis | N/A
14112001 | 2020 | 2020 | Upgrade Fuel Storage Tanks CHT | Upgrade Fuel Storage Tanks - Charlottetown | 467.169 | 310.6504 | -156.5186 | -33.5% | Included in Original Analysis | N/A
13492008 | 2020 | 2020 | Perform WPLM Program | Wood Pole Line Management Program - Various Sites | 2792.724 | 2882.6142 | 89.8902 | 3.219% | Included in Original Analysis | N/A
12932001 | 2020 | 2020 | Upgrd Public Safety,Dams | Upgrade Public Safety, Dams | 728.514 | 467.1982 | -261.3158 | -35.87% | Included in Original Analysis | N/A
20082001 | 2020 | 2020 | Purchase Office Equipment-HYP | Purchase Office Equipment | 60.9 | 6.9706 | -53.9294 | -88.55% | Included in Original Analysis | N/A
12682001 | 2020 | 2020 | Thermal Generation Tools&Equip | Purchase Tools and Equipment less than $50,000 | 15.7 | 21.5057 | 5.8057 | 36.98% | Included in Original Analysis | N/A
12422007 | 2020 | 2020 | Purchase Test Equipment | Purchase Tools and Equipment less than $50,000 | 93.4 | 46.2635 | -47.1365 | -50.47% | Included in Original Analysis | N/A
12682002 | 2020 | 2020 | HRD - Tools and Equipment 50K | Purchase Tools and Equipment less than $50,000 | 26 | 26.5213 | 0.5213 | 2.005% | Included in Original Analysis | N/A
12792001 | 2020 | 2020 | Hydro Generation Tools & Equip | Purchase Tools and Equipment Less than $ 50,000 | 21 | 36.1166 | 15.1166 | 71.98% | Included in Original Analysis | N/A
12931702 | 2017 | 2021 | BDE-U1-6 Rplc Exciter Control | Replace Exciter Controls Units 1 to 6 - Bay d'Espoir | 3347 | 2343.2927 | -1003.7073 | -29.99% | Included in Original Analysis | N/A
13251601 | 2016 | 2021 | Upgrade Circuit Breakers 16/20 | Upgrade Circuit Breakers - Various Sites | 61460.4 | 44310.9252 | -17149.4748 | -27.9% | Included in Original Analysis | N/A
14011808 | 2018 | 2021 | MAK-Diesel Genset Replacement | Diesel Genset Replacements - Makkovik | 8900.2 | 10456.444 | 1556.244 | 17.49% | Included in Original Analysis | N/A
13251913 | 2019 | 2021 | Upgrd Data Alarm System HRDM20 | Upgrade Data Alarm Systems - HRD (2019-20) | 636.8 | 789.3047 | 152.5047 | 23.95% | Included in Original Analysis | N/A
13251917 | 2019 | 2021 | Upgrd RecloseCircuit BRKRs-HRD | Upgrade Reclosing Circuit Breakers B12L65 & B2L68 - HRD | 367.6 | 171.4778 | -196.1222 | -53.35% | Included in Original Analysis | N/A
13881903 | 2019 | 2021 | Refurbish 230kV TS WAB-M20 | Refurbish 230kV TS - WAB | 4969.8 | 1989.1801 | -2980.6199 | -59.97% | Included in Original Analysis | N/A
12922002 | 2020 | 2021 | Install Remote Seepage MS-BDE | Install Remote Seepage Monitoring System - BDE | 394.7 | 1260.66 | 865.96 | 219.4% | Included in Original Analysis | N/A
12932003 | 2020 | 2021 | BDE-Refurb U 5 Gen Stator | Refurbish U5 Generatpr Stator -BDE | 5630 | 6854.3221 | 1224.3221 | 21.75% | Included in Original Analysis | N/A
14112008 | 2020 | 2021 | Diesel Genset Replace MSH | Diesel Genset Replacements - Mary's Harbour | 3900.714 | 3527.9937 | -372.7203 | -9.555% | Included in Original Analysis | N/A
14012001 | 2020 | 2021 | Diesel Plant Vent. Up. NAN | Diesel Plant Ventilation Upgrade - Nain | 853.076 | 653.1224 | -199.9536 | -23.44% | Included in Original Analysis | N/A
12942001 | 2020 | 2021 | Rplc Diesel Genset-VCS | Replace Diesel Genset-VCS | 944.028 | 1064.0392 | 120.0112 | 12.71% | Included in Original Analysis | N/A
21842002 | 2020 | 2021 | Inspect Generator Rotor - HVY | Generator Assessment - Happy Valley Gas Turbine | 1097.604 | 1221.9491 | 124.3451 | 11.33% | Included in Original Analysis | N/A
13252015 | 2020 | 2021 | Upgrade Power Transformers - V | Upgrade Power Transformers - Various (2020-21) | 1245.723 | 1228.4232 | -17.2998 | -1.389% | Included in Original Analysis | N/A
13252013 | 2020 | 2021 | Upgrade Data Alarm Systems MDR | Upgrade Data Alarm Systems - MDR (2020-21) | 326.499 | 380.4052 | 53.9062 | 16.51% | Included in Original Analysis | N/A
13252014 | 2020 | 2021 | Replace Disconnect Switches | Replace Disconnects - Various (2020-21) | 1069.847 | 1223.7236 | 153.8766 | 14.38% | Included in Original Analysis | N/A
13252016 | 2020 | 2021 | Install Fire Protec, 230kV STB | Install Fire Protection in 230 kV Stations - STB (2020-21) | 681.195 | 390.2868 | -290.9082 | -42.71% | Included in Original Analysis | N/A
13252008 | 2020 | 2021 | Replace Insulators - Various | Replace Insulators - Various (2020-21) | 243.106 | 226.6151 | -16.4909 | -6.783% | Included in Original Analysis | N/A
12962001 | 2020 | 2021 | HRD-Rewind Unit 3 Stator | Rewind Unit 3 Stator - Holyrood | 6945.6 | 7285.6551 | 340.0551 | 4.896% | Included in Original Analysis | N/A
21842001 | 2020 | 2021 | HVYGT-Replace Fire Suppression | Replace Fire Supression System - Happy Valley Gas Turbine | 2642.45 | 1923.0097 | -719.4403 | -27.23% | Included in Original Analysis | N/A
12932005 | 2020 | 2021 | Replace Control Cables BDE | Replace Control Cables BDE | 311.291 | 312.2041 | 0.9131 | 0.2933% | Included in Original Analysis | N/A
13252012 | 2020 | 2021 | Instl BRKRFailProtect-BUC/HBY | Upgrade Breaker Failure Protection (2020-2021) | 510.169 | 958.8475 | 448.6785 | 87.95% | Included in Original Analysis | N/A
13972003 | 2020 | 2021 | Additions for Load-DistMAK HPD | Additions for Load - Distribution System - Makkovik and Hopedale | 846.113 | 824.0509 | -22.0621 | -2.607% | Included in Original Analysis | N/A
13252004 | 2020 | 2021 | Repla Instr. Transformers VAR | Replace Instrument Transformers - Various (2020-21) | 339.054 | 690.3462 | 351.2922 | 103.6% | Included in Original Analysis | N/A
13502003 | 2020 | 2021 | 2020/21-Distribution Upgrades | Distribution System Upgrades (2020-2021) - Various | 3257.1 | 3485.513 | 228.413 | 7.013% | Included in Original Analysis | N/A
13252006 | 2020 | 2021 | Upgrade Station Lighting - VAR | Upgrade Station Lighting - HRD | 414.833 | 316.0256 | -98.8074 | -23.82% | Included in Original Analysis | N/A
12852001 | 2020 | 2021 | Rplc TG Cont & Vib Mon Sy PRV | Replace Turbine and Generator Control & Vibration Monitoring System - PRV | 238.571 | 277.1194 | 38.5484 | 16.16% | Included in Original Analysis | N/A
12932002 | 2020 | 2021 | Reburbish Hydraulic Struct VAR | Reburbish Hydraulic Structures VAR | 5368.415 | 5182.5133 | -185.9017 | -3.463% | Included in Original Analysis | N/A
13502091 | 2020 | 2021 | SUP-EV Charger Installation | Construction and Installation of an Electric Vehcile Fast Track Network | 259.4 | 367.7847 | 108.3847 | 41.78% | Included in Original Analysis | N/A
14112092 | 2020 | 2021 | MSH - Integrate Renewables PH2 | Integrate Renewable PH2 - Mary's Harbour | 498 | 1.4552e-14 | -498 | -100% | Included in Original Analysis | N/A
12852102 | 2021 | 2021 | Penstock Lvl 2 Cond Assess PRV | Penstock Level II Condition Assessment - PRV | 196.8 | 256.7393 | 59.9393 | 30.46% | Included in Original Analysis | N/A
12932101 | 2021 | 2021 | Upgrd Public Safety Dams BDE21 | Upgrade Public Safety Around Dams and Waterways - BDE | 436.28 | 380.6985 | -55.5815 | -12.74% | Included in Original Analysis | N/A
13252101 | 2021 | 2021 | Terminal Stat In-Serv Failures | Terminal Station In-Service Failures | 1800 | 1178.0273 | -621.9727 | -34.55% | Included in Original Analysis | N/A
13252105 | 2021 | 2021 | Upg. Terminal St. Equip Founda | Upgrade Terminal Station Equipment Foundations - Various (2021) | 175.4 | 163.5641 | -11.8359 | -6.748% | Included in Original Analysis | N/A
14012102 | 2021 | 2021 | Inspect Fuel Stg Tks - Postvil | Inspect Fuel Storage Tanks - Postville | 532.6 | 350.282 | -182.318 | -34.23% | Included in Original Analysis | N/A
13252107 | 2021 | 2021 | Upgrade Fault Recorders - Var | Upgrade Fault Recorders - Various (2021) | 346.408 | 219.5125 | -126.8955 | -36.63% | Included in Original Analysis | N/A
13072101 | 2021 | 2021 | Meters and Metering Equipment | Purchase Meters and Metering Equipment - Various | 233.4 | 228.5207 | -4.8793 | -2.091% | Included in Original Analysis | N/A
14012103 | 2021 | 2021 | Rplc Fuel Storage Tank - PR | Replace Fuel Storage Tanks - PR | 350.3 | 234.0964 | -116.2036 | -33.17% | Included in Original Analysis | N/A
13252102 | 2021 | 2021 | Replace Surge Arresters - VAR | Replace Surge Arresters - Various (2021) | 61.649 | 54.3044 | -7.3446 | -11.91% | Included in Original Analysis | N/A
13252119 | 2021 | 2021 | Pur SF6 Reclaim Units-SVL/HVY | Purchase SF6 Reclaim Units - Various | 142.722 | 142.2401 | -0.48187 | -0.3376% | Included in Original Analysis | N/A
12422104 | 2021 | 2021 | Rplc Network Communications Eq | Replace Network Communications Equipment - Various | 194 | 242.8356 | 48.8356 | 25.17% | Included in Original Analysis | N/A
12422105 | 2021 | 2021 | Upgrade Site Facilities | Upgrade Site Facilities - Various | 48.943 | 48.375 | -0.56799 | -1.161% | Included in Original Analysis | N/A
20682105 | 2021 | 2021 | Perform Minor Enhancements HYP | Perform Minor Enhancements - Hydro Place | 372.1 | 281.1013 | -90.9987 | -24.46% | Included in Original Analysis | N/A
12422110 | 2021 | 2021 | Rplc Batt Banks & Chargers-VAR | Replace Battery Banks and Chargers - Various | 327.2 | 350.4117 | 23.2117 | 7.094% | Included in Original Analysis | N/A
12982101 | 2021 | 2021 | Remove Safety Hazards-2021 | Remove Safety Hazards - Various | 199.1 | 224.7445 | 25.6445 | 12.88% | Included in Original Analysis | N/A
12682102 | 2021 | 2021 | HRD GT - Tools and Equipment | Purchase Tools and Equipment Less than $ 50,000 - HRD GT | 45.6 | 37.3845 | -8.2155 | -18.02% | Included in Original Analysis | N/A
13252103 | 2021 | 2021 | Upgrd Cables, Trenches, AC/DC | Upgrade Cables - various (2021) | 496.693 | 251.938 | -244.755 | -49.28% | Included in Original Analysis | N/A
12932102 | 2021 | 2021 | BDE - Unit 5 Gen Overhaul | Unit 5 Generator Overhaul - BDE | 220.427 | 303.222 | 82.795 | 37.56% | Included in Original Analysis | N/A
12852101 | 2021 | 2021 | PRV - Generator Overhaul | Generator Overhaul - PRV | 341.906 | 316.1892 | -25.7168 | -7.522% | Included in Original Analysis | N/A
12932110 | 2021 | 2021 | Hydraulic Generation In-Servic | Hydraulic In-Service Failures | 1250 | 2059.1178 | 809.1178 | 64.73% | Included in Original Analysis | N/A
12792101 | 2021 | 2021 | Hydro Generation Tools & Equip | Purchase Tools and Equipment Less than $ 50,000 | 194.3 | 168.8137 | -25.4863 | -13.12% | Included in Original Analysis | N/A
12932105 | 2021 | 2021 | BDE - Replace Air Conditioning | Replace Air Conditioning - BDE | 162.9 | 177.8179 | 14.9179 | 9.158% | Included in Original Analysis | N/A
20082101 | 2021 | 2021 | Purchase Office Equipment-HYP | Purchase Office Equipment | 62.264 | 20.4248 | -41.8392 | -67.2% | Included in Original Analysis | N/A
13492108 | 2021 | 2021 | Perform WPLM Program | Wood Pole Line Management Program - Various Sites | 2896.9 | 2964.946 | 68.046 | 2.349% | Included in Original Analysis | N/A
13332101 | 2021 | 2021 | Overhaul Diesel Units-Var | Overhaul Diesel Units - Various | 1232.9 | 790.3924 | -442.5076 | -35.89% | Included in Original Analysis | N/A
12422108 | 2021 | 2021 | Upgrade RTUs | Upgrade Remote Terminal Units - Various | 183.4 | 199.1898 | 15.7898 | 8.609% | Included in Original Analysis | N/A
12422106 | 2021 | 2021 | Var-Replace Radomes | Replace Radomes - Various | 240.4 | 231.9067 | -8.4933 | -3.533% | Included in Original Analysis | N/A
12972101 | 2021 | 2021 | HRD-Boiler Cond Assessmt/Upgrd | Boiler Condition Assessment/Upgrade - Holyrood | 3000 | 3889.2474 | 889.2474 | 29.64% | Included in Original Analysis | N/A
12972103 | 2021 | 2021 | HRD-Inspect Chemical Tanks | Inspect Chemical Tanks - Holyrood | 919.8 | 514.6453 | -405.1547 | -44.05% | Included in Original Analysis | N/A
12962103 | 2021 | 2021 | HRD-Thermal In-Service Failure | Thermal In-Service Failure - Holyrood | 2000 | 5807.515 | 3807.515 | 190.4% | Included in Original Analysis | N/A
12962104 | 2021 | 2021 | HRD-O/H U3 Boiler Feed Pump E | Overhaul Unit 3 Boiler Feed Pump - Holyrood | 373 | 257.7866 | -115.2134 | -30.89% | Included in Original Analysis | N/A
12962101 | 2021 | 2021 | HRD-O/H Unit 1 Turbine / Value | Overhaul Unit 1 Turbine / Valve - Holyrood | 8026.6 | 9765.0063 | 1738.4063 | 21.66% | Included in Original Analysis | N/A
20682103 | 2021 | 2021 | Core IT/OT Infrastructure | Upgrade Core IT Infrastructure - Hydro Place | 262.776 | 257.5458 | -5.2302 | -1.99% | Included in Original Analysis | N/A
20682104 | 2021 | 2021 | Refresh Security Software HYP | Refresh Cyber Security Infrastructure - Hydro Place | 217.494 | 211.2176 | -6.2764 | -2.886% | Included in Original Analysis | N/A
20682109 | 2021 | 2021 | Upgrd Hydro ECC Wall Infrastr | Upgrade Hydro ECC Wall Infrastructure - Hydro Place | 188.476 | 142.3349 | -46.1411 | -24.48% | Included in Original Analysis | N/A
12962102 | 2021 | 2021 | HRD-O/H Unit 3 Generator | Overhaul Unit 3 Generator - Holyrood | 572.7 | 610.9818 | 38.2818 | 6.684% | Included in Original Analysis | N/A
12422107 | 2021 | 2021 | Purchase Test Equipment | Purchase Tools and Equipment less than $50,000 | 40 | 34.0015 | -5.9985 | -15% | Included in Original Analysis | N/A
12682101 | 2021 | 2021 | Thermal Generation Tools&Equip | Purchase Tools and Equipment less than $50,000 | 18.8 | 7.9027 | -10.8973 | -57.96% | Included in Original Analysis | N/A
13252109 | 2021 | 2021 | Repl. TS Batt. Banks and Charg | Replace TS Battery Banks and Chargers - Various | 177.4 | 156.5489 | -20.8511 | -11.75% | Included in Original Analysis | N/A
20682108 | 2021 | 2021 | Hydro - Mobile Devices | Hydro - Mobile Devices | 48.2 | 47.1449 | -1.0551 | -2.189% | Included in Original Analysis | N/A
14011908 | 2019 | 2022 | Rplc Diesel Genset 2052 - CTW | Diesel Genset Replacements (2019-2020) | 3947.4 | 4163.9017 | 216.5017 | 5.485% | Included in Original Analysis | N/A
14012002 | 2020 | 2022 | Replace Auto. Equipment RIG | Replace Automation Equipment - Rigolet | 363.8 | 459.4468 | 95.6468 | 26.29% | Included in Original Analysis | N/A
13402002 | 2020 | 2022 | HRD GT Partial Disch. Mon. | Install Partial Discharge Monitoring - Holyrood Gas Turbine | 612.755 | 521.333 | -91.422 | -14.92% | Included in Original Analysis | N/A
13502017 | 2020 | 2022 | Install Recloser Remote Contro | Install Recloser Remote Control (2020-2021) - Hampden and Upper Salmon | 256.647 | 285.012 | 28.365 | 11.05% | Included in Original Analysis | N/A
13882003 | 2020 | 2022 | Refurbish 230kV TS WAB-M21 | Refurbish 230 kV Terminal Station Part 2 - WAB (2020-21) | 2465.576 | 1509.4403 | -956.1357 | -38.78% | Included in Original Analysis | N/A
14022001 | 2020 | 2022 | Install Fault Recorders - HVY | Install Fault Recorders - HVY (2020-21) | 687.951 | 393.8016 | -294.1494 | -42.76% | Included in Original Analysis | N/A
13882093 | 2020 | 2022 | WAB L34/L35 Protection Upgrade | Wabush L34 and L35 Protective Relays - CIAC | 259.302 | 0 | -259.302 | -100% | Included in Original Analysis | N/A
13402102 | 2021 | 2022 | Purchase Capital Spares – GT | Purchase Capital Spares - Holyrood Gas Turbine | 213.8 | 200.7921 | -13.0079 | -6.084% | Included in Original Analysis | N/A
13402101 | 2021 | 2022 | HRD GT-Const LO Cooler Hood | Construct LO Cooler Hood - Holyrood Gas Turbine | 318.8 | 562.2037 | 243.4037 | 76.35% | Included in Original Analysis | N/A
14011904 | 2019 | 2022 | Rplc Human Machine Interface | Replace Human Machine Interface - Cartwright | 306.9 | 306.491 | -0.40904 | -0.1333% | Included in Original Analysis | N/A
13962103 | 2021 | 2022 | HVY L7-Additon for Load Growth | Addition for Load Growth - Happy Valley L7 | 617.6 | 613.2703 | -4.3297 | -0.7011% | Included in Original Analysis | N/A
13462102 | 2021 | 2022 | Rplc Light Duty Mobile Equip | Replace Light Duty Mobile Equipment - Various Sites | 549.6 | 601.0809 | 51.4809 | 9.367% | Included in Original Analysis | N/A
13252115 | 2021 | 2022 | Upgrade Power Transformers - V | Upgrade Power Transformers - Various (2021-22) | 4312.318 | 3072.2791 | -1240.0389 | -28.76% | Included in Original Analysis | N/A
13252111 | 2021 | 2022 | Perform Grounding Upgrades-M22 | Perform Grounding Upgrades - Various Sites (2021-22) | 2107.3 | 1732.1113 | -375.1887 | -17.8% | Included in Original Analysis | N/A
13252110 | 2021 | 2022 | Replace Protective Relays-M22 | Replace Protective Relays - Various Sites (2021-22) | 2007 | 1765.0953 | -241.9047 | -12.05% | Included in Original Analysis | N/A
13252116 | 2021 | 2022 | Upgrs XFMR Parallel-HWD T1-T4 | Upgrades XFMR Parallel | 176.2 | 184.1815 | 7.9815 | 4.53% | Included in Original Analysis | N/A
21842103 | 2021 | 2022 | HVYGT-Upgrade Compressed Air | Upgrade Compressed Air System - Happy Valley Gas Turbine | 145.8 | 186.6058 | 40.8058 | 27.99% | Included in Original Analysis | N/A
21842101 | 2021 | 2022 | HVYGT-Replace Voltage Regulato | Replace Voltage Regulator - Happy Valley Gas Turbine | 342.3 | 283.1753 | -59.1247 | -17.27% | Included in Original Analysis | N/A
21842102 | 2021 | 2022 | Rplc Fuel Lube Glycol Pump HVY | Replace Fuel Oil, Lube Oil, and Glycol Pumps - Happy Valley Gas Turbine | 405.2 | 405.0603 | -0.13969 | -0.03447% | Included in Original Analysis | N/A
13252113 | 2021 | 2022 | Upgrade Data Alarm Mgmt. OPD | Upgrade Data Alarm Management - OPD (2021-22) | 353.309 | 561.5813 | 208.2723 | 58.95% | Included in Original Analysis | N/A
13252112 | 2021 | 2022 | Install Breaker Fail OPD DR | Install Breaker Failure Protection (2021-22) | 451.472 | 480.5956 | 29.1236 | 6.451% | Included in Original Analysis | N/A
13252114 | 2021 | 2022 | Replace Disconnect Switches | Replace Disconnect Switches - Various (2021-22) | 1292.7 | 1554.6703 | 261.9703 | 20.27% | Included in Original Analysis | N/A
13502103 | 2021 | 2022 | 2021/22-Distribution Upgrades | Upgrade of Worst-Performing Distribution Feeders (2021-2022) | 1124.5 | 1841.9017 | 717.4017 | 63.8% | Included in Original Analysis | N/A
13252106 | 2021 | 2022 | Upgrade Station Lighting - VAR | Upgrade Station Lighting - Various (2021) | 278.9 | 201.905 | -76.995 | -27.61% | Included in Original Analysis | N/A
13252104 | 2021 | 2022 | Repla Instr. Transformers VAR | Replace Instrument Transformers - Various (2021-22) | 460.9 | 729.6884 | 268.7884 | 58.32% | Included in Original Analysis | N/A
20682203 | 2022 | 2022 | Upgrade Core IT/OT Infrastruct | Upgrade Core IT/OT Infrastructure (2022) - Hydro Place | 308.2 | 308.2768 | 0.07683 | 0.02493% | Included in Original Analysis | N/A
20682204 | 2022 | 2022 | Refresh Security Software HYP | Refresh Cyber Security Infrastructure (2022) - Hydro Place | 221.7 | 333.3953 | 111.6953 | 50.38% | Included in Original Analysis | N/A
20682205 | 2022 | 2022 | Perform Minor Enhancements HYP | Perform Software Upgrades and Minor Enhancements - Hydro Place | 621.7 | 493.687 | -128.013 | -20.59% | Included in Original Analysis | N/A
12422201 | 2022 | 2022 | Replace RTUs (2022) - Various | Upgrade Remote Terminal Units (2022) - Various | 171.1 | 153.1715 | -17.9285 | -10.48% | Included in Original Analysis | N/A
12422203 | 2022 | 2022 | Upgr Site Facilities VAR 22 | Upgrade Site Facilities (2022) - Various | 49.6 | 50.3063 | 0.70634 | 1.424% | Included in Original Analysis | N/A
13332201 | 2022 | 2022 | Overhaul Diesel Units-Var | Overhaul Diesel Units (2022) - Various | 1360.5 | 1216.9338 | -143.5662 | -10.55% | Included in Original Analysis | N/A
14112202 | 2022 | 2022 | Upgr Fuel Storage Tanks MSH 22 | Upgrade Fuel Storage Tanks (2022) - Mary's Harbour | 499.1 | 622.6749 | 123.5749 | 24.76% | Included in Original Analysis | N/A
12422208 | 2022 | 2022 | Replace Mobile Devices - Hydro | Replace Mobile Devices | 49.7 | 48.8921 | -0.80786 | -1.625% | Included in Original Analysis | N/A
13252205 | 2022 | 2022 | Upgr Terminal Stn Fdn BCX/LLK | Upgrade Terminal Station Foundations - BCX/LLK | 614.5 | 552.4733 | -62.0267 | -10.09% | Included in Original Analysis | N/A
20682211 | 2022 | 2022 | STLF HYDRO 22 | Replacement of Short-Term Load Forecasting Software | 439.5 | 409.1187 | -30.3813 | -6.913% | Included in Original Analysis | N/A
13492201 | 2022 | 2022 | Wood Pole Line Management Prgm | Wood Pole Line Management Program (2022) | 1603.5 | 1986.4668 | 382.9668 | 23.88% | Included in Original Analysis | N/A
12982201 | 2022 | 2022 | Remove Safety Hazards - Var | Remove Safety Hazards (2022) - Various | 199.6 | 170.5701 | -29.0299 | -14.54% | Included in Original Analysis | N/A
12422204 | 2022 | 2022 | Rplc Batt Banks & Chargers-VAR | Replace Battery Banks and Chargers (2022) - Various | 226.6 | 192.7347 | -33.8653 | -14.94% | Included in Original Analysis | N/A
12422205 | 2022 | 2022 | Purchase Tools and Equipment | Purchase Tools and Equipment Less than $50,000 (2022) | 42 | 56.0279 | 14.0279 | 33.4% | Included in Original Analysis | N/A
12422206 | 2022 | 2022 | Var - Replace Radomes 2022 | Replace Radomes (2022) - Various | 179.9 | 124.7468 | -55.1532 | -30.66% | Included in Original Analysis | N/A
13502191 | 2021 | 2022 | Phase 2 - EV fast Charging Net | Phase 2 - EV charging Network | 1581.501 | 1844.0956 | 262.5946 | 16.6% | Included in Original Analysis | N/A
13252122 | 2021 | 2022 | Replace HTGS T2 | Replace Holyrood Thermal Generating Station T2 | 1393.157 | 2047.8321 | 654.6752 | 46.99% | Included in Original Analysis | N/A
13251910 | 2019 | 2022 | Replace Protective Relays-M20 | Replace Protective Relays - Various (2019-20) | 4579.4 | 2781.0307 | -1798.3693 | -39.27% | Included in Original Analysis | N/A
13402202 | 2022 | 2022 | Purchase Tools & Equipment -GT | Purchase Tools and Equipment Less than $50,000 (2022) - Gas Turbine | 19.6 | 20.0301 | 0.43014 | 2.195% | Included in Original Analysis | N/A
13252209 | 2022 | 2022 | Install Breaker Fail - DLK | Install Breaker Failure Protection - DLK (2022-23) | 171.216 | 59.6105 | -111.6055 | -65.18% | Included in Original Analysis | N/A
13252107 | 2021 | 2022 | Upgrade Fault Recorders - Var | Upgrade Fault Recorders - Various (2021) | 346.408 | 219.5125 | -126.8955 | -36.63% | Included in Original Analysis | N/A
13252109 | 2021 | 2022 | Repl. TS Batt. Banks and Charg | Replace TS Battery Banks and Chargers - Various | 177.4 | 156.5489 | -20.8511 | -11.75% | Included in Original Analysis | N/A
14272290 | 2022 | 2022 | Hampden New Line from TS SUPP | Hampden New Line from TS | 443.8 | 415.3142 | -28.4858 | -6.419% | Included in Original Analysis | N/A
12932204 | 2022 | 2022 | Upgrd Public Safety Dams BDE22 | Upgrade Public Safety Around Dams and Waterways - BDE | 469.5 | 587.4774 | 117.9774 | 25.13% | Included in Original Analysis | N/A
12962204 | 2022 | 2022 | Tools and Equip. <50K Therm 22 | Purchase Tools and Equipment Less than $50,000 (2022) - Thermal Plants | 18.9 | 18.5074 | -0.39263 | -2.077% | Included in Original Analysis | N/A
12962205 | 2022 | 2022 | Turbine Valve Overhaul Unit 3 | Turbine Valve Overhaul Unit 3 - Holyrood | 3623.5 | 2485.5916 | -1137.9084 | -31.4% | Included in Original Analysis | N/A
12932205 | 2022 | 2022 | Overhaul Turbine Gen - BDE | Overhaul Unit 6 - BDE | 225.4 | 564.4001 | 339.0001 | 150.4% | Included in Original Analysis | N/A
12932206 | 2022 | 2022 | Overhaul Turbine Gen - Unit 4 | Overhaul Unit 4 - BDE | 225 | 251.1359 | 26.1359 | 11.62% | Included in Original Analysis | N/A
12932209 | 2022 | 2022 | Purchase Tools & Eq. <50K | Purchase Tools and Equipment Less than $50,000 (2022) - Hydraulic Plants | 187.3 | 151.9023 | -35.3977 | -18.9% | Included in Original Analysis | N/A
20082201 | 2022 | 2022 | Tools & Equipment - Admin 2022 | Purchase Office Equipment Less Than $50,000 (2022) | 67.1 | 68.8243 | 1.7243 | 2.57% | Included in Original Analysis | N/A
12902002 | 2020 | 2022 | Refurb Sump Lvl Sys-CatArm | Refurbish Sump Level Control System - Cat Arm | 355.923 | 895.6326 | 539.7096 | 151.6% | Included in Original Analysis | N/A
12842001 | 2020 | 2022 | Rplc Sump Pump-Upper Salmon | Rplc Sump Pump-Upper Salmon | 407.153 | 396.2344 | -10.9186 | -2.682% | Included in Original Analysis | N/A
12962002 | 2020 | 2022 | Up.Uninterruptible Pow 3&4 HRD | Upgrade Uninterruptible Power Supply 3 & 4 - Holyrood | 348.7 | 512.7327 | 164.0327 | 47.04% | Included in Original Analysis | N/A
12922101 | 2021 | 2022 | Lvl 2 Condition Assessment SRS | Level II Condition Assessment - SRS | 556.808 | 481.6585 | -75.1495 | -13.5% | Included in Original Analysis | N/A
12932103 | 2021 | 2022 | BDE-Refurb U 6 Gen Stator | Refurbish Unit 6 Generator Stator - BDE | 9160.879 | 7106.4588 | -2054.4202 | -22.43% | Included in Original Analysis | N/A
12812101 | 2021 | 2022 | HLK-Rep Frazil Ice Monitor Sys | Replace Frazil Ice Monitor System - HLK | 199.5 | 336.7249 | 137.2249 | 68.78% | Included in Original Analysis | N/A
12922102 | 2021 | 2022 | Burnt Dam-Replace 60kW Diesel | Replace 60 kW Diesel Generator - Burnt Dam | 1161.7 | 383.2038 | -778.4962 | -67.01% | Included in Original Analysis | N/A
12972102 | 2021 | 2022 | HRD-Upgrd WasteWater Equal.Sys | Upgrade Waste Water Equalization System - Holyrood | 2361.1 | 2668.957 | 307.857 | 13.04% | Included in Original Analysis | N/A
12932203 | 2022 | 2022 | BDE Unit 6 Replace Control Ca | BDE Unit 6 Replace Control Cables | 304.8 | 331.6525 | 26.8525 | 8.81% | Included in Original Analysis | N/A
12972201 | 2022 | 2022 | HRD - Upgrade Wastewater Treat | Upgrade Wastewater Treatment Plant 600 V Variable Frequency Drives - Holyrood | 70.1 | 58.2025 | -11.8975 | -16.97% | Included in Original Analysis | N/A
12972202 | 2022 | 2022 | Air Receivers Condition Assess | Air Receivers Condition Assessment and Upgrades - Holyrood | 336.5 | 192.3849 | -144.1151 | -42.83% | Included in Original Analysis | N/A
12962202 | 2022 | 2022 | Major Pump Overhaul - Holyrood | Major Pumps Overhaul - Holyrood | 491.3 | 907.7166 | 416.4166 | 84.76% | Included in Original Analysis | N/A
12972203 | 2022 | 2022 | HRD-Boiler Cond Assessmt/Upgrd | Boiler Condition Assessment and Miscellaneous Upgrades - Holyrood | 3014.2 | 3899.3703 | 885.1703 | 29.37% | Included in Original Analysis | N/A
14362001 | 2020 | 2023 | Rplc Diesel Plant Roof-LAL,STA | Replace Diesel Plant Roof - LAL/STA | 2313.5555 | 1335.8991 | -977.6564 | -42.26% | Included in Original Analysis | N/A
20082002 | 2020 | 2023 | Replace Elevator Motors HYP | Replace Elevator Motors and Controls Equipment - HYP | 882.8477 | 964.652 | 81.8043 | 9.266% | Included in Original Analysis | N/A
13462105 | 2021 | 2023 | L2 Chargers for Electric Veh. | Install Level 2 Chargers for Electric Vehicles | 478.005 | 357.2934 | -120.7116 | -25.25% | Included in Original Analysis | N/A
13462001 | 2020 | 2023 | RplcLight&HvyDty Vehicles -VAR | Replace Lignt and Heavy Duty Vehicles - Various (2020) | 8848.5694 | 4055.059 | -4793.5103 | -54.17% | Included in Original Analysis | N/A
13252108 | 2021 | 2023 | Instl Fire Protect 230kVST-MDR | Install Fire Protection in 230 kV Stations - Massey Drive | 921.499 | 521.9126 | -399.5863 | -43.36% | Included in Original Analysis | N/A
12932104 | 2021 | 2023 | BDE-Replace Annunciators | BDE-Replace Annunciators | 384.9684 | 353.3838 | -31.5846 | -8.204% | Included in Original Analysis | N/A
12962105 | 2021 | 2023 | HRD-Upgrd Dist.Control System | Upgrade Distributed Control System Hardware - Holyrood | 1122.6141 | 863.5919 | -259.0222 | -23.07% | Included in Original Analysis | N/A
20082102 | 2021 | 2023 | HYP-Rplc Transfer Switches/Hrd | Replace Transfer Switches and Associated Hardware - Hydro Place | 2324.6091 | 1485.3389 | -839.2703 | -36.1% | Included in Original Analysis | N/A
13462101 | 2021 | 2023 | Rplc Vehicles&Aerial Devices | Replace Light- and Heavy-Duty Vehicles (2021-2022) | 5909.7557 | 1838.9963 | -4070.7594 | -68.88% | Included in Original Analysis | N/A
12422202 | 2022 | 2023 | Rplc Network Comms EQ 2022 | Replace Network Communications Equipment (2022) | 312.5964 | 203.258 | -109.3384 | -34.98% | Included in Original Analysis | N/A
12902201 | 2022 | 2023 | SSLR Communication Link Upgrad | SSL communication Link Upgrade - CAT | 163.1583 | 192.6158 | 29.4576 | 18.05% | Included in Original Analysis | N/A
20682206 | 2022 | 2023 | Upgr Energy MGMT System 22 | Upgrade Energy Management System (2022) - Hydro Place | 335.5683 | 446.3595 | 110.7912 | 33.02% | Included in Original Analysis | N/A
13462203 | 2022 | 2023 | Replace Light- Duty Mobile Equ | Replace Light-Duty Mobile Equipment (2022) - Various | 775.2853 | 705.4096 | -69.8757 | -9.013% | Included in Original Analysis | N/A
13462290 | 2022 | 2023 | Replace Tracks - V7271 <50k | Replace Tracks - V7271 - Supplemental | 96.62 | 45 | -51.62 | -53.43% | Included in Original Analysis | N/A
13252117 | 2021 | 2023 | Upgrade Circuit Breakers 21/22 | Upgrade Circuit Breakers (2021-2022) - Various | 12048.6929 | 8193.3203 | -3855.3726 | -32% | Included in Original Analysis | N/A
13252202 | 2022 | 2023 | Upgrade Circuit Breakers 22/23 | Upgrade Circuit Breakers (2022-2023) - Various | 8402.5238 | 5643.3502 | -2759.1737 | -32.84% | Included in Original Analysis | N/A
21842201 | 2022 | 2023 | Install Infrared Scanning Port | Install Infrared Scanning Ports - Happy Valley Gas Turbine | 87.5574 | 53.0414 | -34.516 | -39.42% | Included in Original Analysis | N/A
13402201 | 2022 | 2023 | Holyrood GT Control Systems Up | Control System Replacement - Holyrood Gas Turbine | 262.1713 | 192.3079 | -69.8634 | -26.65% | Included in Original Analysis | N/A
13252203 | 2022 | 2023 | Instll Fire Protect 230kv- BUC | Install Fire Protection in 230 kV Stations - BUC (2022-23) | 492.8023 | 390.8944 | -101.9079 | -20.68% | Included in Original Analysis | N/A
13252204 | 2022 | 2023 | Replace Protective Relays-M23 | Replace Protective Relays - Various (2022-23) | 2253.2078 | 1407.7079 | -845.4999 | -37.52% | Included in Original Analysis | N/A
12962203 | 2022 | 2023 | Unit 3 Gen. Comp Cond Asst | Unit 3 Generator Components Condition Assessment and Miscellaneous Upgrades | 422.0236 | 544.6956 | 122.672 | 29.07% | Included in Original Analysis | N/A
13502203 | 2022 | 2023 | Upgrade Distribution Feeders | Upgrade of Worst-Performing Distribution Feeders (2022-2023) | 2761.098 | 3052.5192 | 291.4212 | 10.55% | Included in Original Analysis | N/A
12922201 | 2022 | 2023 | Refurb Hydlic Struct Burnt Dam | Refurbish Hydraulic Structures - Burnt Dam (2022-23) | 3756.277 | 3003.7782 | -752.4988 | -20.03% | Included in Original Analysis | N/A
13252206 | 2022 | 2023 | Repl TS Batt Banks/Chargers22 | Replace TS Battery Banks and Chargers - EHW, HWD, SDP, SHE, SOK | 315.2393 | 369.0905 | 53.8512 | 17.08% | Included in Original Analysis | N/A
12932207 | 2022 | 2023 | Replace Generator Bearing Seal | Replace Units 1-6 Generator Bearing Cover Seals - BDE | 296.4675 | 149.2869 | -147.1806 | -49.64% | Included in Original Analysis | N/A
12902202 | 2022 | 2023 | Replace Surface Air Coolers | Replace Surface Air Coolers for Both Units - CAT | 869.0732 | 583.5549 | -285.5183 | -32.85% | Included in Original Analysis | N/A
13252207 | 2022 | 2023 | Upgrade Power Transformers-22 | Upgrade Power Transformers - Various (2022-23) | 3758.9072 | 2642.7505 | -1116.1567 | -29.69% | Included in Original Analysis | N/A
12842201 | 2022 | 2023 | Replace Rotary Strainer - USL | Replace Rotary Strainer - USL | 239.9966 | 238.4998 | -1.4968 | -0.6237% | Included in Original Analysis | N/A
12932210 | 2022 | 2023 | Replace Monorail Beams | Replace Monorail Beams & Associated Mounts SRS - BDE | 592.8804 | 874.5932 | 281.7129 | 47.52% | Included in Original Analysis | N/A
13502202 | 2022 | 2023 | Install Recloser Remote Contro | Install Recloser Remote Control (2021-2022) - Various | 360.4826 | 213.7629 | -146.7196 | -40.7% | Included in Original Analysis | N/A
13252209 | 2022 | 2023 | Install Breaker Fail - DLK | Install Breaker Failure Protection - DLK (2022-23) | 171.2 | 59.6105 | -111.5895 | -65.18% | Included in Original Analysis | N/A
13252208 | 2022 | 2023 | Replace Disconnects - Various | Replace Disconnect Switches - Various (2022-23) | 1235.7013 | 1002.3861 | -233.3152 | -18.88% | Included in Original Analysis | N/A
13252211 | 2022 | 2023 | Upgrade Reclosing Circuit Brea | Upgrade Reclosing Circuit Breakers - SSD B1L03 & HRD B1L65 (2022-23) | 210.9698 | 231.818 | 20.8483 | 9.882% | Included in Original Analysis | N/A
13252210 | 2022 | 2023 | Replace Station Lighting - BUC | Upgrade Station Lighting - BUCTS and HWDTS (2022-23) | 202.6364 | 314.9315 | 112.2951 | 55.42% | Included in Original Analysis | N/A
13252212 | 2022 | 2023 | Replace Instrument Transformer | Replace Instrument Transformers - Various (2022-23) | 402.3595 | 487.9087 | 85.5492 | 21.26% | Included in Original Analysis | N/A
14012290 | 2022 | 2023 | Rplc Diesel Plant RF MAK SUPP | Makkovik Diesel Generating Station Roof Replacement - Supplemental | 891.6241 | 733.8948 | -157.7293 | -17.69% | Included in Original Analysis | N/A
12962291 | 2022 | 2023 | Lt Stage Blades Holyrood Supp | Purchase Turbine Last Stage Blades - Holyrood - Supplemental | 1432.6215 | 1595.5372 | 162.9157 | 11.37% | Included in Original Analysis | N/A
12842290 | 2022 | 2023 | USL Rotor Rim Shrinking (Supp) | Upper Salmon Hydroelectric Generating Station Rotor Rim Shrink and Stator Recentering - Supplemental | 4236.3289 | 9146.6379 | 4910.3091 | 115.9% | Included in Original Analysis | N/A
12972290 | 2022 | 2023 | HRD SUPP Rpl Tank Farm Undgrd | Holyrood Tank Farm Underground Firewater System Replacment - Supplemental | 1469.6289 | 1262.9116 | -206.7173 | -14.07% | Included in Original Analysis | N/A
12972292 | 2022 | 2023 | HRD SUPP Day Tank Refurb | Holyrood Inspect and Refurbish Day Tank - Supplemental | 846.7719 | 942.1432 | 95.3712 | 11.26% | Included in Original Analysis | N/A
12422309 | 2023 | 2023 | Rplc standalone PHX phone sys | Replace Standalone PBX Phone Systems (2023) | 175.5 | 208.9658 | 33.4658 | 19.07% | Included in Original Analysis | N/A
12422305 | 2023 | 2023 | Purchase Tools and Equipment | Purchase Tools and Equipment Less than $50,000 (2023) - Telecontrol | 40.4 | 47.4011 | 7.0011 | 17.33% | Included in Original Analysis | N/A
12422303 | 2023 | 2023 | Upgr Site Facilities VAR 23 | Upgrade Site Facilities (2023) | 45.2 | 47.1129 | 1.9129 | 4.232% | Included in Original Analysis | N/A
12422308 | 2023 | 2023 | Purchase Mobile Devices Hydro | Purchase Mobile Devices (2023) | 83.4 | 116.3509 | 32.9509 | 39.51% | Included in Original Analysis | N/A
20682305 | 2023 | 2023 | Prfm soft upgrs/minor echan 23 | Perform Software Upgrades and Minor Enhancements (2023) | 451.2 | 357.3164 | -93.8836 | -20.81% | Included in Original Analysis | N/A
20682303 | 2023 | 2023 | Upgrade Core IT/OT Infrastruct | Upgrade Core OT Infrastructure (2023) | 171.7 | 255.2619 | 83.5619 | 48.67% | Included in Original Analysis | N/A
20682304 | 2023 | 2023 | Upde Cyber Security Software23 | Update Cyber Security Infrastructure (2023) | 232.1 | 230.5331 | -1.5669 | -0.6751% | Included in Original Analysis | N/A
12962302 | 2023 | 2023 | Overhaul Pumps Holyrood 23 | Overhaul Pumps (2023) - Holyrood | 742.4 | 1429.8882 | 687.4882 | 92.6% | Included in Original Analysis | N/A
12962303 | 2023 | 2023 | Tools and Equip. Thermal 23 | Purchase Tools and Equipment Less than $50,000 (2023) - Thermal Plants | 55.1 | 122.782 | 67.682 | 122.8% | Included in Original Analysis | N/A
13332301 | 2023 | 2023 | Diesel In-Service Failures 23 | Diesel In-Service Failures (2023) | 480.4 | 727.1768 | 246.7768 | 51.37% | Included in Original Analysis | N/A
12972301 | 2023 | 2023 | HRD-Boiler Cond Assessmt/Upgrd | Boiler Condition Assessment and Miscellaneous Upgrades (2023) - Holyrood | 2926.6 | 4336.3612 | 1409.7612 | 48.17% | Included in Original Analysis | N/A
12962305 | 2023 | 2023 | Refurb Workshop Roof - HRD | Refurbish Workshop Roof (2023) - Holyrood | 243.7 | 237.7527 | -5.9473 | -2.44% | Included in Original Analysis | N/A
12422301 | 2023 | 2023 | Replace RTUs (2023) - Various | Replace Remote Terminal Units (2023) | 179.7 | 234.4336 | 54.7336 | 30.46% | Included in Original Analysis | N/A
13402301 | 2023 | 2023 | Purchase Tools & Equipment -GT | Purchase Tools and Equipment Less than $50,000 (2023) - Gas Turbine | 18.3 | 16.6577 | -1.6423 | -8.974% | Included in Original Analysis | N/A
21882301 | 2023 | 2023 | Gas Turbine In-Service Failure | Gas Turbine In-Service Failures (2023) | 344.2 | 3606.7459 | 3262.5459 | 947.9% | Included in Original Analysis | N/A
13252301 | 2023 | 2023 | Terminal Stat In-Serv Failures | Terminal Station In-Service Failures (2023) | 1300 | 2846.6948 | 1546.6948 | 119% | Included in Original Analysis | N/A
12982301 | 2023 | 2023 | Remove Safety Hazards - Var | Remove Safety Hazards (2023) | 198.2 | 207.0342 | 8.8342 | 4.457% | Included in Original Analysis | N/A
12932301 | 2023 | 2023 | Hydraulic In-Serv Failures 23 | Hydraulic In-Service Failures (2023) | 1500 | 4081.0911 | 2581.0911 | 172.1% | Included in Original Analysis | N/A
12932303 | 2023 | 2023 | Upgr Public Safety Dams BDE 23 | Upgrade Public Safety Around Dams and Waterways (2023) | 482.1 | 795.4595 | 313.3595 | 65% | Included in Original Analysis | N/A
12962301 | 2023 | 2023 | Thermal In-Service Failures 23 | Thermal In-Service Failures (2023) | 3300 | 2887.8278 | -412.1722 | -12.49% | Included in Original Analysis | N/A
12422302 | 2023 | 2023 | Rplc Network Comms EQ 2023 | Replace Network Communications Equipment (2023) | 189 | 238.6899 | 49.6899 | 26.29% | Included in Original Analysis | N/A
12972303 | 2023 | 2023 | Upgr Bio-Green Sewage HRD | Refurbish BioGreen Sewage System (2023) - Holyrood | 256.6 | 504.9448 | 248.3448 | 96.78% | Included in Original Analysis | N/A
14012302 | 2023 | 2023 | SBN-Dsl Genset Rplc Unit 2056 | Diesel Genset Replacement Program (2023-2025) | 543 | 474.6987 | -68.3013 | -12.58% | Included in Original Analysis | N/A
12922301 | 2023 | 2023 | SRS - Replace Emergency Lift | Replace Emergency Lift (2023) - Salmon River Spillway | 49.8 | 90.7418 | 40.9418 | 82.21% | Included in Original Analysis | N/A
20082301 | 2023 | 2023 | Purchase office equipment <50k | Purchase Office Equipment Less Than $50,000 (2023) | 75.6 | 55.6933 | -19.9067 | -26.33% | Included in Original Analysis | N/A
12932305 | 2023 | 2023 | Pur Tools & Eq. <50K Hydraulic | Purchase Tools and Equipment Less than $50,000 (2023) - Hydraulic Plants | 144.9 | 149.9791 | 5.0791 | 3.505% | Included in Original Analysis | N/A
13072301 | 2023 | 2023 | Meters and Metering Equipment | Purchase Meters and Metering Equipment (2023) | 226.6 | 202.9578 | -23.6422 | -10.43% | Included in Original Analysis | N/A
12422306 | 2023 | 2023 | Rplc Batt Banks & Chargers-VAR | Replace 48 V Battery Banks and Chargers (2023) | 439.7 | 418.9626 | -20.7374 | -4.716% | Included in Original Analysis | N/A
13332302 | 2023 | 2023 | Overhaul Diesel Units-Var | Overhaul Diesel Units (2023) | 1502 | 1347.2625 | -154.7375 | -10.3% | Included in Original Analysis | N/A
12942302 | 2023 | 2023 | BDE unit 7 lvl 2 cond asst | Unit 7 Condition Assessment (2023) - Bay d'Espoir | 597.5 | 379.4053 | -218.0947 | -36.5% | Included in Original Analysis | N/A
12902301 | 2023 | 2023 | Hydraulic Unit 1&3 Overhaul | Hydraulic Unit Overhauls Program (2023) | 975.7 | 1289.4118 | 313.7118 | 32.15% | Included in Original Analysis | N/A
13492301 | 2023 | 2023 | Wood Pole Line Management Prgm | Wood Pole Line Management Program (2023) | 2824.4 | 5085.8377 | 2261.4377 | 80.07% | Included in Original Analysis | N/A
13492302 | 2023 | 2023 | Transmission Inservice Failure | Transmission In-Service Failures (2023) | 151.7 | 193.5891 | 41.8891 | 27.61% | Included in Original Analysis | N/A
12812102 | 2021 | 2024 | HLK-Annunciator Replacement | HLK-Annunciator Replacement | 371.1331 | 483.6696 | 112.5365 | 30.32% | Included in Original Analysis | N/A
13402001 | 2020 | 2024 | HRD GT-Combustor Inpection | Perform Combustor Inspection - Holyrood Gas Turbine | 5473.5432 | 5120.9907 | -352.5525 | -6.441% | Included in Original Analysis | N/A
14112203 | 2022 | 2024 | Diesel Genset Rplc Unit STL | Diesel Genset Replacement Unit 2039 - St. Lewis | 1980.8 | 1580.0628 | -400.7372 | -20.23% | Included in Original Analysis | N/A
13332202 | 2022 | 2024 | Instll Fire Prtct Diesel RAM | Install Fire Protection in Diesel Plants (2022-2023) - Ramea | 1928.8 | 1515.6301 | -413.1699 | -21.42% | Included in Original Analysis | N/A
13962203 | 2022 | 2024 | Lab City L22Voltage Conversion | Labrador City L22 Voltage Conversion (2022-2023) | 1491.2 | 2175.6355 | 684.4355 | 45.9% | Included in Original Analysis | N/A
13462201 | 2022 | 2024 | Purchase 46 ft Category B | Purchase 46' Material Handler Aerial Device on Track Unit | 758 | 740.9146 | -17.0854 | -2.254% | Included in Original Analysis | N/A
13462202 | 2022 | 2024 | Purchase 85' Material Handler | Purchase 85' Material Handler Aerial Device on Track Unit | 1353.9 | 1201.724 | -152.176 | -11.24% | Included in Original Analysis | N/A
14012303 | 2023 | 2024 | Replace Building Ext Postville | Replace Building Exterior (2023-2024) - Postville | 683.3 | 1200.8386 | 517.5386 | 75.74% | Included in Original Analysis | N/A
13882301 | 2023 | 2024 | Cond asst Condensers 1&2 WABTS | Major Condition Assessment and Miscellaneous Refurbishments Synchronous Condenser 1 and 2 (2023-2024) - Wabush Terminal Station | 1093.3 | 1049.263 | -44.037 | -4.028% | Included in Original Analysis | N/A
13462305 | 2023 | 2024 | Replace HVAC Unit BIF | Replace HVAC System (2023-2024) - Bishop's Falls | 172.2 | 274.4595 | 102.2594 | 59.38% | Included in Original Analysis | N/A
14012390 | 2023 | 2024 | CHT/MSH rplc unit 2090/2044 | Replace Unit 2090/2044 - Charlottetown and Mary's Harbour | 401.022 | 492.5594 | 91.5374 | 22.83% | Included in Original Analysis | N/A
12962390 | 2023 | 2024 | Pur/RplcLT Blades Unit 1&2 SUP | Holyrood Thermal Generating Station Unit 1 and Unit 2 Turbine Last Stage Blades - Supplemental | 6408.7 | 6673.0654 | 264.3654 | 4.125% | Included in Original Analysis | N/A
12962292 | 2022 | 2024 | Upgrd Tur Ctrl Sys Unit 2 SUPP | Holyrood Upgrade Turbine Control System Unit 2 - Supplemental | 726 | 752.1551 | 26.1551 | 3.603% | Included in Original Analysis | N/A
12422304 | 2023 | 2024 | Rplc Pwr Ln Carrier (2023-24) | Replace Power Line Carrier (2023–2024) - TL223 and TL224 | 957.7 | 879.4252 | -78.2748 | -8.173% | Included in Original Analysis | N/A
21842301 | 2023 | 2024 | Rpl Human Machine Inter 2023 | Replace Human Machine Interface (2023) - Happy Valley Gas Turbine | 138.6 | 166.2288 | 27.6288 | 19.93% | Included in Original Analysis | N/A
21842302 | 2023 | 2024 | Rpl Oil Mist Seperator 23/24 | Replace Oil Mist Separator (2023-2024) - Happy Valley Gas Turbine | 400.6 | 179.0169 | -221.5831 | -55.31% | Included in Original Analysis | N/A
13252302 | 2023 | 2024 | Instll Fire Protect 230kv- DLK | Install Fire Protection in 230 kV Stations (2023-2024) - Deer Lake | 614.5 | 534.4027 | -80.0973 | -13.03% | Included in Original Analysis | N/A
13252305 | 2023 | 2024 | InstallCAT T1S oil spill cont | Install Oil Spill Containment Transformer T1S (2023-2024) - Cat Arm | 581.6 | 873.8137 | 292.2137 | 50.24% | Included in Original Analysis | N/A
13462403 | 2024 | 2024 | Replace Grader V9829 BDE | Replace Grader Unit V9829 (2024) - Bay d'Espoir | 836.7 | 872.9393 | 36.2393 | 4.331% | Included in Original Analysis | N/A
12422410 | 2024 | 2024 | Install Anemometer Cat Arm 24 | Install Anemometer (2024) - Cat Arm | 68.6 | 100.7424 | 32.1424 | 46.85% | Included in Original Analysis | N/A
12972403 | 2024 | 2024 | HRD Marine Term Arm 24 | Overhaul Marine Terminal Loading Arms (2024) - Holyrood | 511 | 468.3003 | -42.6997 | -8.356% | Included in Original Analysis | N/A
12422420 | 2024 | 2024 | Replace CCTV System 24 | Replace CCTV Cameras (2024) | 317.6 | 369.7161 | 52.1161 | 16.41% | Included in Original Analysis | N/A
12422421 | 2024 | 2024 | Replace SONET Multiplexers 24 | Replace SONET Multiplexors (2024) | 430.4 | 398.6951 | -31.7049 | -7.366% | Included in Original Analysis | N/A
12922402 | 2024 | 2024 | Rpl Timber Crib 24 Burnt Dam | Replace Timber Crib and Insulation (2024) - Burnt Dam Spillway | 161.8 | 100.0608 | -61.7392 | -38.16% | Included in Original Analysis | N/A
12962406 | 2024 | 2024 | Refurb Fuel Oil Store 4 HRD | Refurbish Fuel Oil Storage Tank 4 (2024) - Holyrood | 1920 | 2150.8605 | 230.8605 | 12.02% | Included in Original Analysis | N/A
20082401 | 2024 | 2024 | Lvl 2 EV Chargers - HYP 24 | Upgrade Fleet Infrastructure Program - Install L2 EV Chargers (2024) - Hydro Place | 322.635 | 143.5823 | -179.0527 | -55.5% | Included in Original Analysis | N/A
12842401 | 2024 | 2024 | Penstock lvl2 Cond asst 24 USL | Penstock Level II Condition Assessment (2024) - Upper Salmon | 382.8 | 149.2214 | -233.5787 | -61.02% | Included in Original Analysis | N/A
12952401 | 2024 | 2024 | GCL-Overhaul Hydraulic units24 | Overhaul Hydraulic Units (2024) | 323.8 | 376.8143 | 53.0143 | 16.37% | Included in Original Analysis | N/A
13252010 | 2020 | 2024 | Replace Transformer T7 - HRD | Replace Transformer T7 - HRD | 2678.14 | 4701.0658 | 2022.9258 | 75.53% | Included in Original Analysis | N/A
13882202 | 2022 | 2024 | IOC SCADA Data Link | IOC SCADA Data Link | 28.218 | 28.8798 | 0.66184 | 2.345% | Included in Original Analysis | N/A
13252022 | 2020 | 2024 | Valentine Gold Interconnection | Valentine Gold Interconnection - Supplemental | 16347.4 | 16148.7257 | -198.6743 | -1.215% | Included in Original Analysis | N/A
12972204 | 2022 | 2024 | Replace Underground Fire Water | Replace Underground Fire Water Distribution System - Holyrood | 1706.3 | 3080.4524 | 1374.1524 | 80.53% | Included in Original Analysis | N/A
12842301 | 2023 | 2024 | Rpl PHstation srvice panel USL | Replace Powerhouse Station Service Panel (2023-2024) - Upper Salmon | 1568.5 | 2526.6794 | 958.1794 | 61.09% | Included in Original Analysis | N/A
14112290 | 2022 | 2024 | CHT Winterize Unit 2102 SUPP | CHT Winterize Unit 2102 and Install Mobile - Supplemental | 1314.7 | 1786.7325 | 472.0325 | 35.9% | Included in Original Analysis | N/A
13492490 | 2024 | 2024 | TL201 Dyn line rating sys<750k | Install Line Monitoring System (2024) - TL201 | 469.902 | 455.1293 | -14.7727 | -3.144% | Included in Original Analysis | N/A
20082404 | 2024 | 2024 | Upgr HVAC Network Eng/Con HYP | Upgrade HVAC Supervisory Controllers (2024) - Hydro Place | 149.6 | 136.9756 | -12.6244 | -8.439% | Included in Original Analysis | N/A
12962490 | 2024 | 2024 | Instl L1 Blade Unit 1 Turb HRD | Install L-1 Blades Unit 1 (2024) Holyrood | 581.263 | 512.496 | -68.767 | -11.83% | Included in Original Analysis | N/A
14282490 | 2024 | 2024 | TL226,TL239,TL259 WIDEN ROW | Widen Rights-of-Way of Transmission Lines TL239 & TL259 (2024) | 668.914 | 624.2195 | -44.6945 | -6.682% | Included in Original Analysis | N/A
12812401 | 2024 | 2025 | Flatten Downstream Slope 24/25 | Flatten Downstream Slope (2024-2025) - Hinds Lake | 3229.5 | 1821.7461 | -1407.7539 | -43.59% | Included in Original Analysis | N/A
12842501 | 2025 | 2025 | Inst Power Canal SBoom 25 USL | Install Power Canal Public Safety Boom (2025) - Upper Salmon | 463.8 | 268.6314 | -195.1686 | -42.08% | Included in Original Analysis | N/A
13252412 | 2024 | 2025 | Upgr Reclosing CBreakers TL247 | Replace Circuit Breaker Reclosing Controllers (2024–2025) - TL247 | 328.2 | 238.2979 | -89.9021 | -27.39% | Included in Original Analysis | N/A
20082403 | 2024 | 2025 | General Prop Rehab HYP | General Property Rehabilitation (2024) - Hydro Place | 234 | 401.482 | 167.482 | 71.57% | Included in Original Analysis | N/A
13252407 | 2024 | 2025 | Install Proct 230KV Voisey's | Install Fire Protection in 230 kV Stations (2024–2025) - Voisey's Bay | 652.8 | 504.362 | -148.438 | -22.74% | Included in Original Analysis | N/A
12422504 | 2025 | 2025 | Replace CCTV Cameras 25 | Install CCTV Systems (2025) | 440.1 | 353.6907 | -86.4093 | -19.63% | Included in Original Analysis | N/A
12902502 | 2025 | 2025 | Lvl2 Cond Asst Phouse 25 CAT | Perform Level 2 Condition Assessment - Powerhouse Slope (2025) - Cat Arm | 169.4 | 138.1864 | -31.2137 | -18.43% | Included in Original Analysis | N/A
18192501 | 2025 | 2025 | Pur Surveying soft/equip 25 | Purchase Surveying Software and Equipment (2025) | 316.4 | 286.6651 | -29.7349 | -9.398% | Included in Original Analysis | N/A
12422412 | 2024 | 2025 | Rpl MDR8000 Microwave Radios | Replace MDR8000 Microwave Radios (2024-2025) | 1453.8 | 1424.1702 | -29.6298 | -2.038% | Included in Original Analysis | N/A
13402502 | 2025 | 2025 | Inps Fuel Tanks 25 HRD | Inspect Fuel Tanks (2025) - Holyrood | 608 | 575.507 | -32.493 | -5.344% | Included in Original Analysis | N/A
12932406 | 2024 | 2025 | Rpl PWhouse Air Con BDE 24/25 | Replace Powerhouse 1 Air Conditioning Unit (2024-2025) - Bay d'Espoir | 289 | 291.0157 | 2.0157 | 0.6975% | Included in Original Analysis | N/A
12932404 | 2024 | 2025 | Refurb Intake Gate 1 24/25 BDE | Refurbish Intake 1 (2024-2025) - Bay d'Espoir | 3344 | 3418.668 | 74.668 | 2.233% | Included in Original Analysis | N/A
13252312 | 2023 | 2025 | Upg Station Lighting Var 23/24 | Replace Terminal Station Lighting (2023-2024) | 917.4 | 1432.1492 | 514.7492 | 56.11% | Included in Original Analysis | N/A
12972501 | 2025 | 2025 | LV2 Cond asst Stage 1&2 WSump | Perform Level 2 Condition Assessment - Stage I & II Cooling Water Sump Structures (2025) - Holyrood | 1747.033 | 1838.5639 | 91.5309 | 5.239% | Included in Original Analysis | N/A
12422507 | 2025 | 2025 | Refurb Meterological STN 25 | Refurbish Meteorological Stations (2025) | 167.8 | 179.8792 | 12.0792 | 7.199% | Included in Original Analysis | N/A
14012304 | 2023 | 2025 | Upgrade Fuel Storage Nain | Replace Intermediate Fuel Storage Tanks (2023-2024) - Nain | 721.1 | 1313.8397 | 592.7397 | 82.2% | Included in Original Analysis | N/A
12932304 | 2023 | 2025 | BDE Water Sys Assessment/Upgr | Water System Condition Assessment and Upgrades (2023) - Bay d'Espoir | 665.9 | 1387.0284 | 721.1284 | 108.3% | Included in Original Analysis | N/A
12972404 | 2024 | 2025 | Refurb Outbuilding&Powerhouse | Refurbish Outbuilding and Powerhouse Building Envelopes (2024-2025) - Holyrood | 1195.6 | 1292.9245 | 97.3245 | 8.14% | Included in Original Analysis | N/A
13402402 | 2024 | 2025 | Constr Main Platform 24/25 GT | Construct Maintenance Platform (2024-2025) - Holyrood Gas Turbine | 359.2 | 404.9963 | 45.7963 | 12.75% | Included in Original Analysis | N/A
12972401 | 2024 | 2025 | Upgr UPS 1&2 HRD 24/25 | Upgrade UPS 1 & 2 (2024-2025) - Holyrood | 370.6 | 423.0747 | 52.4747 | 14.16% | Included in Original Analysis | N/A
12932201 | 2022 | 2025 | BDE- TUBE SUB LVL1-2 COND ASST | Draft Tube Deck Substructure Level 2 Condition Assessment | 343.6 | 984.9386 | 641.3386 | 186.7% | Included in Original Analysis | N/A
12902401 | 2024 | 2025 | Rpl Annun panels 24/25 cat arm | Replace Annunciator Panels (2024-2025) - Cat Arm | 351.4 | 603.0922 | 251.6922 | 71.63% | Included in Original Analysis | N/A
12922302 | 2023 | 2025 | Rpl Diesel Genset Ebbegunbaeg | Replace Diesel Genset 1 (2023-2024) - Ebbegunbaeg | 1026.3 | 1130.5443 | 104.2443 | 10.16% | Included in Original Analysis | N/A
20682510 | 2025 | 2025 | Upgr Work Protection Code25/26 | Upgrade Work Protection Code Application (2025-2026) | 708.64 | 592.214 | -116.426 | -16.43% | Included in Original Analysis | N/A
13332501 | 2025 | 2025 | Replace Roof Grey River 25 | Replace Roof (2025) - Grey River | 390.8 | 519.7822 | 128.9822 | 33% | Included in Original Analysis | N/A
13252405 | 2024 | 2025 | Upg Station Lighting Var 24/25 | Upgrade Station Lighting (2024-2025) - Bottom Waters, Deer Lake, Doyles, Indian River, and Western Avalon Terminal Stations | 520.6 | 680.1284 | 159.5284 | 30.64% | Included in Original Analysis | N/A
12922401 | 2024 | 2025 | Refurb Surge Tank 1 24/25 BDE | Refurbish Surge Tank 1 (2024-2025) - Bay d'Espoir | 2287.2 | 3485.6652 | 1198.4652 | 52.4% | Included in Original Analysis | N/A
21882503 | 2025 | 2025 | Inspt fuel tanks25 Stephenvile | Inspect Fuel Tanks (2025) - Stephenville | 676.9 | 1048.1662 | 371.2663 | 54.85% | Included in Original Analysis | N/A
21882402 | 2024 | 2025 | Inspt fuel tanks 24 HardwoodGT | Inspect Fuel Tanks (2024) - Hardwoods Gas Turbines | 692.9 | 1038.7661 | 345.8661 | 49.92% | Included in Original Analysis | N/A
12962403 | 2024 | 2025 | Upgr Unit 1 contr sys24/25 HRD | Upgrade Unit 1 Control System (2024-2025) - Holyrood | 652.6 | 732.5407 | 79.9407 | 12.25% | Included in Original Analysis | N/A
12932302 | 2023 | 2025 | Refurb SuprStructure SRS 23/24 | Refurbish Superstructure (2023-2024) - Salmon River Spillway | 2828.3 | 959.4117 | -1868.8884 | -66.08% | Included in Original Analysis | N/A
13252310 | 2023 | 2025 | Upgr Data Alarm system Buchans | Replace Data Alarm System Annunciators (2023) - Buchans | 166 | 425.808 | 259.808 | 156.5% | Included in Original Analysis | N/A
12422406 | 2024 | 2025 | Upgrade SCADA Network (2024) | Upgrade SCADA Network (2024) | 402.3 | 843.668 | 441.368 | 109.7% | Included in Original Analysis | N/A
14012101 | 2021 | 2025 | NAN-Diesel Genset Replac-21/22 | Diesel Genset Replacements (2021-2022) | 2846.8 | 3346.7633 | 499.9633 | 17.56% | Included in Original Analysis | N/A
13882201 | 2022 | 2025 | Install Fault Recorder WABTS | Upgrade Fault Recorders - WABTS (2022-2023) | 422.4 | 656.9887 | 234.5887 | 55.54% | Included in Original Analysis | N/A
13252309 | 2023 | 2025 | Ugr Breakr Fail Proc SSD 230KV | Install Breaker Failure Protection (2023-2024) - Sunnyside | 289.7 | 1477.4993 | 1187.7993 | 410% | Included in Original Analysis | N/A
13072201 | 2022 | 2025 | Replace Metering System | Replace Metering System | 5875.8 | 9295.4733 | 3419.6733 | 58.2% | Included in Original Analysis | N/A
13501791 | 2017 | 2017 | BWT-Additions for Load Growth | Additions for Load Growth - Bottom Waters | 3045 | 3024.8317 | -20.1683 | -0.6623% | Excluded from Original Analysis | Supplemental Project
12961791 | 2017 | 2017 | HRD-Exciter Controls Replcmnt | Exciter Controls Replacement - Holyrood | 1349.2 | 1339.8812 | -9.3188 | -0.6907% | Excluded from Original Analysis | Supplemental Project
12931791 | 2017 | 2017 | BDE Unit 3 Turb Rehabilitation | Unit 3 Turbine Rehabilitation - Bay d'Espoir | 2361.5 | 1905.3701 | -456.1299 | -19.32% | Excluded from Original Analysis | Supplemental Project
12931792 | 2017 | 2017 | BDE Penstock #2 Refurbishment | Penstock #2 Refurbishment - Bay d'Espoir | 9063.7 | 3586.3227 | -5477.3773 | -60.43% | Excluded from Original Analysis | Supplemental Project
21841791 | 2017 | 2017 | HVY GT Engine Refurbishments | Repair and Advanced Overhaul of the Happy Valley Gas Turbine | 3714.8 | 2049.2883 | -1665.5117 | -44.83% | Excluded from Original Analysis | Supplemental Project
12961792 | 2017 | 2018 | HRD-Reliability & Perform Upgr | Reliability Improvements - Holyrood | 2610 | 3883.9136 | 1273.9136 | 48.81% | Excluded from Original Analysis | Supplemental Project
12961693 | 2016 | 2018 | HRD-12MW Diesel Generation | Purchase of 12 MW Diesel Generation - Holyrood | 4700 | 4959.3215 | 259.3215 | 5.517% | Excluded from Original Analysis | Supplemental Project
13881791 | 2017 | 2018 | Wabush TS Upgrades (Twinco) | Terminal Station Upgrades - Wabush | 2912.5 | 1962.0603 | -950.4397 | -32.63% | Excluded from Original Analysis | Supplemental Project
13501891 | 2018 | 2018 | WRSB-HampdenWasteTransferSite | Provide Service to Western Regional Servce Board's Waste Transfer Site - Hampden | 748.4 | 644.5 | -103.9 | -13.88% | Excluded from Original Analysis | Supplemental Project
13961891 | 2018 | 2018 | Smokey Mountain-Line Upgrade | Perform Voltage Conversion of the Distribution Feeder VA26 - Labrador City | 719.4 | 705.1371 | -14.2629 | -1.983% | Excluded from Original Analysis | Supplemental Project
12961891 | 2018 | 2018 | HRD-Improve Boiler Capacity | Improve Boiler Capacity - Holyrood | 2560.5 | 1665.9473 | -894.5527 | -34.94% | Excluded from Original Analysis | Supplemental Project
13961892 | 2018 | 2018 | HVY - Gang Switch | Gang Switch - Happy Valley-Goose Bay | 195.4 | 85.1934 | -110.2066 | -56.4% | Excluded from Original Analysis | Supplemental Project
12811991 | 2019 | 2019 | HLK-Overhaul Unit 1 | Hinds Lake Unit Major Overhaul | 259.5 | 422.9321 | 163.4321 | 62.98% | Excluded from Original Analysis | Supplemental Project
12931991 | 2019 | 2019 | Penstock InspectionBDE,HLK,GCL | Level II Condition Assessments for Bay d'espoir Penstock 4, Granite Canal Penstock, and Hinds Lake Penstock | 414.3 | 294.4446 | -119.8554 | -28.93% | Excluded from Original Analysis | Supplemental Project
14281891 | 2018 | 2019 | TL226/TL239 ReRoute-Northern | TL226 and TL239 Reroute | 932.4 | 994.0751 | 61.6751 | 6.615% | Excluded from Original Analysis | Supplemental Project
12931892 | 2018 | 2019 | BDE-Penstock Cond Assessments | Penstock Condition Assessments - Bay d'Espoir | 1120.6 | 1832.673 | 712.073 | 63.54% | Excluded from Original Analysis | Supplemental Project
14111891 | 2018 | 2019 | Mary's Harbour Hydro Intergrat | Mary's Harbour Hydro Integration - CIAC | 195.5 | 242.67 | 47.17 | 24.13% | Excluded from Original Analysis | Supplemental Project
13882092 | 2020 | 2020 | Interconn BlockLab Data Center | Construction of a line extension and the installation of power usage monitoring and control equipment at the BlockLab site | 244 | 295.0094 | 51.0094 | 20.91% | Excluded from Original Analysis | Supplemental Project
12962091 | 2020 | 2020 | SUP OH U2 Turbine Valves -HRD | Overhaul Unit 2 Turbine Valves - Holyrood | 2919.5 | 3159.2509 | 239.7509 | 8.212% | Excluded from Original Analysis | Supplemental Project
12962092 | 2020 | 2020 | SUP Overhaul Unit 2 Genera HRD | Overhaul Unit 2 Generator - Holyrood | 1294.1 | 1410.2104 | 116.1104 | 8.972% | Excluded from Original Analysis | Supplemental Project
12962093 | 2020 | 2020 | SUP Overh.U3 Boiler FeedPu HRD | Overhaul Unit 3 Boiler Feed Pump West - Holyrood | 367.9 | 369.4504 | 1.5505 | 0.4214% | Excluded from Original Analysis | Supplemental Project
12972094 | 2020 | 2020 | SUP BoilerCon.Asses.MiscUpgHRD | Boiler Condition Assessment and Miscellaneous Upgrades - Holyrood | 3056.7 | 3221.1775 | 164.4775 | 5.381% | Excluded from Original Analysis | Supplemental Project
12422011 | 2020 | 2020 | Nain Diesel Plant Fibre Upgrad | Diesel Plant Fibre Upgrade - Nain | 44.773 | 37.1142 | -7.6588 | -17.11% | Excluded from Original Analysis | Supplemental Project
12962106 | 2021 | 2021 | Overhaul Unit 1 bolier Pump | Holyrood Overhaul Unit 1 boiler feed pump | 443.022 | 554.6588 | 111.6368 | 25.2% | Excluded from Original Analysis | Supplemental Project
14112102 | 2021 | 2021 | CHT Purchase Diesel Gen U 2102 | CHT Purchase Diesel | 350 | 350 | 0 | 0% | Excluded from Original Analysis | Supplemental Project
13401801 | 2018 | 2022 | Inc Fuel & Water Treatment Cap | Increase Fuel and Water Treatment System Capacity - Holyrood Gas Turbine | 11842.6 | 7625.4773 | -4217.1227 | -35.61% | Excluded from Original Analysis | Considered to be an anomaly based on estimate assumptions.
14101802 | 2018 | 2022 | STA-Rplc Automation Eqmt-18/19 | Replace Automation Equipment - St. Anthony | 1873.3 | 2516.4073 | 643.1073 | 34.33% | Excluded from Original Analysis | Modified Scope
13851901 | 2019 | 2022 | MF-HV Interconnect | Muskrat Falls to Happy Valley Interconnection | 19978.5 | 22693.8395 | 2715.3395 | 13.59% | Excluded from Original Analysis | Considered to be a large project therefore would skew the analysis.
13252201 | 2022 | 2022 | Terminal Stat In-Serv Failures | Terminal Station In-Service Failures (2022) | 900 | 3626.0948 | 2726.0948 | 302.9% | Excluded from Original Analysis | Undefined scope when budgeted
12932208 | 2022 | 2022 | Hydraulic In-Service Failures | Hydraulic Generation In-Service Failures (2022) | 1000 | 1425.7794 | 425.7794 | 42.58% | Excluded from Original Analysis | Undefined scope when budgeted
12962201 | 2022 | 2022 | Thermal In-Service Failures 22 | Thermal In-Service Failures (2022) | 2000 | 2893.7743 | 893.7743 | 44.69% | Excluded from Original Analysis | Undefined scope when budgeted
13252118 | 2021 | 2024 | Upgrd Retire SVLGT-BBK T4 | Upgrades for Future Retirement of Stephenville Gas Turbine | 6874.9 | 5115.5786 | -1759.3214 | -25.59% | Excluded from Original Analysis | Cancelled Scope
13462304 | 2023 | 2024 | Rpl Diesel Shop Building BIF | Replace Diesel Shop Building (2023-2025) - Bishop's Falls | 1422.1 | 241.8687 | -1180.2313 | -82.99% | Excluded from Original Analysis | Cancelled Scope
12982401 | 2024 | 2024 | Remove Safety Hazards - Var | Remove Safety Hazards (2024) | 198.3 | 322.4833 | 124.1833 | 62.62% | Excluded from Original Analysis | Undefined Scope when budgeted
13332401 | 2024 | 2024 | Diesel In-Service Failures 24 | Diesel In-Service Failures (2024) | 488.3 | 1984.5096 | 1496.2096 | 306.4% | Excluded from Original Analysis | Undefined scope when budgeted
21882401 | 2024 | 2024 | Gas Turbine In-Service Fail 24 | Gas Turbine In-Service Failures (2024) | 358 | 7101.6794 | 6743.6794 | 1884% | Excluded from Original Analysis | Undefined scope when budgeted
12932401 | 2024 | 2024 | Hydraulic In-Serv Failures 24 | Hydraulic In-Service Failures (2024) | 1500 | 2973.945 | 1473.945 | 98.26% | Excluded from Original Analysis | Undefined scope when budgeted
20682406 | 2024 | 2024 | Upgr Energy MGMT System 24 | Upgrade Energy Management System (2024) | 366.4 | 4.6125 | -361.7875 | -98.74% | Excluded from Original Analysis | Cancelled Scope
12422403 | 2024 | 2024 | Telecom ISFs 24 | Telecommunications In-Service Failure (2024) | 91.4 | 253.8086 | 162.4086 | 177.7% | Excluded from Original Analysis | Undefined scope when budgeted
13252402 | 2024 | 2024 | Terminal Station ISFs 24 | Terminal Station In-Service Failures (2024) | 1300 | 2459.2469 | 1159.2469 | 89.17% | Excluded from Original Analysis | Undefined scope when budgeted
13492403 | 2024 | 2024 | Transmission ISFs 2024 | Transmission In-Service Failures (2024) | 158.5 | 162.2437 | 3.7437 | 2.362% | Excluded from Original Analysis | Undefined scope when budgeted
12962401 | 2024 | 2024 | Thermal In-Service Failures 24 | Thermal In-Service Failures (2024) | 3508.7 | 4587.7513 | 1079.0513 | 30.75% | Excluded from Original Analysis | Undefined scope when budgeted
13462204 | 2022 | 2024 | Replace Vehicles and Aerial | Replace Light- and Heavy-Duty Vehicles (2022-2024) | 3481.8 | 2975.6269 | -506.1731 | -14.54% | Excluded from Original Analysis | Program subject to scope change within program scope
13252308 | 2023 | 2024 | Rpl Instr Transforms VAR 23/24 | Replace Instrument Transformers VAR 23/24 | 508.2 | 685.8358 | 177.6358 | 34.95% | Excluded from Original Analysis | Program subject to scope change within program scope
13252307 | 2023 | 2024 | Replace Disconnects 23/24 | Replace Disconnects 23/24 | 652.8 | 1081.3524 | 428.5524 | 65.65% | Excluded from Original Analysis | Program subject to scope change within program scope
14302301 | 2023 | 2024 | Rpl TS Battery Banks/Chargers | Replace Terminal Station Battery Banks/Chargers | 218.2 | 207.23 | -10.97 | -5.028% | Excluded from Original Analysis | Program subject to scope change within program scope
13502303 | 2023 | 2024 | Upg Distribution Feeders 23/24 | Upgrade of Worst-Performing Distribution Feeders (2023-2024) | 1446 | 2092.0239 | 646.0239 | 44.68% | Excluded from Original Analysis | Program subject to scope change within program scope
13462302 | 2023 | 2024 | Rplc Mobile equipment 2023 | Replace Mobile Equipment (2023-2024) | 728.5 | 764.6125 | 36.1125 | 4.957% | Excluded from Original Analysis | Program subject to scope change within program scope
13252304 | 2023 | 2024 | Upgr Power Transformers 23/24 | Upgrade Power Transformers 23/24 | 3979.3 | 4872.9742 | 893.6742 | 22.46% | Excluded from Original Analysis | Program subject to scope change within program scope
13252303 | 2023 | 2024 | Circuit Breakers Ren prg 23/24 | Circuit Breakers Renewal Program 23/24 | 3812 | 5578.6897 | 1766.6897 | 46.35% | Excluded from Original Analysis | Program subject to scope change within program scope
13252306 | 2023 | 2024 | Replace Protective Relays-M24 | Replace Protective Relays - M24 | 1959.7 | 2889.149 | 929.449 | 47.43% | Excluded from Original Analysis | Program subject to scope change within program scope
13332402 | 2024 | 2024 | Overhaul Diesel Units-Var 24 | Overhaul Diesel Units -Var 24 | 829.2 | 1300.3095 | 471.1095 | 56.81% | Excluded from Original Analysis | Program subject to scope change within program scope
13492401 | 2024 | 2024 | Wood Pole Line Management Prgm | Wood Pole Line Management (2024) | 3765.2 | 5122.7667 | 1357.5667 | 36.06% | Excluded from Original Analysis | Program subject to scope change within program scope
20682405 | 2024 | 2024 | Prfm soft upgrs/minor echan 24 | Perform Software Upgrades and Minor Enhancements (2024) | 864.2 | 337.0688 | -527.1312 | -61% | Excluded from Original Analysis | Program subject to scope change within program scope
20682403 | 2024 | 2024 | Upgrade Core IT/OT Infrast 24 | Upgrade Core OT Infrastructure (2024) | 174.7 | 148.1279 | -26.5721 | -15.21% | Excluded from Original Analysis | Program subject to scope change within program scope
20682404 | 2024 | 2024 | Upde Cyber Security Software24 | Update Cyber Security Infrastructure (2024) | 281.3 | 409.501 | 128.201 | 45.57% | Excluded from Original Analysis | Program subject to scope change within program scope
12422402 | 2024 | 2024 | Rplc Network Comms EQ 2024 | Replace Network Communications Equipment (2024) | 180.7 | 235.1952 | 54.4952 | 30.16% | Excluded from Original Analysis | Program subject to scope change within program scope
12422409 | 2024 | 2024 | Minor Telecomm Enhancements 24 | Minor Telecommunications Enhancements (2024) | 96.9 | 87.5957 | -9.3043 | -9.602% | Excluded from Original Analysis | Program subject to scope change within program scope
12422408 | 2024 | 2024 | Pur Mobile Devices Hydro 24 | Purchase Mobile Devices (2024) | 155.6 | 166.5659 | 10.9659 | 7.048% | Excluded from Original Analysis | Program subject to scope change within program scope
12972402 | 2024 | 2024 | HRD-Boiler Cond Asst Upgr 24 | Boiler Condition Assessment and Miscellaneous Upgrades (2024) - Holyrood | 3957.8 | 7864.5455 | 3906.7455 | 98.71% | Excluded from Original Analysis | Program subject to scope change within program scope
12962404 | 2024 | 2024 | Overhaul Pumps Holyrood 24 | Overhaul Pumps (2024) - Holyrood | 661 | 134.7362 | -526.2638 | -79.62% | Excluded from Original Analysis | Program subject to scope change within program scope
12422411 | 2024 | 2024 | Rplc 48VDC Batt/Charg VAR 24 | Replace 48 V Battery Banks and Chargers (2024) | 422.2 | 253.2494 | -168.9506 | -40.02% | Excluded from Original Analysis | Program subject to scope change within program scope
13072402 | 2024 | 2024 | Meters and Metering Equipment | Purchase Meters and Metering Equipment (2024) | 470.7 | 443.0241 | -27.6759 | -5.88% | Excluded from Original Analysis | Program subject to scope change within program scope
12422414 | 2024 | 2024 | Upgr Remote Terminals Units 24 | Upgrade Remote Terminal Units (2024) | 165.9 | 200.5309 | 34.6309 | 20.87% | Excluded from Original Analysis | Program subject to scope change within program scope
12972293 | 2022 | 2024 | HRD SUPP Refurb Tank 1 (2022) | Holyrood Fuel Tank #1 Fuel Inspection And Refurbishment - Supplemental | 2052.1 | 5793.7505 | 3741.6505 | 182.3% | Excluded from Original Analysis | Program subject to scope change within program scope
12932403 | 2024 | 2024 | Pur Tools/Eq under 50k Hydra24 | Purchase Tools and Equipment Less than $50,000 (2024) - Hydraulic Plants | 209.4 | 177.7685 | -31.6315 | -15.11% | Excluded from Original Analysis | Program subject to scope change within program scope
12422405 | 2024 | 2024 | Purchase Tools and Equipment | Purchase Tools and Equipment Less than $50,000 (2024) - Telecontrol | 45.6 | 44.5092 | -1.0908 | -2.392% | Excluded from Original Analysis | Program subject to scope change within program scope
13402401 | 2024 | 2024 | Purchase Tools & Equipment -GT | Purchase Tools and Equipment Less than $50,000 (2024) - Gas Turbine | 18.6 | 19.4235 | 0.82355 | 4.428% | Excluded from Original Analysis | Program subject to scope change within program scope
12962407 | 2024 | 2024 | Tools and Equip. Thermal 24 | Purchase Tools and Equipment Less than $50,000 (2024) - Thermal Plants | 167.1 | 152.2695 | -14.8305 | -8.875% | Excluded from Original Analysis | Program subject to scope change within program scope
20082402 | 2024 | 2024 | Purchase office equipment <50k | Purchase Office Equipment Less Than $50,000 (2024) | 50 | 55.0579 | 5.0579 | 10.12% | Excluded from Original Analysis | Program subject to scope change within program scope
20082491 | 2024 | 2024 | HYP Office Retrofits | Perform Office Modifications (2024) - Hydro Place | 249.809 | 96.367 | -153.442 | -61.42% | Excluded from Original Analysis | Program subject to scope change within program scope
13252504 | 2025 | 2025 | Terminal Station ISFs 25 | Terminal Station In-Service Failures (2025) | 2500 | 516.0051 | -1983.9949 | -79.36% | Excluded from Original Analysis | Undefined scope when budgeted
12962501 | 2025 | 2025 | Thermal In-Service Failures 25 | Thermal In-Service Failures (2025) | 3900 | 3058.7405 | -841.2595 | -21.57% | Excluded from Original Analysis | Undefined scope when budgeted
12422503 | 2025 | 2025 | Telecom ISFs 25 | Telecommunications In-Service Failures (2025) | 94.1 | 76.9914 | -17.1086 | -18.18% | Excluded from Original Analysis | Undefined scope when budgeted
13492501 | 2025 | 2025 | Transmission ISFs 2025 | Transmission In-Service Failures (2025) | 184.3 | 162.3248 | -21.9752 | -11.92% | Excluded from Original Analysis | Undefined scope when budgeted
14012502 | 2025 | 2025 | Diesel In-Service Failures 25 | Diesel In-Service Failures (2025) | 800 | 758.4302 | -41.5698 | -5.196% | Excluded from Original Analysis | Undefined scope when budgeted
21882501 | 2025 | 2025 | Gas Turbine In-Service Fail 25 | Gas Turbine In-Service Failures (2025) | 500 | 1868.1898 | 1368.1898 | 273.6% | Excluded from Original Analysis | Undefined scope when budgeted
20082590 | 2025 | 2025 | Inst Work Stations LVL 3&4 HYP | Supply & Install New Work Stations Level 4 Hydro Place (2025) | 747.767 | 707.3335 | -40.4335 | -5.407% | Excluded from Original Analysis | Supplemental Project
14272490 | 2024 | 2025 | Main Brook L1 Recon 24/25 | Additions for Load - Distribution Systems (2024-2026) - Main Brook | 353.02 | 483.5244 | 130.5044 | 36.97% | Excluded from Original Analysis | Supplemental Project
12942590 | 2025 | 2025 | Procure Stop Logs BDE unit 1-7 | Procure Stop Logs for Bay D'Espoir Units 1-7 | 740 | 728.584 | -11.416 | -1.543% | Excluded from Original Analysis | Supplemental Project
12422490 | 2024 | 2025 | Inst site-wide Radio Sys HRD | Purchase & Install Site Radio System (2024) - Holyrood | 412.2 | 425.2118 | 13.0118 | 3.157% | Excluded from Original Analysis | Supplemental Project
20082492 | 2024 | 2025 | HYP 4th fl fire restore | Completion of Fire Restoration – Fourth Floor Hydro Place | 1067.9 | 1151.9531 | 84.0531 | 7.871% | Excluded from Original Analysis | Supplemental Project
13332592 | 2025 | 2025 | Install Add Fuel Tank Ram 25 | Install Additional Fuel Tank Ramea (2025) | 232.5 | 179.1124 | -53.3876 | -22.96% | Excluded from Original Analysis | Supplemental Project
12962402 | 2024 | 2025 | Upgr DCS Hware Unit 1/3 BMS 3 | Upgrade DCS Hardware - Units 1 and 2 (2024-2025) - Holyrood | 472.5 | 616.5842 | 144.0842 | 30.49% | Excluded from Original Analysis | Modified Scope
13972403 | 2024 | 2025 | Upg Distribution Feeders 24/25 | Upgrade Worst-Performing Distribution Feeders (2024-2025) | 3291.7 | 5505.7124 | 2214.0124 | 67.26% | Excluded from Original Analysis | Modified scope
13502404 | 2024 | 2025 | Distr Feeders Refurb 24/25 | Renew Distribution Feeders (2024-2025) | 2532.4 | 2433.3572 | -99.0428 | -3.911% | Excluded from Original Analysis | Modified scope
14112201 | 2022 | 2025 | Add Load 22 - MSH SER CON | Additions for Load (2022) - Mary's Harbour Service Conductor | 359.1 | 183.1224 | -175.9776 | -49.01% | Excluded from Original Analysis | Cancelled scope
13882101 | 2021 | 2025 | WAB Substation Ugrde-M23 | Additions for Load - Wabush Substation Upgrades | 10694.1 | 8995.2589 | -1698.8411 | -15.89% | Excluded from Original Analysis | Cancelled Scope
20682504 | 2025 | 2025 | Upde Cyber Security Infrast25 | Update Cyber Security Infrastructure (2025) | 115.6 | 68.185 | -47.415 | -41.02% | Excluded from Original Analysis | Program subject to scope change within program scope
12422502 | 2025 | 2025 | Rplc Network Comms EQ 2025 | Replace Network Communications Equipment (2025) | 413.2 | 246.0502 | -167.1498 | -40.45% | Excluded from Original Analysis | Program subject to scope change within program scope
13402503 | 2025 | 2025 | Purchase Tools & Equipment -GT | Purchase Tools and Equipment (2025) - Gas Turbines | 46.6 | 30.3801 | -16.2199 | -34.81% | Excluded from Original Analysis | Program subject to scope change within program scope
20682505 | 2025 | 2025 | Prfm soft upgrs/minor echan 25 | Perform Software Upgrades and Minor Enhancements (2025) | 808.7 | 565.4577 | -243.2423 | -30.08% | Excluded from Original Analysis | Program subject to scope change within program scope
12962505 | 2025 | 2025 | Tools and Equip. Thermal 25 | Purchase Tools and Equipment (2025) - Thermal Plants | 127.3 | 100.6117 | -26.6883 | -20.96% | Excluded from Original Analysis | Program subject to scope change within program scope
13252403 | 2024 | 2025 | Upgr Power Transformers 24/25 | Upgrade Power Transformers (2024-2025) | 3575.9 | 5209.2209 | 1633.3209 | 45.68% | Excluded from Original Analysis | Program subject to scope change within program scope
12422508 | 2025 | 2025 | Pur Mobile Devices Hydro 25 | Purchase Mobile Devices (2025) | 160.2 | 132.4761 | -27.7239 | -17.31% | Excluded from Original Analysis | Program subject to scope change within program scope
13252401 | 2024 | 2025 | Circuit Breakers Ren prg 24/25 | Renew Circuit Breakers (2024–2025) | 2304 | 2271.086 | -32.914 | -1.429% | Excluded from Original Analysis | Program subject to scope change within program scope
14112204 | 2022 | 2025 | Diesel Genset RplcUnit2012 LAL | Diesel Genset Replacement Unit 2012 - L'Anse-Au-Loup | 3063.3 | 2699.8056 | -363.4944 | -11.87% | Excluded from Original Analysis | Program subject to scope change within program scope
20682503 | 2025 | 2025 | Upgrade Core IT/OT Infrast 25 | Upgrade Core OT Infrastructure (2025) | 674.3 | 621.8872 | -52.4128 | -7.773% | Excluded from Original Analysis | Program subject to scope change within program scope
20082502 | 2025 | 2025 | Perf Security Improvements 25 | Perform Security Improvements (2025) | 160.7 | 150.6949 | -10.0051 | -6.226% | Excluded from Original Analysis | Program subject to scope change within program scope
12422509 | 2025 | 2025 | Minor Telecomm Enhancements 25 | Perform Minor Telecommunications Enhancements (2025) | 99.8 | 96.904 | -2.896 | -2.902% | Excluded from Original Analysis | Program subject to scope change within program scope
12962405 | 2024 | 2025 | Overhaul unit 1 turb/valves 24 | Overhaul Unit 1 Turbine Valves and Generator (2024) - Holyrood | 5181.4 | 11724.3023 | 6542.9023 | 126.3% | Excluded from Original Analysis | Program subject to scope change within program scope
12962304 | 2023 | 2025 | Overhaul unit 2 turb/valves 23 | Overhaul Unit 2 Turbine and Valves (2023) - Holyrood | 9701.8 | 12628.3989 | 2926.5989 | 30.17% | Excluded from Original Analysis | Program subject to scope change within program scope
12422506 | 2025 | 2025 | Upgr Remote Terminals Units 25 | Upgrade Remote Terminal Units (2025) | 238.4 | 240.9255 | 2.5255 | 1.059% | Excluded from Original Analysis | Program subject to scope change within program scope
12422501 | 2025 | 2025 | Rplc 48V Batt Banks/Chargers25 | Replace 48 V Battery Banks and Chargers (2025) | 559.1 | 566.6032 | 7.5032 | 1.342% | Excluded from Original Analysis | Program subject to scope change within program scope
12422505 | 2025 | 2025 | Purchase Tools and Equipment | Purchase Tools and Equipment (2025) - Telecontrol | 45.3 | 46.029 | 0.72897 | 1.609% | Excluded from Original Analysis | Program subject to scope change within program scope
14012501 | 2025 | 2025 | Overhaul Diesel Units 25 | Overhaul Diesel Units (2025) | 1000 | 1102.2838 | 102.2838 | 10.23% | Excluded from Original Analysis | Program subject to scope change within program scope
13252408 | 2024 | 2025 | Replace Protective Relays-M25 | Replace Protective Relays (2024–2025) | 3439.1 | 5120.0159 | 1680.916 | 48.88% | Excluded from Original Analysis | Program subject to scope change within program scope
20082501 | 2025 | 2025 | Mod Office Bldg Procure Eq 25 | Modify Office Buildings and Procure Furniture, Fixtures, & Equipment (2025) | 178.5 | 214.4658 | 35.9658 | 20.15% | Excluded from Original Analysis | Program subject to scope change within program scope
12932503 | 2025 | 2025 | Pur Tools & Eq. Hydraulic | Purchase Tools and Equipment (2025) - Hydraulic Plants | 154.9 | 191.8962 | 36.9962 | 23.88% | Excluded from Original Analysis | Program subject to scope change within program scope
13462401 | 2024 | 2025 | Rplc Mobile equipment 2024 | Replace Mobile Equipment (2024-2025) | 816.6 | 884.8293 | 68.2293 | 8.355% | Excluded from Original Analysis | Program subject to scope change within program scope
12932501 | 2025 | 2025 | Hydraulic In-Serv Failures 25 | Hydraulic In-Service Failures (2025) | 2000 | 2723.2428 | 723.2428 | 36.16% | Excluded from Original Analysis | Program subject to scope change within program scope
13492502 | 2025 | 2025 | Wood Pole Line Management Prgm | Wood Pole Line Management (2025) | 4281.3 | 5877.517 | 1596.2169 | 37.28% | Excluded from Original Analysis | Program subject to scope change within program scope
13252409 | 2024 | 2025 | Replace Disconnects 24/25 | Replace Disconnects (2024–2025) | 1485.5 | 2233.1765 | 747.6765 | 50.33% | Excluded from Original Analysis | Program subject to scope change within program scope
13462301 | 2023 | 2025 | Rplc Light/Heavy Duty Mbl Equi | Replace Light- and Heavy-Duty Vehicles (2023-2025) | 4566 | 5443.1925 | 877.1925 | 19.21% | Excluded from Original Analysis | Program subject to scope change within program scope
12972502 | 2025 | 2025 | Boiler CA/Misc Upgr 25 HRD | Perform Boiler Condition Assessment and Miscellaneous Upgrades (2025) - Holyrood | 4905.8 | 8085.6781 | 3179.8781 | 64.82% | Excluded from Original Analysis | Program subject to scope change within program scope
12982501 | 2025 | 2025 | Remove Safety Hazards 25 | Remove Safety Hazards (2025) | 203.3 | 340.2559 | 136.9559 | 67.37% | Excluded from Original Analysis | Program subject to scope change within program scope
13252406 | 2024 | 2025 | Rpl Instr Transforms VAR 24/25 | Replace Instrument Transformers (2024–2025) | 869.7 | 1344.0434 | 474.3434 | 54.54% | Excluded from Original Analysis | Program subject to scope change within program scope
13252404 | 2024 | 2025 | Repl TS Batt Banks/Chargers24 | Replace Terminal Station Battery Banks and Chargers (2024–2025) | 192.7 | 301.8753 | 109.1753 | 56.66% | Excluded from Original Analysis | Program subject to scope change within program scope
12962502 | 2025 | 2025 | Overhaul Pumps Holyrood 25 | Overhaul Major Pumps (2025) - Holyrood | 1101.9 | 2826.12 | 1724.22 | 156.5% | Excluded from Original Analysis | Program subject to scope change within program scope
[5 empty] | 1268186.7225 | 1250322.3177 | -17864.4048
|  |  |  | check | 0 | 0 | -2.9104e-11

## REVISED Statistical Analysis
Values
Var % | CBA / CAPEX Title | Sum of Budget | Sum of Actual Cost | Category | Chart Data | Stats Data
-100% | Integrate Renewable PH2 - Mary's Harbour | 498 | 1.4552e-14 | (>=100%) | -100% | -100% | 0
-100% | Wabush L34 and L35 Protective Relays - CIAC | 259.302 | 0 | (>=100%) | -100% | -100% | 0
-92.03% | Refurbish Hydraulic Structures - BDE (2019-20) | 5036.5 | 401.279 | (99.9%-90%) | -92.03% | -92.03% | 0
-88.55% | Purchase Office Equipment | 60.9 | 6.9706 | (89.9%-80%) | -88.55% | -88.55% | 0
-81.57% | Replace Insulators - Various (2019-20) | 989 | 182.2252 | (89.9%-80%) | -81.57% | -81.57% | 1
-81.38% | Security Improvements - Hydro Place | 45.5 | 8.47 | (89.9%-80%) | -81.38% | -81.38% | 1
-81.17% | Stage 2 Emergency Diesel Generator Refurbishment - Holyrood | 49.5 | 9.3213 | (89.9%-80%) | -81.17% | -81.17% | 1
-79.76% | Replace Insulators - Various Sites | 971.9 | 196.665 | (79.9%-70%) | -79.76% | -79.76% | 1 | Min | -100%
-76.22% | Replace Insulators - Various Sites | 961.8 | 228.7218 | (79.9%-70%) | -76.22% | -76.22% | 1 | Max | 1884% | Count of Chart Data
-73.81% | Replace Surge Arrestors - Various Sites | 361.8 | 94.7661 | (79.9%-70%) | -73.81% | -73.81% | 1 | Var | 86.98% | Category | Total
-72.69% | Replace Units 1-6 Generator Bearing Cover Seals - BDE | 656.7 | 179.374 | (79.9%-70%) | -72.69% | -72.69% | 1 | Std Dev | 93.26% | (>=100%) | 2
-70.8% | Replace Office Desk Chairs - Hydro Place | 90 | 26.2783 | (79.9%-70%) | -70.8% | -70.8% | 1 | Avg | 6.885% | (19.9%-10%) | 83
-68.88% | Replace Light- and Heavy-Duty Vehicles (2021-2022) | 5909.7557 | 1838.9963 | (69.9%-60%) | -68.88% | -68.88% | 1 | Count | 710 | (29.9%-20%) | 60
-67.2% | Purchase Office Equipment | 62.264 | 20.4248 | (69.9%-60%) | -67.2% | -67.2% | 1 | Lower SD | -86.38% | (39.9%-30%) | 55
-67.01% | Replace 60 kW Diesel Generator - Burnt Dam | 1161.7 | 383.2038 | (69.9%-60%) | -67.01% | -67.01% | 1 | Upper SD | 100.1% | (49.9%-40%) | 37
-66.08% | Refurbish Superstructure (2023-2024) - Salmon River Spillway | 2828.3 | 959.4117 | (69.9%-60%) | -66.08% | -66.08% | 1 |  |  | (59.9%-50%) | 24
-66.03% | Upgrade Cables - Various (2020) | 473.611 | 160.902 | (69.9%-60%) | -66.03% | -66.03% | 1 |  |  | (69.9%-60%) | 15
-65.95% | Install Recloser Remote Control (2019-2020) - Rocky Harbour | 386 | 131.4482 | (69.9%-60%) | -65.95% | -65.95% | 1 |  |  | (79.9%-70%) | 7
-65.18% | Install Breaker Failure Protection - DLK (2022-23) | 171.216 | 59.6105 | (69.9%-60%) | -65.18% | -65.18% | 1 |  |  | (89.9%-80%) | 5
-65.18% | Install Breaker Failure Protection - DLK (2022-23) | 171.2 | 59.6105 | (69.9%-60%) | -65.18% | -65.18% | 1 |  |  | (9.9%-0.01%) | 105
-64.73% | Replace Disconnects - Various Sites | 3369.9 | 1188.4301 | (69.9%-60%) | -64.73% | -64.73% | 1 |  |  | (99.9%-90%) | 2
-63.84% | Hydraulic In-Service Failures | 1251.1 | 452.4231 | (69.9%-60%) | -63.84% | -63.84% | 1 |  |  | >100% | 26
-61.02% | Penstock Level II Condition Assessment (2024) - Upper Salmon | 382.8 | 149.2214 | (69.9%-60%) | -61.02% | -61.02% | 1 |  |  | >500% | 3
-60.98% | Install Infrared Viewports - VAR | 257.5 | 100.4698 | (69.9%-60%) | -60.98% | -60.98% | 1 |  |  | 0%-9.9% | 95
-59.97% | Refurbish 230kV TS - WAB | 4969.8 | 1989.1801 | (59.9%-50%) | -59.97% | -59.97% | 1 |  |  | 10%-19.9% | 47
-58.64% | Additions for Load Growth - Makkovik and Rigolet | 730.1 | 301.9776 | (59.9%-50%) | -58.64% | -58.64% | 1 |  |  | 20%-29.9% | 31
-57.96% | Purchase Tools and Equipment less than $50,000 | 18.8 | 7.9027 | (59.9%-50%) | -57.96% | -57.96% | 1 |  |  | 30%-39.9% | 34
-56.65% | Additions for Load - Distribution System | 186.7 | 80.9272 | (59.9%-50%) | -56.65% | -56.65% | 1 |  |  | 40%-49.9% | 23
-56.11% | Gas Turbine Life Extension - Stephenville | 1353.2 | 593.922 | (59.9%-50%) | -56.11% | -56.11% | 1 |  |  | 50%-59.9% | 21
-55.95% | Additions for Load Growth - Happy Valley | 505 | 222.4552 | (59.9%-50%) | -55.95% | -55.95% | 1 |  |  | 60%-69.9% | 14
-55.82% | Refurbish Hydraulic Structures - Various | 4367.3 | 1929.5158 | (59.9%-50%) | -55.82% | -55.82% | 1 |  |  | 70%-79.9% | 8
-55.5% | Upgrade Fleet Infrastructure Program - Install L2 EV Chargers (2024) - Hydro Place | 322.635 | 143.5823 | (59.9%-50%) | -55.5% | -55.5% | 1 |  |  | 80%-89.9% | 8
-55.39% | Upgrade Fault Recorders - BHL (2019) | 623.5 | 278.1333 | (59.9%-50%) | -55.39% | -55.39% | 1 |  |  | 90%-99.9% | 5
-55.31% | Replace Oil Mist Separator (2023-2024) - Happy Valley Gas Turbine | 400.6 | 179.0169 | (59.9%-50%) | -55.31% | -55.31% | 1 |  |  | Grand Total | 710
-54.75% | Install Fire Protection in 230 kV Stations - OPD (2019-20) | 883.3 | 399.6995 | (59.9%-50%) | -54.75% | -54.75% | 1
-54.56% | Install Protective Guards in Turbine Pits - BDE, USL | 541 | 245.8418 | (59.9%-50%) | -54.56% | -54.56% | 1
-54.17% | Replace Lignt and Heavy Duty Vehicles - Various (2020) | 8848.5694 | 4055.059 | (59.9%-50%) | -54.17% | -54.17% | 1
-53.6% | Upgrade Power Transformers - Various Sites | 4829 | 2240.7098 | (59.9%-50%) | -53.6% | -53.6% | 1
-53.43% | Replace Tracks - V7271 - Supplemental | 96.62 | 45 | (59.9%-50%) | -53.43% | -53.43% | 1
-53.35% | Upgrade Reclosing Circuit Breakers B12L65 & B2L68 - HRD | 367.6 | 171.4778 | (59.9%-50%) | -53.35% | -53.35% | 1
-52.81% | Replace Disconnect Switches - Various Sites | 2458.5 | 1160.2887 | (59.9%-50%) | -52.81% | -52.81% | 1
-52.74% | Line Depot Condition Assessment and Refurbishment Program - Various Sites | 1458.8 | 689.3875 | (59.9%-50%) | -52.74% | -52.74% | 1
-51.93% | Replace 66 kV Station Service Feed - Holyrood | 1261.4 | 606.3337 | (59.9%-50%) | -51.93% | -51.93% | 1
-50.95% | Gas Turbine Life Extension - Hardwoods | 956.7 | 469.2565 | (59.9%-50%) | -50.95% | -50.95% | 1
-50.71% | Install Fire Protection in 230 kV Stations - Various Sites | 764.9 | 377.0449 | (59.9%-50%) | -50.71% | -50.71% | 1
-50.47% | Purchase Tools and Equipment less than $50,000 | 93.4 | 46.2635 | (59.9%-50%) | -50.47% | -50.47% | 1
-50.21% | Upgrade Aluminum Support Structures - Holyrood | 287.6 | 143.188 | (59.9%-50%) | -50.21% | -50.21% | 1
-49.64% | Replace Units 1-6 Generator Bearing Cover Seals - BDE | 296.4675 | 149.2869 | (49.9%-40%) | -49.64% | -49.64% | 1
-49.28% | Upgrade Cables - various (2021) | 496.693 | 251.938 | (49.9%-40%) | -49.28% | -49.28% | 1
-48.97% | Install Breaker Failure Protection - STB, STD (2019-20) | 582.6 | 297.2845 | (49.9%-40%) | -48.97% | -48.97% | 1
-47.65% | Upgrade Compressed Air System - Holyrood Gas Turbine | 388.4 | 203.315 | (49.9%-40%) | -47.65% | -47.65% | 1
-47.64% | Replace Vent Chambers - BDE | 380.7 | 199.3452 | (49.9%-40%) | -47.64% | -47.64% | 1
-46.34% | Purchase Office Equipment | 38 | 20.3895 | (49.9%-40%) | -46.34% | -46.34% | 1
-45.93% | Upgrade Aluminum Support Structures - Holyrood | 352.9 | 190.8158 | (49.9%-40%) | -45.93% | -45.93% | 1
-45.47% | Replace Roof - Hydro Place | 923.4 | 503.5026 | (49.9%-40%) | -45.47% | -45.47% | 1
-44.96% | Replace Protective Relays - Various Sites | 7535.5 | 4147.7088 | (49.9%-40%) | -44.96% | -44.96% | 1
-44.59% | Condition Assessment for Submarine Cable - Farewell Head to Change Islands | 300.1 | 166.2941 | (49.9%-40%) | -44.59% | -44.59% | 1
-44.43% | Install Asset Health Monitoring System - Upper Salmon | 641.4 | 356.4498 | (49.9%-40%) | -44.43% | -44.43% | 1
-44.06% | Replace Radomes - Various | 384.512 | 215.1132 | (49.9%-40%) | -44.06% | -44.06% | 1
-44.05% | Inspect Chemical Tanks - Holyrood | 919.8 | 514.6453 | (49.9%-40%) | -44.05% | -44.05% | 1
-43.59% | Flatten Downstream Slope (2024-2025) - Hinds Lake | 3229.5 | 1821.7461 | (49.9%-40%) | -43.59% | -43.59% | 1
-43.51% | Replace Power Transformers - Oxen Pond | 1147.6 | 648.3048 | (49.9%-40%) | -43.51% | -43.51% | 1
-43.36% | Install Fire Protection in 230 kV Stations - Massey Drive | 921.499 | 521.9126 | (49.9%-40%) | -43.36% | -43.36% | 1
-43.23% | Replace Instrument Transformers - Various Sites | 1181.1 | 670.5452 | (49.9%-40%) | -43.23% | -43.23% | 1
-42.91% | Replace Disconnects - Various (2019-20) | 2350.7 | 1341.9522 | (49.9%-40%) | -42.91% | -42.91% | 1
-42.83% | Air Receivers Condition Assessment and Upgrades - Holyrood | 336.5 | 192.3849 | (49.9%-40%) | -42.83% | -42.83% | 1
-42.76% | Install Fault Recorders - HVY (2020-21) | 687.951 | 393.8016 | (49.9%-40%) | -42.76% | -42.76% | 1
-42.71% | Install Fire Protection in 230 kV Stations - STB (2020-21) | 681.195 | 390.2868 | (49.9%-40%) | -42.71% | -42.71% | 1
-42.54% | Replace Control Cable PH1 - BDE (2019) | 415.6 | 238.7892 | (49.9%-40%) | -42.54% | -42.54% | 1
-42.26% | Replace Diesel Plant Roof - LAL/STA | 2313.5555 | 1335.8991 | (49.9%-40%) | -42.26% | -42.26% | 1
-42.08% | Install Power Canal Public Safety Boom (2025) - Upper Salmon | 463.8 | 268.6314 | (49.9%-40%) | -42.08% | -42.08% | 1
-41.78% | Replace Recloser - Wabush | 199.2 | 115.9747 | (49.9%-40%) | -41.78% | -41.78% | 1
-41.63% | Install Hydrometeorological Equipment - Various Sites | 314.1 | 183.3448 | (49.9%-40%) | -41.63% | -41.63% | 1
-41.48% | Install Pole Storage Ramps - Various Sites | 816.4 | 477.7208 | (49.9%-40%) | -41.48% | -41.48% | 1
-41.07% | Replace Instrument Transformers - Various Sites | 1345.3 | 792.7631 | (49.9%-40%) | -41.07% | -41.07% | 1
-40.88% | Replace Interior and Exterior Coating on Surge Tank 1 - BDE | 3564.1 | 2107.1363 | (49.9%-40%) | -40.88% | -40.88% | 1
-40.7% | Install Recloser Remote Control (2021-2022) - Various | 360.4826 | 213.7629 | (49.9%-40%) | -40.7% | -40.7% | 1
-40.6% | Upgrade Cables - Various (2019) | 500 | 297.006 | (49.9%-40%) | -40.6% | -40.6% | 1
-40.15% | Upper Salmon -Overhaul Turbine/Gen. Unit | 729.1 | 436.349 | (49.9%-40%) | -40.15% | -40.15% | 1
-39.92% | Security Improvements - Hydro Place | 47.1 | 28.2976 | (39.9%-30%) | -39.92% | -39.92% | 1
-39.42% | Install Infrared Scanning Ports - Happy Valley Gas Turbine | 87.5574 | 53.0414 | (39.9%-30%) | -39.42% | -39.42% | 1
-39.35% | Additions for Load Growth - Postville - Black Tickle | 1453.8 | 881.7762 | (39.9%-30%) | -39.35% | -39.35% | 1
-39.27% | Replace Protective Relays - Various (2019-20) | 4579.4 | 2781.0307 | (39.9%-30%) | -39.27% | -39.27% | 1
-38.78% | Refurbish 230 kV Terminal Station Part 2 - WAB (2020-21) | 2465.576 | 1509.4403 | (39.9%-30%) | -38.78% | -38.78% | 1
-38.57% | Install Pole Storage Ramps - Wabush | 301.7 | 185.3397 | (39.9%-30%) | -38.57% | -38.57% | 1
-38.16% | Replace Timber Crib and Insulation (2024) - Burnt Dam Spillway | 161.8 | 100.0608 | (39.9%-30%) | -38.16% | -38.16% | 1
-37.97% | Upgrade Fault Recorder System for 2018- Various Sites | 1026.9 | 636.9772 | (39.9%-30%) | -37.97% | -37.97% | 1
-37.9% | Refurbish Wabush Terminal Station | 5548.5 | 3445.6882 | (39.9%-30%) | -37.9% | -37.9% | 1
-37.8% | Upgrade Warehouse Lighting - Bishop's Falls | 195.6 | 121.6659 | (39.9%-30%) | -37.8% | -37.8% | 1
-37.52% | Replace Protective Relays - Various (2022-23) | 2253.2078 | 1407.7079 | (39.9%-30%) | -37.52% | -37.52% | 1
-37.36% | Upgrade Power Transformers - Various Sites | 14559 | 9119.2081 | (39.9%-30%) | -37.36% | -37.36% | 1
-36.96% | Upgrade Equipment Foundations - Various Sites | 389.2 | 245.336 | (39.9%-30%) | -36.96% | -36.96% | 1
-36.7% | Upgrade Power Transformers - Various (2019-20) | 9102.7 | 5761.9806 | (39.9%-30%) | -36.7% | -36.7% | 1
-36.64% | Replace Surge Arrestors - Various Sites | 373.4 | 236.5843 | (39.9%-30%) | -36.64% | -36.64% | 1
-36.63% | Upgrade Fault Recorders - Various (2021) | 692.816 | 439.025 | (39.9%-30%) | -36.63% | -36.63% | 1
-36.5% | Unit 7 Condition Assessment (2023) - Bay d'Espoir | 597.5 | 379.4053 | (39.9%-30%) | -36.5% | -36.5% | 1
-36.23% | Replace Slip Rings Units 1-6 - Bay d'Espoir | 472.3 | 301.1664 | (39.9%-30%) | -36.23% | -36.23% | 1
-36.1% | Replace Transfer Switches and Associated Hardware - Hydro Place | 2324.6091 | 1485.3389 | (39.9%-30%) | -36.1% | -36.1% | 1
-35.89% | Overhaul Diesel Units - Various | 1232.9 | 790.3924 | (39.9%-30%) | -35.89% | -35.89% | 1
-35.87% | Upgrade Public Safety, Dams | 728.514 | 467.1982 | (39.9%-30%) | -35.87% | -35.87% | 1
-34.98% | Replace Network Communications Equipment (2022) | 312.5964 | 203.258 | (39.9%-30%) | -34.98% | -34.98% | 1
-34.97% | Install Diesel Fuel Metering Devices - BDE, PRV, VIC, GCL | 406.6 | 264.3975 | (39.9%-30%) | -34.97% | -34.97% | 1
-34.55% | Terminal Station In-Service Failures | 1800 | 1178.0273 | (39.9%-30%) | -34.55% | -34.55% | 1
-34.35% | Diesel Genset Replacements - Port Hope Simpson | 4374.3 | 2871.8409 | (39.9%-30%) | -34.35% | -34.35% | 1
-34.23% | Inspect Fuel Storage Tanks - Postville | 532.6 | 350.282 | (39.9%-30%) | -34.23% | -34.23% | 1
-33.96% | Replace Substation - Holyrood | 1198 | 791.1895 | (39.9%-30%) | -33.96% | -33.96% | 1
-33.84% | Install Breaker Failure - Various Sites | 855.5 | 566.0153 | (39.9%-30%) | -33.84% | -33.84% | 1
-33.53% | Water System Replacements - Bay d'Espoir and Cat Arm | 2553.8 | 1697.4616 | (39.9%-30%) | -33.53% | -33.53% | 1
-33.5% | Upgrade Fuel Storage Tanks - Charlottetown | 467.169 | 310.6504 | (39.9%-30%) | -33.5% | -33.5% | 1
-33.3% | Purchase Tools and Equipment less than $50,000 | 46 | 30.6813 | (39.9%-30%) | -33.3% | -33.3% | 1
-33.17% | Replace Fuel Storage Tanks - PR | 350.3 | 234.0964 | (39.9%-30%) | -33.17% | -33.17% | 1
-32.85% | Replace Surface Air Coolers for Both Units - CAT | 869.0732 | 583.5549 | (39.9%-30%) | -32.85% | -32.85% | 1
-32.84% | Upgrade Circuit Breakers (2022-2023) - Various | 8402.5238 | 5643.3502 | (39.9%-30%) | -32.84% | -32.84% | 1
-32.33% | Penstock 3 Laser Scanning - Bay d'Espoir | 46.3 | 31.3326 | (39.9%-30%) | -32.33% | -32.33% | 1
-32.26% | Inspect Fuel Storage Tanks - Various Sites | 1058.8 | 717.2581 | (39.9%-30%) | -32.26% | -32.26% | 1
-32% | Upgrade Circuit Breakers (2021-2022) - Various | 12048.6929 | 8193.3203 | (39.9%-30%) | -32% | -32% | 1
-31.9% | Purchase Mobile DC Power Systems | 966.5 | 658.2083 | (39.9%-30%) | -31.9% | -31.9% | 1
-31.85% | Refurbish Turbine Unit 2- BDE | 2520.7 | 1717.8404 | (39.9%-30%) | -31.85% | -31.85% | 1
-31.53% | Condition Monitoring Equipment - BDE | 340.4 | 233.0878 | (39.9%-30%) | -31.53% | -31.53% | 1
-31.4% | Turbine Valve Overhaul Unit 3 - Holyrood | 3623.5 | 2485.5916 | (39.9%-30%) | -31.4% | -31.4% | 1
-31.29% | Upgrade Ventilation in Powerhouse 1 and 2 - Bay d'Espoir | 997.9 | 685.6245 | (39.9%-30%) | -31.29% | -31.29% | 1
-31.21% | Transmission Line Upgrades - TL212 and TL218 | 2511.5 | 1727.6704 | (39.9%-30%) | -31.21% | -31.21% | 1
-30.94% | Overhaul Pumps - Holyrood | 438.3 | 302.6828 | (39.9%-30%) | -30.94% | -30.94% | 1
-30.91% | Refurbish Accommodation - USL | 74.5 | 51.4691 | (39.9%-30%) | -30.91% | -30.91% | 1
-30.89% | Implement Terminal Station Flood Mitigation - Springdale | 974 | 673.1173 | (39.9%-30%) | -30.89% | -30.89% | 1
-30.89% | Overhaul Unit 3 Boiler Feed Pump - Holyrood | 373 | 257.7866 | (39.9%-30%) | -30.89% | -30.89% | 1
-30.69% | Upgrade Terminal Station Equipment Foundations - Various (2020) | 349.9 | 242.5254 | (39.9%-30%) | -30.69% | -30.69% | 1
-30.66% | Replace Radomes (2022) - Various | 179.9 | 124.7468 | (39.9%-30%) | -30.66% | -30.66% | 1
-30.44% | Replace Fuel Tank 22E - St. Anthony | 199.8 | 138.973 | (39.9%-30%) | -30.44% | -30.44% | 1
-29.99% | Replace Exciter Controls Units 1 to 6 - Bay d'Espoir | 3347 | 2343.2927 | (29.9%-20%) | -29.99% | -29.99% | 1
-29.69% | Upgrade Power Transformers - Various (2022-23) | 3758.9072 | 2642.7505 | (29.9%-20%) | -29.69% | -29.69% | 1
-29.26% | Tanks 3 & 4 Life Expectancy Study - Holyrood | 48.3172 | 34.18 | (29.9%-20%) | -29.26% | -29.26% | 1
-28.98% | Upgrade Holyrood Access Road - Holyrood | 1162.6 | 825.6932 | (29.9%-20%) | -28.98% | -28.98% | 1
-28.87% | Overhaul Diesel Units - Various Sites | 2852.4 | 2028.9873 | (29.9%-20%) | -28.87% | -28.87% | 1
-28.76% | Upgrade Power Transformers - Various (2021-22) | 4312.318 | 3072.2791 | (29.9%-20%) | -28.76% | -28.76% | 1
-28.69% | Cable Upgrades - Various Sites | 932.1 | 664.7091 | (29.9%-20%) | -28.69% | -28.69% | 1
-28.18% | Replace Insulators - TL227 | 416.9 | 299.4214 | (29.9%-20%) | -28.18% | -28.18% | 1
-28% | Upgrade HMI and AVR - Hardwoods | 685.9 | 493.8231 | (29.9%-20%) | -28% | -28% | 1
-27.93% | Terminal Station In-Service Failures | 1500.046 | 1081.0307 | (29.9%-20%) | -27.93% | -27.93% | 1
-27.9% | Upgrade Circuit Breakers - Various Sites | 61460.4 | 44310.9252 | (29.9%-20%) | -27.9% | -27.9% | 1
-27.85% | Replace TS Battery Banks and Chargers - Various | 123.543 | 89.1301 | (29.9%-20%) | -27.85% | -27.85% | 1
-27.75% | Replace Disconnect Switches - Various Sites | 1967.8 | 1421.6373 | (29.9%-20%) | -27.75% | -27.75% | 1
-27.61% | Upgrade Station Lighting - Various (2021) | 278.9 | 201.905 | (29.9%-20%) | -27.61% | -27.61% | 1
-27.51% | Install Remote Operation of Salmon Spillway - Bay d'Espoir | 2508.4 | 1818.4012 | (29.9%-20%) | -27.51% | -27.51% | 1
-27.51% | Replace Main Fuel Valves - Hardwoods | 404.2 | 293.0207 | (29.9%-20%) | -27.51% | -27.51% | 1
-27.39% | Replace Circuit Breaker Reclosing Controllers (2024–2025) - TL247 | 328.2 | 238.2979 | (29.9%-20%) | -27.39% | -27.39% | 1
-27.3% | Upgrade Public Safety Around Dams and Waterways - Bay d'Espoir | 489 | 355.4848 | (29.9%-20%) | -27.3% | -27.3% | 1
-27.23% | Replace Fire Supression System - Happy Valley Gas Turbine | 2642.45 | 1923.0097 | (29.9%-20%) | -27.23% | -27.23% | 1
-27% | Replace Surge Arrestors - Various (2019) | 163.6 | 119.4258 | (29.9%-20%) | -27% | -27% | 1
-26.81% | Replace Battery Banks and Chargers - Various Sites | 881.6 | 645.2465 | (29.9%-20%) | -26.81% | -26.81% | 1
-26.65% | Control System Replacement - Holyrood Gas Turbine | 262.1713 | 192.3079 | (29.9%-20%) | -26.65% | -26.65% | 1
-26.33% | Purchase Office Equipment Less Than $50,000 (2023) | 75.6 | 55.6933 | (29.9%-20%) | -26.33% | -26.33% | 1
-26.22% | Replace Drainage Pumps - HLK, PRV | 774 | 571.0445 | (29.9%-20%) | -26.22% | -26.22% | 1
-26.05% | Purchase Meters and Metering Equipment - Various | 244.214 | 180.6076 | (29.9%-20%) | -26.05% | -26.05% | 1
-25.52% | Refurbish Control Building - WAV (2020) | 333.7298 | 248.5773 | (29.9%-20%) | -25.52% | -25.52% | 1
-25.25% | Install Level 2 Chargers for Electric Vehicles | 478.005 | 357.2934 | (29.9%-20%) | -25.25% | -25.25% | 1
-24.8% | Purchase SF6 Multi Analyzer - Various | 207.049 | 155.7007 | (29.9%-20%) | -24.8% | -24.8% | 1
-24.48% | Upgrade Hydro ECC Wall Infrastructure - Hydro Place | 188.476 | 142.3349 | (29.9%-20%) | -24.48% | -24.48% | 1
-24.46% | Perform Minor Enhancements - Hydro Place | 372.1 | 281.1013 | (29.9%-20%) | -24.46% | -24.46% | 1
-24.25% | Building Vestibule Powerhouse - Holyrood | 49.3 | 37.3438 | (29.9%-20%) | -24.25% | -24.25% | 1
-23.9% | Refurbish Sump Level System for Powerhouse 2 - Bay d'Espoir | 303.2 | 230.7473 | (29.9%-20%) | -23.9% | -23.9% | 1
-23.82% | Upgrade Station Lighting - HRD | 414.833 | 316.0256 | (29.9%-20%) | -23.82% | -23.82% | 1
-23.44% | Diesel Plant Ventilation Upgrade - Nain | 853.076 | 653.1224 | (29.9%-20%) | -23.44% | -23.44% | 1
-23.07% | Upgrade Distributed Control System Hardware - Holyrood | 1122.6141 | 863.5919 | (29.9%-20%) | -23.07% | -23.07% | 1
-22.91% | Upgrade Transformer Paralleling - WAV | 301.8 | 232.6507 | (29.9%-20%) | -22.91% | -22.91% | 1
-22.84% | Upgrade Diesel Plant Building - Ramea | 352.5 | 272.0043 | (29.9%-20%) | -22.84% | -22.84% | 1
-22.74% | Install Fire Protection in 230 kV Stations (2024–2025) - Voisey's Bay | 652.8 | 504.362 | (29.9%-20%) | -22.74% | -22.74% | 1
-22.74% | Replace Surge Arrestors - Various (2020) | 132.28 | 102.2014 | (29.9%-20%) | -22.74% | -22.74% | 1
-22.72% | Overhaul Diesel Engines - Various Sites | 2095.9 | 1619.7798 | (29.9%-20%) | -22.72% | -22.72% | 1
-22.6% | Install Fire Protection in 230 kV Stations - Bay d'Espoir | 766 | 592.8697 | (29.9%-20%) | -22.6% | -22.6% | 1
-22.43% | Refurbish Unit 6 Generator Stator - BDE | 9160.879 | 7106.4588 | (29.9%-20%) | -22.43% | -22.43% | 1
-21.84% | Upgrade Terminal Station Equipment Foundations - Various Sites | 367 | 286.8618 | (29.9%-20%) | -21.84% | -21.84% | 1
-21.42% | Install Fire Protection in Diesel Plants (2022-2023) - Ramea | 1928.8 | 1515.6301 | (29.9%-20%) | -21.42% | -21.42% | 1
-20.98% | Purchase Backup Diesel For Station Service - Grand Falls and Buchans | 188.9 | 149.274 | (29.9%-20%) | -20.98% | -20.98% | 1
-20.92% | Install Recloser Remote Control - English Harbour West and Barachoix | 338.7 | 267.8528 | (29.9%-20%) | -20.92% | -20.92% | 1
-20.84% | Upgrade Terminal Station Equipment Foundations - Various (2019) | 306.2 | 242.3876 | (29.9%-20%) | -20.84% | -20.84% | 1
-20.81% | Perform Software Upgrades and Minor Enhancements (2023) | 451.2 | 357.3164 | (29.9%-20%) | -20.81% | -20.81% | 1
-20.68% | Install Fire Protection in 230 kV Stations - BUC (2022-23) | 492.8023 | 390.8944 | (29.9%-20%) | -20.68% | -20.68% | 1
-20.59% | Perform Software Upgrades and Minor Enhancements - Hydro Place | 621.7 | 493.687 | (29.9%-20%) | -20.59% | -20.59% | 1
-20.23% | Diesel Genset Replacement Unit 2039 - St. Lewis | 1980.8 | 1580.0628 | (29.9%-20%) | -20.23% | -20.23% | 1
-20.23% | Replace Instrument Transformers - Various (2019-20) | 1100.1 | 877.5705 | (29.9%-20%) | -20.23% | -20.23% | 1
-20.15% | Install Fire Detection in Outbuildings - Holyrood | 198.6 | 158.5842 | (29.9%-20%) | -20.15% | -20.15% | 1
-20.09% | Upgrade Terminal Station for Mobile Substation - Cow Head | 484.7 | 387.3143 | (29.9%-20%) | -20.09% | -20.09% | 1
-20.03% | Refurbish Hydraulic Structures - Burnt Dam (2022-23) | 3756.277 | 3003.7782 | (29.9%-20%) | -20.03% | -20.03% | 1
-19.91% | Install Frequency Monitors - Various Sites | 157.8 | 126.3804 | (19.9%-10%) | -19.91% | -19.91% | 1
-19.76% | Purchase Capital Spares - Terminal Stations | 495.8 | 397.8449 | (19.9%-10%) | -19.76% | -19.76% | 1
-19.63% | Install CCTV Systems (2025) | 440.1 | 353.6907 | (19.9%-10%) | -19.63% | -19.63% | 1
-19.04% | Upgrade Office Facilities and Control Buildings - Various | 1180.6 | 955.8677 | (19.9%-10%) | -19.04% | -19.04% | 1
-18.9% | Purchase Tools and Equipment Less than $50,000 (2022) - Hydraulic Plants | 187.3 | 151.9023 | (19.9%-10%) | -18.9% | -18.9% | 1
-18.88% | Replace Disconnect Switches - Various (2022-23) | 1235.7013 | 1002.3861 | (19.9%-10%) | -18.88% | -18.88% | 1
-18.46% | Overhaul Unit 3 Turbine Valve - Holyrood | 3290.5 | 2682.9733 | (19.9%-10%) | -18.46% | -18.46% | 1
-18.44% | Line Depot Condition Assessment and Refurbishment - Various | 1233 | 1005.6007 | (19.9%-10%) | -18.44% | -18.44% | 1
-18.43% | Perform Level 2 Condition Assessment - Powerhouse Slope (2025) - Cat Arm | 169.4 | 138.1864 | (19.9%-10%) | -18.43% | -18.43% | 1
-18.27% | Replace Battery Banks and Chargers - Various Sites (2017-2018) | 945.5 | 772.7428 | (19.9%-10%) | -18.27% | -18.27% | 1
-18.17% | Install Demand Metering - Various Sites | 89.7 | 73.4013 | (19.9%-10%) | -18.17% | -18.17% | 1
-18.02% | Purchase Tools and Equipment Less than $ 50,000 - HRD GT | 45.6 | 37.3845 | (19.9%-10%) | -18.02% | -18.02% | 1
-17.88% | Replace Condition Monitoring Equipment - BDE (2019) | 382.7 | 314.2607 | (19.9%-10%) | -17.88% | -17.88% | 1
-17.8% | Perform Grounding Upgrades - Various Sites (2021-22) | 2107.3 | 1732.1113 | (19.9%-10%) | -17.8% | -17.8% | 1
-17.76% | Replace Control Cable PH1 - BDE | 515.1 | 423.6075 | (19.9%-10%) | -17.76% | -17.76% | 1
-17.69% | Makkovik Diesel Generating Station Roof Replacement - Supplemental | 891.6241 | 733.8948 | (19.9%-10%) | -17.69% | -17.69% | 1
-17.67% | Upgrade Telecontrol Facilities - Mary March Hill and Blue Grass Hill | 757.1 | 623.2868 | (19.9%-10%) | -17.67% | -17.67% | 1
-17.57% | Replace Powerhouse Lighting - Paradise River | 43.9 | 36.1856 | (19.9%-10%) | -17.57% | -17.57% | 1
-17.39% | Upgrade Office Facilities & Control Buildings - Various Sites | 2197.3 | 1815.2033 | (19.9%-10%) | -17.39% | -17.39% | 1
-17.27% | Replace Voltage Regulator - Happy Valley Gas Turbine | 342.3 | 283.1753 | (19.9%-10%) | -17.27% | -17.27% | 1
-17.17% | Install Fall Protection Equipment - Various Sites | 194.7 | 161.2649 | (19.9%-10%) | -17.17% | -17.17% | 1
-17.13% | Install Fire Protection Systems - Cartwright and Nain | 4407.1 | 3652.201 | (19.9%-10%) | -17.13% | -17.13% | 1
-16.97% | Upgrade Wastewater Treatment Plant 600 V Variable Frequency Drives - Holyrood | 70.1 | 58.2025 | (19.9%-10%) | -16.97% | -16.97% | 1
-16.83% | Distribution Upgrades - Various Sites | 1195.1 | 994.0176 | (19.9%-10%) | -16.83% | -16.83% | 1
-16.82% | Replace Coolers - Hinds Lake | 516.8 | 429.8845 | (19.9%-10%) | -16.82% | -16.82% | 1
-16.81% | Construct Storage Building - Makkovik and Charelottetown | 639.7 | 532.1648 | (19.9%-10%) | -16.81% | -16.81% | 1
-16.78% | Overhaul Diesel Units - Various | 2310.915 | 1923.2427 | (19.9%-10%) | -16.78% | -16.78% | 1
-16.58% | Remove Safety Hazards - Various | 199.4 | 166.3368 | (19.9%-10%) | -16.58% | -16.58% | 1
-16.43% | Upgrade Work Protection Code Application (2025-2026) | 708.64 | 592.214 | (19.9%-10%) | -16.43% | -16.43% | 1
-16.11% | Gas Turbine Equipment Replacement and Refurbishment - Hardwoods and Stephenville | 1427.2 | 1197.2788 | (19.9%-10%) | -16.11% | -16.11% | 1
-15.8% | TL 227 Distribution Line Sally's Cove L1 | 2250 | 1894.4776 | (19.9%-10%) | -15.8% | -15.8% | 1
-15% | Purchase Tools and Equipment less than $50,000 | 40 | 34.0015 | (19.9%-10%) | -15% | -15% | 1
-14.94% | Replace Battery Banks and Chargers (2022) - Various | 226.6 | 192.7347 | (19.9%-10%) | -14.94% | -14.94% | 1
-14.92% | Install Partial Discharge Monitoring - Holyrood Gas Turbine | 612.755 | 521.333 | (19.9%-10%) | -14.92% | -14.92% | 1
-14.71% | Purchase Capital Spares - Gas Turbines | 626.9 | 534.6717 | (19.9%-10%) | -14.71% | -14.71% | 1
-14.56% | Unit 3 Electrical Testing - Holyrood | 39.1131 | 33.4188 | (19.9%-10%) | -14.56% | -14.56% | 1
-14.54% | Remove Safety Hazards (2022) - Various | 199.6 | 170.5701 | (19.9%-10%) | -14.54% | -14.54% | 1
-14.23% | Install Fall Protection Equipment - Various | 46.7 | 40.0556 | (19.9%-10%) | -14.23% | -14.23% | 1
-14.21% | Install Fire Protection - Various Sites | 926.7 | 794.994 | (19.9%-10%) | -14.21% | -14.21% | 1
-14.21% | Overhaul Diesel Units - Various | 2511.3 | 2154.4067 | (19.9%-10%) | -14.21% | -14.21% | 1
-14.09% | Replace Fuel Piping - Hardwoods and Stephenville | 311.8 | 267.8725 | (19.9%-10%) | -14.09% | -14.09% | 1
-14.07% | Holyrood Tank Farm Underground Firewater System Replacment - Supplemental | 1469.6289 | 1262.9116 | (19.9%-10%) | -14.07% | -14.07% | 1
-13.63% | Replace Human Machine Interface - St. Lewis | 280.8 | 242.5202 | (19.9%-10%) | -13.63% | -13.63% | 1
-13.5% | Level II Condition Assessment - SRS | 556.808 | 481.6585 | (19.9%-10%) | -13.5% | -13.5% | 1
-13.12% | Purchase Tools and Equipment Less than $ 50,000 | 194.3 | 168.8137 | (19.9%-10%) | -13.12% | -13.12% | 1
-13.03% | Install Fire Protection in 230 kV Stations (2023-2024) - Deer Lake | 614.5 | 534.4027 | (19.9%-10%) | -13.03% | -13.03% | 1
-13.01% | Upgrade Exterior of Building - Hydro Place | 665.9 | 579.2426 | (19.9%-10%) | -13.01% | -13.01% | 1
-12.92% | Upgrade Powerhouse Building Envelope - Holyrood | 6477.8 | 5640.8877 | (19.9%-10%) | -12.92% | -12.92% | 1
-12.89% | Three Phase Construction - Bishop's Falls | 49.6 | 43.2043 | (19.9%-10%) | -12.89% | -12.89% | 1
-12.89% | Energy Efficiency Improvements - Various Sites | 445.1 | 387.7348 | (19.9%-10%) | -12.89% | -12.89% | 1
-12.86% | Purchase Capital Spares - Gas Turbines | 185 | 161.2058 | (19.9%-10%) | -12.86% | -12.86% | 1
-12.8% | Public Safety Dams/Waterways - Bay d'Espoir | 394.7 | 344.1715 | (19.9%-10%) | -12.8% | -12.8% | 1
-12.74% | Upgrade Public Safety Around Dams and Waterways - BDE | 436.28 | 380.6985 | (19.9%-10%) | -12.74% | -12.74% | 1
-12.58% | Diesel Genset Replacement Program (2023-2025) | 543 | 474.6987 | (19.9%-10%) | -12.58% | -12.58% | 1
-12.5% | Parking Lot Access Improvements - Hydro Place | 47.4 | 41.4768 | (19.9%-10%) | -12.5% | -12.5% | 1
-12.49% | Thermal In-Service Failures (2023) | 3300 | 2887.8278 | (19.9%-10%) | -12.49% | -12.49% | 1
-12.05% | Replace Protective Relays - Various Sites (2021-22) | 2007 | 1765.0953 | (19.9%-10%) | -12.05% | -12.05% | 1
-11.91% | Replace Surge Arresters - Various (2021) | 61.649 | 54.3044 | (19.9%-10%) | -11.91% | -11.91% | 1
-11.91% | Control Structure Refurbishments | 2188.2 | 1927.5433 | (19.9%-10%) | -11.91% | -11.91% | 1
-11.83% | Install L-1 Blades Unit 1 (2024) Holyrood | 581.263 | 512.496 | (19.9%-10%) | -11.83% | -11.83% | 1
-11.81% | Turbine Hot Gas Path Level 2 Inspection and Overhaul - Holyrood Gas Turbine | 11146.5 | 9829.5611 | (19.9%-10%) | -11.81% | -11.81% | 1
-11.75% | Replace TS Battery Banks and Chargers - Various | 354.8 | 313.0977 | (19.9%-10%) | -11.75% | -11.75% | 1
-11.48% | Install Breaker Failure Protection - Various Sites | 622.9 | 551.4077 | (19.9%-10%) | -11.48% | -11.48% | 1
-11.31% | Replace Surge Arrestors - Various Sites | 197.4 | 175.0706 | (19.9%-10%) | -11.31% | -11.31% | 1
-11.24% | Purchase 85' Material Handler Aerial Device on Track Unit | 1353.9 | 1201.724 | (19.9%-10%) | -11.24% | -11.24% | 1
-11.13% | Additions for Load Growth - L'anse au Loup | 4175.6 | 3710.7617 | (19.9%-10%) | -11.13% | -11.13% | 1
-10.55% | Overhaul Diesel Units (2022) - Various | 1360.5 | 1216.9338 | (19.9%-10%) | -10.55% | -10.55% | 1
-10.48% | Upgrade Remote Terminal Units (2022) - Various | 171.1 | 153.1715 | (19.9%-10%) | -10.48% | -10.48% | 1
-10.43% | Purchase Meters and Metering Equipment (2023) | 226.6 | 202.9578 | (19.9%-10%) | -10.43% | -10.43% | 1
-10.42% | Overhaul Turbine/Generator Unit - GCL | 562.2 | 503.6457 | (19.9%-10%) | -10.42% | -10.42% | 1
-10.3% | Overhaul Diesel Units (2023) | 1502 | 1347.2625 | (19.9%-10%) | -10.3% | -10.3% | 1
-10.17% | Upgrade Sump Level System Powerhouse 1 - BDE | 131.6 | 118.2189 | (19.9%-10%) | -10.17% | -10.17% | 1
-10.09% | Upgrade Terminal Station Foundations - BCX/LLK | 614.5 | 552.4733 | (19.9%-10%) | -10.09% | -10.09% | 1
-9.83% | Wood Pole Line Management Program - Various Sites | 3532.9 | 3185.6229 | (9.9%-0.01%) | -9.83% | -9.83% | 1
-9.603% | Refurbish Main Generator Breaker - Upper Salmon | 271.1 | 245.0667 | (9.9%-0.01%) | -9.603% | -9.603% | 1
-9.573% | Overhaul Unit 1 Turbine Valves - Holyrood | 2485.7 | 2247.747 | (9.9%-0.01%) | -9.573% | -9.573% | 1
-9.555% | Diesel Genset Replacements - Mary's Harbour | 3900.714 | 3527.9937 | (9.9%-0.01%) | -9.555% | -9.555% | 1
-9.398% | Purchase Surveying Software and Equipment (2025) | 316.4 | 286.6651 | (9.9%-0.01%) | -9.398% | -9.398% | 1
-9.321% | Upgrade Cranes and Hoists - Holyrood | 380.6 | 345.1238 | (9.9%-0.01%) | -9.321% | -9.321% | 1
-9.276% | Purchase Meters and Metering Equipment - Various | 196.4 | 178.181 | (9.9%-0.01%) | -9.276% | -9.276% | 1
-9.121% | Install Automated Meter Reading - Happy Valley | 1970.2 | 1790.4916 | (9.9%-0.01%) | -9.121% | -9.121% | 1
-9.102% | Refurbish Powerhouse Station Services - Bay d'Espoir | 4347.1 | 3951.4134 | (9.9%-0.01%) | -9.102% | -9.102% | 1
-9.056% | Upgrade Line Depots - Roddickton | 344.7 | 313.4826 | (9.9%-0.01%) | -9.056% | -9.056% | 1
-9.013% | Replace Light-Duty Mobile Equipment (2022) - Various | 775.2853 | 705.4096 | (9.9%-0.01%) | -9.013% | -9.013% | 1
-8.974% | Purchase Tools and Equipment Less than $50,000 (2023) - Gas Turbine | 18.3 | 16.6577 | (9.9%-0.01%) | -8.974% | -8.974% | 1
-8.926% | Replace Powerline Carrier - Various Sites | 836.8 | 762.11 | (9.9%-0.01%) | -8.926% | -8.926% | 1
-8.439% | Upgrade HVAC Supervisory Controllers (2024) - Hydro Place | 149.6 | 136.9756 | (9.9%-0.01%) | -8.439% | -8.439% | 1
-8.356% | Overhaul Marine Terminal Loading Arms (2024) - Holyrood | 511 | 468.3003 | (9.9%-0.01%) | -8.356% | -8.356% | 1
-8.271% | Replace RTUs - Various | 118.3 | 108.5157 | (9.9%-0.01%) | -8.271% | -8.271% | 1
-8.248% | Replace Automation Equipment - Mary's Harbour | 1142 | 1047.8081 | (9.9%-0.01%) | -8.248% | -8.248% | 1
-8.204% | BDE-Replace Annunciators | 384.9684 | 353.3838 | (9.9%-0.01%) | -8.204% | -8.204% | 1
-8.173% | Replace Power Line Carrier (2023–2024) - TL223 and TL224 | 957.7 | 879.4252 | (9.9%-0.01%) | -8.173% | -8.173% | 1
-8.168% | Thermal In-Service Failures | 2000.042 | 1836.6861 | (9.9%-0.01%) | -8.168% | -8.168% | 1
-8.166% | Diesel Genset Replacements - Charlottetown | 1432.5 | 1315.5202 | (9.9%-0.01%) | -8.166% | -8.166% | 1
-8.101% | Replace Radomes - Various | 360.3 | 331.1138 | (9.9%-0.01%) | -8.101% | -8.101% | 1
-7.642% | Purchase Tools and Equipment less than $50,000 | 45.6 | 42.1151 | (9.9%-0.01%) | -7.642% | -7.642% | 1
-7.522% | Generator Overhaul - PRV | 341.906 | 316.1892 | (9.9%-0.01%) | -7.522% | -7.522% | 1
-7.366% | Replace SONET Multiplexors (2024) | 430.4 | 398.6951 | (9.9%-0.01%) | -7.366% | -7.366% | 1
-7.003% | HRD - Major Overhaul: Unit 3 Cooling Water Pump West | 210.8 | 196.0386 | (9.9%-0.01%) | -7.003% | -7.003% | 1
-6.913% | Replacement of Short-Term Load Forecasting Software | 439.5 | 409.1187 | (9.9%-0.01%) | -6.913% | -6.913% | 1
-6.802% | Purchase Tools and Equipment Less than $ 50,000 | 133.5 | 124.42 | (9.9%-0.01%) | -6.802% | -6.802% | 1
-6.783% | Replace Insulators - Various (2020-21) | 243.106 | 226.6151 | (9.9%-0.01%) | -6.783% | -6.783% | 1
-6.748% | Upgrade Terminal Station Equipment Foundations - Various (2021) | 175.4 | 163.5641 | (9.9%-0.01%) | -6.748% | -6.748% | 1
-6.682% | Widen Rights-of-Way of Transmission Lines TL239 & TL259 (2024) | 668.914 | 624.2195 | (9.9%-0.01%) | -6.682% | -6.682% | 1
-6.649% | Diesel Plant Engine Auxiliary Upgrades - Various Sites | 1206.9 | 1126.6529 | (9.9%-0.01%) | -6.649% | -6.649% | 1
-6.441% | Perform Combustor Inspection - Holyrood Gas Turbine | 5473.5432 | 5120.9907 | (9.9%-0.01%) | -6.441% | -6.441% | 1
-6.419% | Hampden New Line from TS | 443.8 | 415.3142 | (9.9%-0.01%) | -6.419% | -6.419% | 1
-6.389% | Remove Safety Hazards - Various Sites | 198.6 | 185.9109 | (9.9%-0.01%) | -6.389% | -6.389% | 1
-6.327% | Upgrade Data Alarm Management - Sunnyside | 611.4 | 572.7145 | (9.9%-0.01%) | -6.327% | -6.327% | 1
-6.084% | Purchase Capital Spares - Holyrood Gas Turbine | 213.8 | 200.7921 | (9.9%-0.01%) | -6.084% | -6.084% | 1
-5.344% | Inspect Fuel Tanks (2025) - Holyrood | 608 | 575.507 | (9.9%-0.01%) | -5.344% | -5.344% | 1
-5.204% | Refurbish Control Building - HRD, CBC | 650.3 | 616.4578 | (9.9%-0.01%) | -5.204% | -5.204% | 1
-5.196% | Replace Aircraft Markers at Grand Lake Crossing - TL228 | 1567.9 | 1486.4391 | (9.9%-0.01%) | -5.196% | -5.196% | 1
-4.937% | Refurbish Station Water System - Upper Salmon | 294.2 | 279.6762 | (9.9%-0.01%) | -4.937% | -4.937% | 1
-4.891% | Main Breaker Replacement-HYP | 18.4 | 17.5 | (9.9%-0.01%) | -4.891% | -4.891% | 1
-4.797% | Replace Network Communications Equipment - Various | 189.5 | 180.4093 | (9.9%-0.01%) | -4.797% | -4.797% | 1
-4.718% | Replace Teleprotection - TL261 | 517.4 | 492.987 | (9.9%-0.01%) | -4.718% | -4.718% | 1
-4.716% | Replace 48 V Battery Banks and Chargers (2023) | 439.7 | 418.9626 | (9.9%-0.01%) | -4.716% | -4.716% | 1
-4.434% | Upgrade Site Facilities - Various | 49 | 46.8273 | (9.9%-0.01%) | -4.434% | -4.434% | 1
-4.028% | Major Condition Assessment and Miscellaneous Refurbishments Synchronous Condenser 1 and 2 (2023-2024) - Wabush Terminal Station | 1093.3 | 1049.263 | (9.9%-0.01%) | -4.028% | -4.028% | 1
-3.929% | Replace Radomes - Various | 263.5 | 253.1481 | (9.9%-0.01%) | -3.929% | -3.929% | 1
-3.878% | Replace Powerhouse #2 Lighting - Bay d'Espoir | 48 | 46.1384 | (9.9%-0.01%) | -3.878% | -3.878% | 1
-3.757% | Replace Instrument Transformers - Various Sites | 3668 | 3530.2062 | (9.9%-0.01%) | -3.757% | -3.757% | 1
-3.703% | Replace Battery Banks and Chargers - Various | 937.9 | 903.1731 | (9.9%-0.01%) | -3.703% | -3.703% | 1
-3.689% | Overhaul Olympus Gas Generator - Stephenville | 1666.8 | 1605.3137 | (9.9%-0.01%) | -3.689% | -3.689% | 1
-3.533% | Replace Radomes - Various | 240.4 | 231.9067 | (9.9%-0.01%) | -3.533% | -3.533% | 1
-3.463% | Reburbish Hydraulic Structures VAR | 5368.415 | 5182.5133 | (9.9%-0.01%) | -3.463% | -3.463% | 1
-3.432% | Upgrade Distribution Systems - Various Sites | 6635.9 | 6408.156 | (9.9%-0.01%) | -3.432% | -3.432% | 1
-3.326% | Replace Transformer T1 - Buchans | 2335.1 | 2257.4354 | (9.9%-0.01%) | -3.326% | -3.326% | 1
-3.144% | Install Line Monitoring System (2024) - TL201 | 469.902 | 455.1293 | (9.9%-0.01%) | -3.144% | -3.144% | 1
-2.886% | Refresh Cyber Security Infrastructure - Hydro Place | 217.494 | 211.2176 | (9.9%-0.01%) | -2.886% | -2.886% | 1
-2.792% | Replace Floor Annunciator Panels - Bay d'Espoir | 46.8 | 45.4934 | (9.9%-0.01%) | -2.792% | -2.792% | 1
-2.683% | Install Energy Efficiency Lighting in Diesel Plants - Various | 345.2 | 335.9397 | (9.9%-0.01%) | -2.683% | -2.683% | 1
-2.682% | Rplc Sump Pump-Upper Salmon | 407.153 | 396.2344 | (9.9%-0.01%) | -2.682% | -2.682% | 1
-2.607% | Additions for Load - Distribution System - Makkovik and Hopedale | 846.113 | 824.0509 | (9.9%-0.01%) | -2.607% | -2.607% | 1
-2.587% | Refurbish Gas Generator Engines - Hardwoods and Stephenville | 3047.1 | 2968.2856 | (9.9%-0.01%) | -2.587% | -2.587% | 1
-2.513% | Penstock Level 2 Condition Assessment - CAT | 261.216 | 254.6524 | (9.9%-0.01%) | -2.513% | -2.513% | 1
-2.44% | Refurbish Workshop Roof (2023) - Holyrood | 243.7 | 237.7527 | (9.9%-0.01%) | -2.44% | -2.44% | 1
-2.254% | Purchase 46' Material Handler Aerial Device on Track Unit | 758 | 740.9146 | (9.9%-0.01%) | -2.254% | -2.254% | 1
-2.189% | Hydro - Mobile Devices | 48.2 | 47.1449 | (9.9%-0.01%) | -2.189% | -2.189% | 1
-2.091% | Purchase Meters and Metering Equipment - Various | 233.4 | 228.5207 | (9.9%-0.01%) | -2.091% | -2.091% | 1
-2.077% | Purchase Tools and Equipment Less than $50,000 (2022) - Thermal Plants | 18.9 | 18.5074 | (9.9%-0.01%) | -2.077% | -2.077% | 1
-2.038% | Replace MDR8000 Microwave Radios (2024-2025) | 1453.8 | 1424.1702 | (9.9%-0.01%) | -2.038% | -2.038% | 1
-1.99% | Upgrade Core IT Infrastructure - Hydro Place | 262.776 | 257.5458 | (9.9%-0.01%) | -1.99% | -1.99% | 1
-1.933% | HRD - Major Overhaul Unit 2 Boiler Feed Pump West | 279.3 | 273.901 | (9.9%-0.01%) | -1.933% | -1.933% | 1
-1.744% | Supply & Install Replacement Waterline - St. Anthony | 47.4 | 46.5735 | (9.9%-0.01%) | -1.744% | -1.744% | 1
-1.66% | 230 kV Transmission Line - Bay d'Espoir to Western Avalon | 291658 | 286817.7549 | (9.9%-0.01%) | -1.66% | -1.66% | 1
-1.625% | Replace Mobile Devices | 49.7 | 48.8921 | (9.9%-0.01%) | -1.625% | -1.625% | 1
-1.599% | Upgrade Remote Terminal Units - Various | 167.7 | 165.0186 | (9.9%-0.01%) | -1.599% | -1.599% | 1
-1.389% | Upgrade Power Transformers - Various (2020-21) | 1245.723 | 1228.4232 | (9.9%-0.01%) | -1.389% | -1.389% | 1
-1.372% | Replace MDR 4000 Microwave Radio East - Various Sites | 1170.5 | 1154.4371 | (9.9%-0.01%) | -1.372% | -1.372% | 1
-1.215% | Valentine Gold Interconnection - Supplemental | 16347.4 | 16148.7257 | (9.9%-0.01%) | -1.215% | -1.215% | 1
-1.191% | Purchase Tools and Equipment Less than $ 50,000 | 113.4 | 112.0489 | (9.9%-0.01%) | -1.191% | -1.191% | 1
-1.161% | Upgrade Site Facilities - Various | 48.943 | 48.375 | (9.9%-0.01%) | -1.161% | -1.161% | 1
-0.7011% | Addition for Load Growth - Happy Valley L7 | 617.6 | 613.2703 | (9.9%-0.01%) | -0.7011% | -0.7011% | 1
-0.6751% | Update Cyber Security Infrastructure (2023) | 232.1 | 230.5331 | (9.9%-0.01%) | -0.6751% | -0.6751% | 1
-0.6699% | Upgrade Remote Terminal Units - Various | 157.054 | 156.0019 | (9.9%-0.01%) | -0.6699% | -0.6699% | 1
-0.6237% | Replace Rotary Strainer - USL | 239.9966 | 238.4998 | (9.9%-0.01%) | -0.6237% | -0.6237% | 1
-0.3376% | Purchase SF6 Reclaim Units - Various | 142.722 | 142.2401 | (9.9%-0.01%) | -0.3376% | -0.3376% | 1
-0.1333% | Replace Human Machine Interface - Cartwright | 306.9 | 306.491 | (9.9%-0.01%) | -0.1333% | -0.1333% | 1
-0.03447% | Replace Fuel Oil, Lube Oil, and Glycol Pumps - Happy Valley Gas Turbine | 405.2 | 405.0603 | (9.9%-0.01%) | -0.03447% | -0.03447% | 1
-0.00239% | Upgrade Transformer Systems - Postville and Cartwright | 465.2 | 465.1889 | (9.9%-0.01%) | -0.00239% | -0.00239% | 1
0.02493% | Upgrade Core IT/OT Infrastructure (2022) - Hydro Place | 308.2 | 308.2768 | 0%-9.9% | 0.02493% | 0.02493% | 1
0.1458% | Refurbish Access Road to Ebbegunbaeg | 803.142 | 804.3129 | 0%-9.9% | 0.1458% | 0.1458% | 1
0.2933% | Replace Control Cables BDE | 311.291 | 312.2041 | 0%-9.9% | 0.2933% | 0.2933% | 1
0.5506% | Construct 230 kV Transmission Line - Soldiers Pond to Hardwoods | 26560.9 | 26707.1371 | 0%-9.9% | 0.5506% | 0.5506% | 1
0.5778% | Replace Roof on Service Building - Bishop's Falls | 612.8 | 616.3406 | 0%-9.9% | 0.5778% | 0.5778% | 1
0.6975% | Replace Powerhouse 1 Air Conditioning Unit (2024-2025) - Bay d'Espoir | 289 | 291.0157 | 0%-9.9% | 0.6975% | 0.6975% | 1
1.096% | Install Wind Monitoring Station North Salmon Dam SD-2 - Bay d'Espoir | 165.5 | 167.3131 | 0%-9.9% | 1.096% | 1.096% | 1
1.246% | Replace Protective Relays - Various Sites | 1816.7 | 1839.3336 | 0%-9.9% | 1.246% | 1.246% | 1
1.424% | Upgrade Site Facilities (2022) - Various | 49.6 | 50.3063 | 0%-9.9% | 1.424% | 1.424% | 1
1.437% | Replace Air Conditioners - Various | 74.4 | 75.4694 | 0%-9.9% | 1.437% | 1.437% | 1
1.538% | Replace Washroom Fixtures - Hydro Place | 49.5 | 50.2615 | 0%-9.9% | 1.538% | 1.538% | 1
1.732% | Upgrade Site Facilities - Various | 49.4 | 50.2554 | 0%-9.9% | 1.732% | 1.732% | 1
1.865% | Upgrade Site Facilities | 49 | 49.9137 | 0%-9.9% | 1.865% | 1.865% | 1
1.884% | Upgrade Site Facilities - Various | 45.522 | 46.3798 | 0%-9.9% | 1.884% | 1.884% | 1
2.005% | Purchase Tools and Equipment less than $50,000 | 26 | 26.5213 | 0%-9.9% | 2.005% | 2.005% | 1
2.048% | Distribution System Upgrades - Various Sites | 3155 | 3219.6105 | 0%-9.9% | 2.048% | 2.048% | 1
2.195% | Purchase Tools and Equipment Less than $50,000 (2022) - Gas Turbine | 19.6 | 20.0301 | 0%-9.9% | 2.195% | 2.195% | 1
2.233% | Refurbish Intake 1 (2024-2025) - Bay d'Espoir | 3344 | 3418.668 | 0%-9.9% | 2.233% | 2.233% | 1
2.245% | Replace Control Room/Communications Room Air Conditioning - Hinds Lake | 94.3 | 96.4168 | 0%-9.9% | 2.245% | 2.245% | 1
2.272% | Replace Air Conditioners - Various Sites | 191.9 | 196.2608 | 0%-9.9% | 2.272% | 2.272% | 1
2.31% | Upgrade Access Roads to Microwave Sites - Various Sites | 118.4 | 121.1352 | 0%-9.9% | 2.31% | 2.31% | 1
2.345% | IOC SCADA Data Link | 28.218 | 28.8798 | 0%-9.9% | 2.345% | 2.345% | 1
2.349% | Wood Pole Line Management Program - Various Sites | 2896.9 | 2964.946 | 0%-9.9% | 2.349% | 2.349% | 1
2.481% | Refurbish Turbine Unit 7 - BDE | 4179 | 4282.6782 | 0%-9.9% | 2.481% | 2.481% | 1
2.57% | Purchase Office Equipment Less Than $50,000 (2022) | 67.1 | 68.8243 | 0%-9.9% | 2.57% | 2.57% | 1
2.671% | Replace MDR 6000 Microwave Radio - Various | 1201 | 1233.0772 | 0%-9.9% | 2.671% | 2.671% | 1
2.827% | Replace Station Service Breakers - Cat Arm | 1008.3 | 1036.8004 | 0%-9.9% | 2.827% | 2.827% | 1
2.847% | Upgrade Diesel Plant Production Data Collection Equipment-Various | 819.4 | 842.7319 | 0%-9.9% | 2.847% | 2.847% | 1
2.979% | Hydraulic In-Service Failures | 1250 | 1287.2367 | 0%-9.9% | 2.979% | 2.979% | 1
3.219% | Wood Pole Line Management Program - Various Sites | 2792.724 | 2882.6142 | 0%-9.9% | 3.219% | 3.219% | 1
3.505% | Replace Network Communications Equipment - Various | 186.797 | 193.3442 | 0%-9.9% | 3.505% | 3.505% | 1
3.505% | Purchase Tools and Equipment Less than $50,000 (2023) - Hydraulic Plants | 144.9 | 149.9791 | 0%-9.9% | 3.505% | 3.505% | 1
3.572% | Diesel Plant Fire Protection - Postville | 842 | 872.0761 | 0%-9.9% | 3.572% | 3.572% | 1
3.603% | Holyrood Upgrade Turbine Control System Unit 2 - Supplemental | 726 | 752.1551 | 0%-9.9% | 3.603% | 3.603% | 1
3.951% | Stage 1 Pumphouse Siding Replacement - Holyrood | 49.9 | 51.8717 | 0%-9.9% | 3.951% | 3.951% | 1
3.962% | Upgrade Ventilation - Cartwright | 465.7 | 484.1515 | 0%-9.9% | 3.962% | 3.962% | 1
4.125% | Holyrood Thermal Generating Station Unit 1 and Unit 2 Turbine Last Stage Blades - Supplemental | 6408.7 | 6673.0654 | 0%-9.9% | 4.125% | 4.125% | 1
4.232% | Upgrade Site Facilities (2023) | 45.2 | 47.1129 | 0%-9.9% | 4.232% | 4.232% | 1
4.331% | Replace Grader Unit V9829 (2024) - Bay d'Espoir | 836.7 | 872.9393 | 0%-9.9% | 4.331% | 4.331% | 1
4.457% | Remove Safety Hazards (2023) | 198.2 | 207.0342 | 0%-9.9% | 4.457% | 4.457% | 1
4.53% | Upgrades XFMR Parallel | 176.2 | 184.1815 | 0%-9.9% | 4.53% | 4.53% | 1
4.666% | Replace Air Conditioning Units 8 and 14 - Hydro Place | 264.1 | 276.4231 | 0%-9.9% | 4.666% | 4.666% | 1
4.896% | Rewind Unit 3 Stator - Holyrood | 6945.6 | 7285.6551 | 0%-9.9% | 4.896% | 4.896% | 1
5.04% | Install Recloser Remote Control - Bottom Waters | 465.7 | 489.1726 | 0%-9.9% | 5.04% | 5.04% | 1
5.232% | Purchase Capital Spares Holyrood | 321.5 | 338.322 | 0%-9.9% | 5.232% | 5.232% | 1
5.239% | Perform Level 2 Condition Assessment - Stage I & II Cooling Water Sump Structures (2025) - Holyrood | 1747.033 | 1838.5639 | 0%-9.9% | 5.239% | 5.239% | 1
5.485% | Diesel Genset Replacements (2019-2020) | 3947.4 | 4163.9017 | 0%-9.9% | 5.485% | 5.485% | 1
5.53% | Overhaul Unit 1 Generator - Holyrood | 1005 | 1060.5755 | 0%-9.9% | 5.53% | 5.53% | 1
5.532% | Upgrade Human Machine Interface - Various Sites | 434 | 458.0087 | 0%-9.9% | 5.532% | 5.532% | 1
6.207% | Distribution System Upgrades - Various Sites | 5880.9 | 6245.9032 | 0%-9.9% | 6.207% | 6.207% | 1
6.264% | Replace 258VDC Battery Banks - Holyrood | 330 | 350.6723 | 0%-9.9% | 6.264% | 6.264% | 1
6.335% | Purchase New Meter Calibration Test Console - Hydro Place | 196.9 | 209.3736 | 0%-9.9% | 6.335% | 6.335% | 1
6.451% | Install Breaker Failure Protection (2021-22) | 451.472 | 480.5956 | 0%-9.9% | 6.451% | 6.451% | 1
6.684% | Overhaul Unit 3 Generator - Holyrood | 572.7 | 610.9818 | 0%-9.9% | 6.684% | 6.684% | 1
6.741% | Remove Safety Hazards - Various | 197.5 | 210.8144 | 0%-9.9% | 6.741% | 6.741% | 1
7.013% | Distribution System Upgrades (2020-2021) - Various | 3257.1 | 3485.513 | 0%-9.9% | 7.013% | 7.013% | 1
7.094% | Replace Battery Banks and Chargers - Various | 327.2 | 350.4117 | 0%-9.9% | 7.094% | 7.094% | 1
7.199% | Refurbish Meteorological Stations (2025) | 167.8 | 179.8792 | 0%-9.9% | 7.199% | 7.199% | 1
7.664% | Purchase Tools and Equipment less than $50,000 | 45.2 | 48.664 | 0%-9.9% | 7.664% | 7.664% | 1
8.14% | Refurbish Outbuilding and Powerhouse Building Envelopes (2024-2025) - Holyrood | 1195.6 | 1292.9245 | 0%-9.9% | 8.14% | 8.14% | 1
8.449% | Overhaul Turbine Valves Unit 2 - Holyrood | 2302.1 | 2496.5952 | 0%-9.9% | 8.449% | 8.449% | 1
8.609% | Upgrade Remote Terminal Units - Various | 183.4 | 199.1898 | 0%-9.9% | 8.609% | 8.609% | 1
8.673% | Hydro Generation Tools & Equip | 235.2 | 255.5992 | 0%-9.9% | 8.673% | 8.673% | 1
8.689% | Upgrade Public Safety Around Dams and Waterways - BDE | 678.5 | 737.4564 | 0%-9.9% | 8.689% | 8.689% | 1
8.81% | BDE Unit 6 Replace Control Cables | 304.8 | 331.6525 | 0%-9.9% | 8.81% | 8.81% | 1
9.087% | Upgrade Telecontrol Facilities - Sandy Brook Hill | 564 | 615.2495 | 0%-9.9% | 9.087% | 9.087% | 1
9.158% | Replace Air Conditioning - BDE | 162.9 | 177.8179 | 0%-9.9% | 9.158% | 9.158% | 1
9.266% | Replace Elevator Motors and Controls Equipment - HYP | 882.8477 | 964.652 | 0%-9.9% | 9.266% | 9.266% | 1
9.367% | Replace Light Duty Mobile Equipment - Various Sites | 549.6 | 601.0809 | 0%-9.9% | 9.367% | 9.367% | 1
9.401% | Overhaul Turbine/Generators - Cat Arm | 305.4 | 334.111 | 0%-9.9% | 9.401% | 9.401% | 1
9.46% | Upgrade Digital Fault Recorders - Various Sites | 502.5 | 550.0368 | 0%-9.9% | 9.46% | 9.46% | 1
9.52% | Replace Site Facilities - Bay d'Espoir | 11981.3 | 13121.8682 | 0%-9.9% | 9.52% | 9.52% | 1
9.735% | Diesel Plant Engine Cooling System Upgrades - Various Sites | 1310 | 1437.5344 | 0%-9.9% | 9.735% | 9.735% | 1
9.809% | Install Partial Discharge Monitoring System - HLK,CAT,GCL | 451.417 | 495.6979 | 0%-9.9% | 9.809% | 9.809% | 1
9.821% | Replace T/G Cooling Water Pump and Strainer - HLK | 408.5 | 448.6202 | 0%-9.9% | 9.821% | 9.821% | 1
9.882% | Upgrade Reclosing Circuit Breakers - SSD B1L03 & HRD B1L65 (2022-23) | 210.9698 | 231.818 | 0%-9.9% | 9.882% | 9.882% | 1
9.951% | Hydraulic In-Service Failures | 1250 | 1374.3921 | 0%-9.9% | 9.951% | 9.951% | 1
9.972% | Replace UPS Systems - Hydro Place | 889.8 | 978.5309 | 0%-9.9% | 9.972% | 9.972% | 1
10% | Remove Safety Hazards - Various | 198.552 | 218.4151 | 10%-19.9% | 10% | 10% | 1
10.16% | Replace Diesel Genset 1 (2023-2024) - Ebbegunbaeg | 1026.3 | 1130.5443 | 10%-19.9% | 10.16% | 10.16% | 1
10.55% | Upgrade of Worst-Performing Distribution Feeders (2022-2023) | 2761.098 | 3052.5192 | 10%-19.9% | 10.55% | 10.55% | 1
11.05% | Install Recloser Remote Control (2020-2021) - Hampden and Upper Salmon | 256.647 | 285.012 | 10%-19.9% | 11.05% | 11.05% | 1
11.05% | Replace PBX Phone Systems - Various | 1242.3 | 1379.6253 | 10%-19.9% | 11.05% | 11.05% | 1
11.19% | Upgrade Telecontrol Facilities - Gull Pond Hill and Bay d’Espoir Hill | 673.9 | 749.3001 | 10%-19.9% | 11.19% | 11.19% | 1
11.26% | Holyrood Inspect and Refurbish Day Tank - Supplemental | 846.7719 | 942.1432 | 10%-19.9% | 11.26% | 11.26% | 1
11.33% | Generator Assessment - Happy Valley Gas Turbine | 1097.604 | 1221.9491 | 10%-19.9% | 11.33% | 11.33% | 1
11.37% | Purchase Turbine Last Stage Blades - Holyrood - Supplemental | 1432.6215 | 1595.5372 | 10%-19.9% | 11.37% | 11.37% | 1
11.62% | Overhaul Unit 4 - BDE | 225 | 251.1359 | 10%-19.9% | 11.62% | 11.62% | 1
11.7% | Upgrade Line Depots - Various | 648.3 | 724.178 | 10%-19.9% | 11.7% | 11.7% | 1
12.02% | Refurbish Fuel Oil Storage Tank 4 (2024) - Holyrood | 1920 | 2150.8605 | 10%-19.9% | 12.02% | 12.02% | 1
12.25% | Upgrade Unit 1 Control System (2024-2025) - Holyrood | 652.6 | 732.5407 | 10%-19.9% | 12.25% | 12.25% | 1
12.71% | Replace Diesel Genset-VCS | 944.028 | 1064.0392 | 10%-19.9% | 12.71% | 12.71% | 1
12.75% | Construct Maintenance Platform (2024-2025) - Holyrood Gas Turbine | 359.2 | 404.9963 | 10%-19.9% | 12.75% | 12.75% | 1
12.88% | Remove Safety Hazards - Various | 199.1 | 224.7445 | 10%-19.9% | 12.88% | 12.88% | 1
13.04% | Upgrade Waste Water Equalization System - Holyrood | 2361.1 | 2668.957 | 10%-19.9% | 13.04% | 13.04% | 1
13.4% | Replace Spherical By-Pass Valves Units 1 and 2 - Bay d'Espoir | 351.5 | 398.6093 | 10%-19.9% | 13.4% | 13.4% | 1
14.16% | Upgrade UPS 1 & 2 (2024-2025) - Holyrood | 370.6 | 423.0747 | 10%-19.9% | 14.16% | 14.16% | 1
14.38% | Replace Disconnects - Various (2020-21) | 1069.847 | 1223.7236 | 10%-19.9% | 14.38% | 14.38% | 1
14.72% | Replace Teleprotection - TL202 & TL206 | 196.8 | 225.7597 | 10%-19.9% | 14.72% | 14.72% | 1
14.73% | Replace Network Communications Equipment - Various Sites | 199.3 | 228.6491 | 10%-19.9% | 14.73% | 14.73% | 1
15.26% | Refurbish Generator Rotor - HLK | 1340.299 | 1544.8498 | 10%-19.9% | 15.26% | 15.26% | 1
16.16% | Replace Turbine and Generator Control & Vibration Monitoring System - PRV | 238.571 | 277.1194 | 10%-19.9% | 16.16% | 16.16% | 1
16.37% | Overhaul Hydraulic Units (2024) | 323.8 | 376.8143 | 10%-19.9% | 16.37% | 16.37% | 1
16.41% | Replace CCTV Cameras (2024) | 317.6 | 369.7161 | 10%-19.9% | 16.41% | 16.41% | 1
16.47% | Wood Pole Line Management Program - Various Sites | 2467 | 2873.4173 | 10%-19.9% | 16.47% | 16.47% | 1
16.51% | Upgrade Data Alarm Systems - MDR (2020-21) | 326.499 | 380.4052 | 10%-19.9% | 16.51% | 16.51% | 1
16.6% | Phase 2 - EV charging Network | 1581.501 | 1844.0956 | 10%-19.9% | 16.6% | 16.6% | 1
17.08% | Replace TS Battery Banks and Chargers - EHW, HWD, SDP, SHE, SOK | 315.2393 | 369.0905 | 10%-19.9% | 17.08% | 17.08% | 1
17.15% | Upgrade Data Alarm Systems - Various Sites | 308.5 | 361.4071 | 10%-19.9% | 17.15% | 17.15% | 1
17.33% | Purchase Tools and Equipment Less than $50,000 (2023) - Telecontrol | 40.4 | 47.4011 | 10%-19.9% | 17.33% | 17.33% | 1
17.35% | Purchase Tools and Equipment Less than $ 50,000 | 15.4 | 18.0717 | 10%-19.9% | 17.35% | 17.35% | 1
17.49% | Diesel Genset Replacements - Makkovik | 8900.2 | 10456.444 | 10%-19.9% | 17.49% | 17.49% | 1
17.56% | Diesel Genset Replacements (2021-2022) | 2846.8 | 3346.7633 | 10%-19.9% | 17.56% | 17.56% | 1
18.05% | SSL communication Link Upgrade - CAT | 163.1583 | 192.6158 | 10%-19.9% | 18.05% | 18.05% | 1
18.13% | Additions for Load - Isolated Generation Systems | 2182.5 | 2578.1254 | 10%-19.9% | 18.13% | 18.13% | 1
18.44% | Upgrade Equipment Doors - Various Sites | 348.5 | 412.7652 | 10%-19.9% | 18.44% | 18.44% | 1
19.02% | Overhaul Unit 2 - Cat Arm | 326.492 | 388.5783 | 10%-19.9% | 19.02% | 19.02% | 1
19.07% | Replace Standalone PBX Phone Systems (2023) | 175.5 | 208.9658 | 10%-19.9% | 19.07% | 19.07% | 1
19.21% | Purchase Metering and Metering Equipment - Various Sites | 198.5 | 236.6416 | 10%-19.9% | 19.21% | 19.21% | 1
19.83% | Replace Network Communications Equipment - Various | 199.5 | 239.053 | 10%-19.9% | 19.83% | 19.83% | 1
19.93% | Replace Human Machine Interface (2023) - Happy Valley Gas Turbine | 138.6 | 166.2288 | 10%-19.9% | 19.93% | 19.93% | 1
20.27% | Replace Disconnect Switches - Various (2021-22) | 1292.7 | 1554.6703 | 20%-29.9% | 20.27% | 20.27% | 1
20.66% | Upgrade Terminal Station for Mobile Substation - St. Anthony | 492 | 593.6632 | 20%-29.9% | 20.66% | 20.66% | 1
21.26% | Replace Instrument Transformers - Various (2022-23) | 402.3595 | 487.9087 | 20%-29.9% | 21.26% | 21.26% | 1
21.66% | Overhaul Unit 1 Turbine / Valve - Holyrood | 8026.6 | 9765.0063 | 20%-29.9% | 21.66% | 21.66% | 1
21.75% | Refurbish U5 Generatpr Stator -BDE | 5630 | 6854.3221 | 20%-29.9% | 21.75% | 21.75% | 1
22.03% | Install Raw Water Line - Holyrood | 1252.6 | 1528.5458 | 20%-29.9% | 22.03% | 22.03% | 1
22.83% | Replace Unit 2090/2044 - Charlottetown and Mary's Harbour | 401.022 | 492.5594 | 20%-29.9% | 22.83% | 22.83% | 1
23.88% | Wood Pole Line Management Program (2022) | 1603.5 | 1986.4668 | 20%-29.9% | 23.88% | 23.88% | 1
23.95% | Upgrade Data Alarm Systems - HRD (2019-20) | 636.8 | 789.3047 | 20%-29.9% | 23.95% | 23.95% | 1
24.43% | Construct Heated Storage for Spare Parts and Lube Oil - Hardwoods and Happy Valley | 49.8 | 61.9637 | 20%-29.9% | 24.43% | 24.43% | 1
24.76% | Upgrade Fuel Storage Tanks (2022) - Mary's Harbour | 499.1 | 622.6749 | 20%-29.9% | 24.76% | 24.76% | 1
25.13% | Upgrade Public Safety Around Dams and Waterways - BDE | 469.5 | 587.4774 | 20%-29.9% | 25.13% | 25.13% | 1
25.17% | Replace Network Communications Equipment - Various | 194 | 242.8356 | 20%-29.9% | 25.17% | 25.17% | 1
25.47% | Condition Assessment and Miscellaneous Upgrades - Holyrood | 2437.3 | 3058.1091 | 20%-29.9% | 25.47% | 25.47% | 1
26.29% | Replace Network Communications Equipment (2023) | 189 | 238.6899 | 20%-29.9% | 26.29% | 26.29% | 1
26.29% | Replace Automation Equipment - Rigolet | 363.8 | 459.4468 | 20%-29.9% | 26.29% | 26.29% | 1
27.29% | Perform Grounding Upgrades - Various Sites | 293.8 | 373.9864 | 20%-29.9% | 27.29% | 27.29% | 1
27.57% | Inspect Fuel Storage Tanks - Black Tickle | 818.7 | 1044.4445 | 20%-29.9% | 27.57% | 27.57% | 1
27.61% | Transmission In-Service Failures (2023) | 151.7 | 193.5891 | 20%-29.9% | 27.61% | 27.61% | 1
27.99% | Upgrade Compressed Air System - Happy Valley Gas Turbine | 145.8 | 186.6058 | 20%-29.9% | 27.99% | 27.99% | 1
29.07% | Unit 3 Generator Components Condition Assessment and Miscellaneous Upgrades | 422.0236 | 544.6956 | 20%-29.9% | 29.07% | 29.07% | 1
29.17% | Purchase Capital Spares - Hydraulic | 487.4 | 629.5901 | 20%-29.9% | 29.17% | 29.17% | 1
29.37% | Boiler Condition Assessment and Miscellaneous Upgrades - Holyrood | 3014.2 | 3899.3703 | 20%-29.9% | 29.37% | 29.37% | 1
29.64% | Boiler Condition Assessment/Upgrade - Holyrood | 3000 | 3889.2474 | 20%-29.9% | 29.64% | 29.64% | 1
30.06% | Install Frazil Ice Forecast - UPS | 176.987 | 230.1898 | 30%-39.9% | 30.06% | 30.06% | 1
30.32% | HLK-Annunciator Replacement | 371.1331 | 483.6696 | 30%-39.9% | 30.32% | 30.32% | 1
30.46% | Penstock Level II Condition Assessment - PRV | 196.8 | 256.7393 | 30%-39.9% | 30.46% | 30.46% | 1
30.46% | Replace Remote Terminal Units (2023) | 179.7 | 234.4336 | 30%-39.9% | 30.46% | 30.46% | 1
30.64% | Upgrade Station Lighting (2024-2025) - Bottom Waters, Deer Lake, Doyles, Indian River, and Western Avalon Terminal Stations | 520.6 | 680.1284 | 30%-39.9% | 30.64% | 30.64% | 1
31.24% | Refurbish Draft Tube Deck Phase 1 - BDE | 1032.4 | 1354.8981 | 30%-39.9% | 31.24% | 31.24% | 1
31.77% | Replace Accommodations and Septic System - Ebbegunbaeg | 1550.8 | 2043.4628 | 30%-39.9% | 31.77% | 31.77% | 1
32.15% | Hydraulic Unit Overhauls Program (2023) | 975.7 | 1289.4118 | 30%-39.9% | 32.15% | 32.15% | 1
32.74% | Overhaul Unit 1 - BDE | 202 | 268.1303 | 30%-39.9% | 32.74% | 32.74% | 1
32.88% | Replace PH1 Station Service Transformer - Bay d'Espoir | 401.2 | 533.1079 | 30%-39.9% | 32.88% | 32.88% | 1
33% | Replace Roof (2025) - Grey River | 390.8 | 519.7822 | 30%-39.9% | 33% | 33% | 1
33.02% | Upgrade Energy Management System (2022) - Hydro Place | 335.5683 | 446.3595 | 30%-39.9% | 33.02% | 33.02% | 1
33.07% | Replace Electromechanical Timers - Various Sites | 197.8 | 263.2126 | 30%-39.9% | 33.07% | 33.07% | 1
33.4% | Purchase Tools and Equipment Less than $50,000 (2022) | 42 | 56.0279 | 30%-39.9% | 33.4% | 33.4% | 1
33.92% | HRD - Major Overhaul: Unit 3 Extraction Pump North | 142.9 | 191.3764 | 30%-39.9% | 33.92% | 33.92% | 1
34.51% | Upgrade Work - Cat Arm | 1911.3 | 2570.9537 | 30%-39.9% | 34.51% | 34.51% | 1
34.55% | Wood Pole Line Management Program - Various Sites | 2404.1 | 3234.6081 | 30%-39.9% | 34.55% | 34.55% | 1
34.55% | Replace Battery Banks and Chargers - Various | 195.955 | 263.6608 | 30%-39.9% | 34.55% | 34.55% | 1
35.9% | CHT Winterize Unit 2102 and Install Mobile - Supplemental | 1314.7 | 1786.7325 | 30%-39.9% | 35.9% | 35.9% | 1
36.98% | Purchase Tools and Equipment less than $50,000 | 15.7 | 21.5057 | 30%-39.9% | 36.98% | 36.98% | 1
37.48% | Install Sub-Surface Drainage System - Paradise River | 524.9 | 721.6131 | 30%-39.9% | 37.48% | 37.48% | 1
37.56% | Unit 5 Generator Overhaul - BDE | 220.427 | 303.222 | 30%-39.9% | 37.56% | 37.56% | 1
37.76% | Purchase Meters and Metering Equipment - Various Sites | 198.8 | 273.866 | 30%-39.9% | 37.76% | 37.76% | 1
39.51% | Purchase Mobile Devices (2023) | 83.4 | 116.3509 | 30%-39.9% | 39.51% | 39.51% | 1
41.78% | Construction and Installation of an Electric Vehcile Fast Track Network | 259.4 | 367.7847 | 40%-49.9% | 41.78% | 41.78% | 1
41.95% | Replace Programmable Logic Controllers - Various Sites | 958 | 1359.9236 | 40%-49.9% | 41.95% | 41.95% | 1
42.09% | Condition Assessment and Miscellaneous Upgrades - Holyrood | 2749.6 | 3906.9442 | 40%-49.9% | 42.09% | 42.09% | 1
43.72% | In-Service Failures - Various Sites | 1000 | 1437.207 | 40%-49.9% | 43.72% | 43.72% | 1
45.61% | Install Automated Meter Reading - Labrador West | 967.2 | 1408.3221 | 40%-49.9% | 45.61% | 45.61% | 1
45.9% | Labrador City L22 Voltage Conversion (2022-2023) | 1491.2 | 2175.6355 | 40%-49.9% | 45.9% | 45.9% | 1
46.85% | Install Anemometer (2024) - Cat Arm | 68.6 | 100.7424 | 40%-49.9% | 46.85% | 46.85% | 1
46.99% | Replace Holyrood Thermal Generating Station T2 | 1393.157 | 2047.8321 | 40%-49.9% | 46.99% | 46.99% | 1
47.04% | Upgrade Uninterruptible Power Supply 3 & 4 - Holyrood | 348.7 | 512.7327 | 40%-49.9% | 47.04% | 47.04% | 1
47.52% | Replace Monorail Beams & Associated Mounts SRS - BDE | 592.8804 | 874.5932 | 40%-49.9% | 47.52% | 47.52% | 1
48.17% | Boiler Condition Assessment and Miscellaneous Upgrades (2023) - Holyrood | 2926.6 | 4336.3612 | 40%-49.9% | 48.17% | 48.17% | 1
48.67% | Upgrade Core OT Infrastructure (2023) | 171.7 | 255.2619 | 40%-49.9% | 48.67% | 48.67% | 1
49.42% | Condition Assessment and Miscellaneous Upgrades - Holyrood | 1968.8 | 2941.7036 | 40%-49.9% | 49.42% | 49.42% | 1
49.92% | Inspect Fuel Tanks (2024) - Hardwoods Gas Turbines | 692.9 | 1038.7661 | 40%-49.9% | 49.92% | 49.92% | 1
50.24% | Install Oil Spill Containment Transformer T1S (2023-2024) - Cat Arm | 581.6 | 873.8137 | 50%-59.9% | 50.24% | 50.24% | 1
50.38% | Refresh Cyber Security Infrastructure (2022) - Hydro Place | 221.7 | 333.3953 | 50%-59.9% | 50.38% | 50.38% | 1
51.37% | Diesel In-Service Failures (2023) | 480.4 | 727.1768 | 50%-59.9% | 51.37% | 51.37% | 1
51.54% | Install Variable Frequency Drives - Grey River | 169.9 | 257.4728 | 50%-59.9% | 51.54% | 51.54% | 1
52.4% | Refurbish Surge Tank 1 (2024-2025) - Bay d'Espoir | 2287.2 | 3485.6652 | 50%-59.9% | 52.4% | 52.4% | 1
52.71% | Penstock 3 Press Transducer - Bay d'Espoir | 29.5 | 45.0508 | 50%-59.9% | 52.71% | 52.71% | 1
52.75% | Perform Grounding Upgrades - Various Sites | 1719.4 | 2626.3449 | 50%-59.9% | 52.75% | 52.75% | 1
54.85% | Inspect Fuel Tanks (2025) - Stephenville | 676.9 | 1048.1662 | 50%-59.9% | 54.85% | 54.85% | 1
55.42% | Upgrade Station Lighting - BUCTS and HWDTS (2022-23) | 202.6364 | 314.9315 | 50%-59.9% | 55.42% | 55.42% | 1
55.54% | Upgrade Fault Recorders - WABTS (2022-2023) | 422.4 | 656.9887 | 50%-59.9% | 55.54% | 55.54% | 1
56.09% | Inspect Fuel Storage Tanks - Gray River | 203.1 | 317.0214 | 50%-59.9% | 56.09% | 56.09% | 1
56.11% | Replace Terminal Station Lighting (2023-2024) | 917.4 | 1432.1492 | 50%-59.9% | 56.11% | 56.11% | 1
58.2% | Replace Metering System | 5875.8 | 9295.4733 | 50%-59.9% | 58.2% | 58.2% | 1
58.32% | Replace Instrument Transformers - Various (2021-22) | 460.9 | 729.6884 | 50%-59.9% | 58.32% | 58.32% | 1
58.77% | Replace Sewage Lift System - Rigolet | 127.926 | 203.1138 | 50%-59.9% | 58.77% | 58.77% | 1
58.95% | Upgrade Data Alarm Management - OPD (2021-22) | 353.309 | 561.5813 | 50%-59.9% | 58.95% | 58.95% | 1
59.38% | Replace HVAC System (2023-2024) - Bishop's Falls | 172.2 | 274.4595 | 50%-59.9% | 59.38% | 59.38% | 1
61.09% | Replace Powerhouse Station Service Panel (2023-2024) - Upper Salmon | 1568.5 | 2526.6794 | 60%-69.9% | 61.09% | 61.09% | 1
63.8% | Upgrade of Worst-Performing Distribution Feeders (2021-2022) | 1124.5 | 1841.9017 | 60%-69.9% | 63.8% | 63.8% | 1
64.73% | Hydraulic In-Service Failures | 1250 | 2059.1178 | 60%-69.9% | 64.73% | 64.73% | 1
64.94% | Upgrade Bear Brook Crossing | 435.354 | 718.0934 | 60%-69.9% | 64.94% | 64.94% | 1
65% | Upgrade Public Safety Around Dams and Waterways (2023) | 482.1 | 795.4595 | 60%-69.9% | 65% | 65% | 1
67.68% | Replace Secondary Containment System Liner - Nain | 3089.6 | 5180.7068 | 60%-69.9% | 67.68% | 67.68% | 1
68.78% | Replace Frazil Ice Monitor System - HLK | 199.5 | 336.7249 | 60%-69.9% | 68.78% | 68.78% | 1
71.57% | General Property Rehabilitation (2024) - Hydro Place | 234 | 401.482 | 70%-79.9% | 71.57% | 71.57% | 1
71.63% | Replace Annunciator Panels (2024-2025) - Cat Arm | 351.4 | 603.0922 | 70%-79.9% | 71.63% | 71.63% | 1
71.98% | Purchase Tools and Equipment Less than $ 50,000 | 21 | 36.1166 | 70%-79.9% | 71.98% | 71.98% | 1
74.46% | Terminal Station In-Service Failures | 1000 | 1744.6067 | 70%-79.9% | 74.46% | 74.46% | 1
75.53% | Replace Transformer T7 - HRD | 2678.14 | 4701.0658 | 70%-79.9% | 75.53% | 75.53% | 1
75.74% | Replace Building Exterior (2023-2024) - Postville | 683.3 | 1200.8386 | 70%-79.9% | 75.74% | 75.74% | 1
76.35% | Construct LO Cooler Hood - Holyrood Gas Turbine | 318.8 | 562.2037 | 70%-79.9% | 76.35% | 76.35% | 1
78.5% | Replace Protective Relays - Various Sites | 1857 | 3314.7093 | 70%-79.9% | 78.5% | 78.5% | 1
80.07% | Wood Pole Line Management Program (2023) | 2824.4 | 5085.8377 | 80%-89.9% | 80.07% | 80.07% | 1
80.53% | Replace Underground Fire Water Distribution System - Holyrood | 1706.3 | 3080.4524 | 80%-89.9% | 80.53% | 80.53% | 1
82.2% | Replace Intermediate Fuel Storage Tanks (2023-2024) - Nain | 721.1 | 1313.8397 | 80%-89.9% | 82.2% | 82.2% | 1
82.21% | Replace Emergency Lift (2023) - Salmon River Spillway | 49.8 | 90.7418 | 80%-89.9% | 82.21% | 82.21% | 1
84.76% | Major Pumps Overhaul - Holyrood | 491.3 | 907.7166 | 80%-89.9% | 84.76% | 84.76% | 1
86.19% | Thermal In-Service Failures | 1250 | 2327.4256 | 80%-89.9% | 86.19% | 86.19% | 1
87.95% | Upgrade Breaker Failure Protection (2020-2021) | 510.169 | 958.8475 | 80%-89.9% | 87.95% | 87.95% | 1
92.6% | Overhaul Pumps (2023) - Holyrood | 742.4 | 1429.8882 | 90%-99.9% | 92.6% | 92.6% | 1
92.78% | Replace Pump House and Associated Equipment - Bay d'Espoir | 545.2 | 1051.0373 | 90%-99.9% | 92.78% | 92.78% | 1
96.78% | Refurbish BioGreen Sewage System (2023) - Holyrood | 256.6 | 504.9448 | 90%-99.9% | 96.78% | 96.78% | 1
103.6% | Replace Instrument Transformers - Various (2020-21) | 339.054 | 690.3462 | >100% | 103.6% | 103.6% | 0
104.8% | Upgrade Underground Plant Drainage System - Holyrood | 923.1 | 1890.807 | >100% | 104.8% | 104.8% | 0
108.3% | Water System Condition Assessment and Upgrades (2023) - Bay d'Espoir | 665.9 | 1387.0284 | >100% | 108.3% | 108.3% | 0
109.7% | Upgrade SCADA Network (2024) | 402.3 | 843.668 | >100% | 109.7% | 109.7% | 0
115.9% | Upper Salmon Hydroelectric Generating Station Rotor Rim Shrink and Stator Recentering - Supplemental | 4236.3289 | 9146.6379 | >100% | 115.9% | 115.9% | 0
116% | Thermal In-Service Failures | 1250 | 2699.9082 | >100% | 116% | 116% | 0
119% | Terminal Station In-Service Failures (2023) | 1300 | 2846.6948 | >100% | 119% | 119% | 0
120.1% | Perform Grounding Upgrades - Various (2019-20) | 1845.5 | 4061.3314 | >100% | 120.1% | 120.1% | 0
122.8% | Purchase Tools and Equipment Less than $50,000 (2023) - Thermal Plants | 55.1 | 122.782 | >100% | 122.8% | 122.8% | 0
126.9% | Terminal Station In-Service Failures | 1000 | 2268.9446 | >100% | 126.9% | 126.9% | 0
150.4% | Overhaul Unit 6 - BDE | 225.4 | 564.4001 | >100% | 150.4% | 150.4% | 0
151.6% | Refurbish Sump Level Control System - Cat Arm | 355.923 | 895.6326 | >100% | 151.6% | 151.6% | 0
156.5% | Replace Data Alarm System Annunciators (2023) - Buchans | 166 | 425.808 | >100% | 156.5% | 156.5% | 0
172.1% | Hydraulic In-Service Failures (2023) | 1500 | 4081.0911 | >100% | 172.1% | 172.1% | 0
186.3% | Install Breaker Failure Protection - Various Sites | 277 | 793.1427 | >100% | 186.3% | 186.3% | 0
186.7% | Draft Tube Deck Substructure Level 2 Condition Assessment | 343.6 | 984.9386 | >100% | 186.7% | 186.7% | 0
190.4% | Thermal In-Service Failure - Holyrood | 2000 | 5807.515 | >100% | 190.4% | 190.4% | 0
219.4% | Install Remote Seepage Monitoring System - BDE | 394.7 | 1260.66 | >100% | 219.4% | 219.4% | 0
410% | Install Breaker Failure Protection (2023-2024) - Sunnyside | 289.7 | 1477.4993 | >100% | 410% | 410% | 0
947.9% | Gas Turbine In-Service Failures (2023) | 344.2 | 3606.7459 | >500% | 947.9% | 947.9% | 0
-0.6623% | Additions for Load Growth - Bottom Waters | 3045 | 3024.8317 | (9.9%-0.01%) | -0.6623% | -0.6623% | 1
-0.6907% | Exciter Controls Replacement - Holyrood | 1349.2 | 1339.8812 | (9.9%-0.01%) | -0.6907% | -0.6907% | 1
-19.32% | Unit 3 Turbine Rehabilitation - Bay d'Espoir | 2361.5 | 1905.3701 | (19.9%-10%) | -19.32% | -19.32% | 1
-60.43% | Penstock #2 Refurbishment - Bay d'Espoir | 9063.7 | 3586.3227 | (69.9%-60%) | -60.43% | -60.43% | 1
-44.83% | Repair and Advanced Overhaul of the Happy Valley Gas Turbine | 3714.8 | 2049.2883 | (49.9%-40%) | -44.83% | -44.83% | 1
48.81% | Reliability Improvements - Holyrood | 2610 | 3883.9136 | 40%-49.9% | 48.81% | 48.81% | 1
5.517% | Purchase of 12 MW Diesel Generation - Holyrood | 4700 | 4959.3215 | 0%-9.9% | 5.517% | 5.517% | 1
-32.63% | Terminal Station Upgrades - Wabush | 2912.5 | 1962.0603 | (39.9%-30%) | -32.63% | -32.63% | 1
-1.983% | Perform Voltage Conversion of the Distribution Feeder VA26 - Labrador City | 719.4 | 705.1371 | (9.9%-0.01%) | -1.983% | -1.983% | 1
-34.94% | Improve Boiler Capacity - Holyrood | 2560.5 | 1665.9473 | (39.9%-30%) | -34.94% | -34.94% | 1
-56.4% | Gang Switch - Happy Valley-Goose Bay | 195.4 | 85.1934 | (59.9%-50%) | -56.4% | -56.4% | 1
62.98% | Hinds Lake Unit Major Overhaul | 259.5 | 422.9321 | 60%-69.9% | 62.98% | 62.98% | 1
-28.93% | Level II Condition Assessments for Bay d'espoir Penstock 4, Granite Canal Penstock, and Hinds Lake Penstock | 414.3 | 294.4446 | (29.9%-20%) | -28.93% | -28.93% | 1
6.615% | TL226 and TL239 Reroute | 932.4 | 994.0751 | 0%-9.9% | 6.615% | 6.615% | 1
63.54% | Penstock Condition Assessments - Bay d'Espoir | 1120.6 | 1832.673 | 60%-69.9% | 63.54% | 63.54% | 1
24.13% | Mary's Harbour Hydro Integration - CIAC | 195.5 | 242.67 | 20%-29.9% | 24.13% | 24.13% | 1
20.91% | Construction of a line extension and the installation of power usage monitoring and control equipment at the BlockLab site | 244 | 295.0094 | 20%-29.9% | 20.91% | 20.91% | 1
8.212% | Overhaul Unit 2 Turbine Valves - Holyrood | 2919.5 | 3159.2509 | 0%-9.9% | 8.212% | 8.212% | 1
8.972% | Overhaul Unit 2 Generator - Holyrood | 1294.1 | 1410.2104 | 0%-9.9% | 8.972% | 8.972% | 1
0.4214% | Overhaul Unit 3 Boiler Feed Pump West - Holyrood | 367.9 | 369.4504 | 0%-9.9% | 0.4214% | 0.4214% | 1
5.381% | Boiler Condition Assessment and Miscellaneous Upgrades - Holyrood | 3056.7 | 3221.1775 | 0%-9.9% | 5.381% | 5.381% | 1
-17.11% | Diesel Plant Fibre Upgrade - Nain | 44.773 | 37.1142 | (19.9%-10%) | -17.11% | -17.11% | 1
25.2% | Holyrood Overhaul Unit 1 boiler feed pump | 443.022 | 554.6588 | 20%-29.9% | 25.2% | 25.2% | 1
0% | CHT Purchase Diesel | 350 | 350 | 0%-9.9% | 0% | 0% | 1
-35.61% | Increase Fuel and Water Treatment System Capacity - Holyrood Gas Turbine | 11842.6 | 7625.4773 | (39.9%-30%) | -35.61% | -35.61% | 1
34.33% | Replace Automation Equipment - St. Anthony | 1873.3 | 2516.4073 | 30%-39.9% | 34.33% | 34.33% | 1
13.59% | Muskrat Falls to Happy Valley Interconnection | 19978.5 | 22693.8395 | 10%-19.9% | 13.59% | 13.59% | 1
302.9% | Terminal Station In-Service Failures (2022) | 900 | 3626.0948 | >100% | 302.9% | 302.9% | 0
42.58% | Hydraulic Generation In-Service Failures (2022) | 1000 | 1425.7794 | 40%-49.9% | 42.58% | 42.58% | 1
44.69% | Thermal In-Service Failures (2022) | 2000 | 2893.7743 | 40%-49.9% | 44.69% | 44.69% | 1
-25.59% | Upgrades for Future Retirement of Stephenville Gas Turbine | 6874.9 | 5115.5786 | (29.9%-20%) | -25.59% | -25.59% | 1
-82.99% | Replace Diesel Shop Building (2023-2025) - Bishop's Falls | 1422.1 | 241.8687 | (89.9%-80%) | -82.99% | -82.99% | 1
62.62% | Remove Safety Hazards (2024) | 198.3 | 322.4833 | 60%-69.9% | 62.62% | 62.62% | 1
306.4% | Diesel In-Service Failures (2024) | 488.3 | 1984.5096 | >100% | 306.4% | 306.4% | 0
1884% | Gas Turbine In-Service Failures (2024) | 358 | 7101.6794 | >500% | 1884% | 1884% | 0
98.26% | Hydraulic In-Service Failures (2024) | 1500 | 2973.945 | 90%-99.9% | 98.26% | 98.26% | 1
-98.74% | Upgrade Energy Management System (2024) | 366.4 | 4.6125 | (99.9%-90%) | -98.74% | -98.74% | 0
177.7% | Telecommunications In-Service Failure (2024) | 91.4 | 253.8086 | >100% | 177.7% | 177.7% | 0
89.17% | Terminal Station In-Service Failures (2024) | 1300 | 2459.2469 | 80%-89.9% | 89.17% | 89.17% | 1
2.362% | Transmission In-Service Failures (2024) | 158.5 | 162.2437 | 0%-9.9% | 2.362% | 2.362% | 1
30.75% | Thermal In-Service Failures (2024) | 3508.7 | 4587.7513 | 30%-39.9% | 30.75% | 30.75% | 1
-14.54% | Replace Light- and Heavy-Duty Vehicles (2022-2024) | 3481.8 | 2975.6269 | (19.9%-10%) | -14.54% | -14.54% | 1
34.95% | Replace Instrument Transformers VAR 23/24 | 508.2 | 685.8358 | 30%-39.9% | 34.95% | 34.95% | 1
65.65% | Replace Disconnects 23/24 | 652.8 | 1081.3524 | 60%-69.9% | 65.65% | 65.65% | 1
-5.028% | Replace Terminal Station Battery Banks/Chargers | 218.2 | 207.23 | (9.9%-0.01%) | -5.028% | -5.028% | 1
44.68% | Upgrade of Worst-Performing Distribution Feeders (2023-2024) | 1446 | 2092.0239 | 40%-49.9% | 44.68% | 44.68% | 1
4.957% | Replace Mobile Equipment (2023-2024) | 728.5 | 764.6125 | 0%-9.9% | 4.957% | 4.957% | 1
22.46% | Upgrade Power Transformers 23/24 | 3979.3 | 4872.9742 | 20%-29.9% | 22.46% | 22.46% | 1
46.35% | Circuit Breakers Renewal Program 23/24 | 3812 | 5578.6897 | 40%-49.9% | 46.35% | 46.35% | 1
47.43% | Replace Protective Relays - M24 | 1959.7 | 2889.149 | 40%-49.9% | 47.43% | 47.43% | 1
56.81% | Overhaul Diesel Units -Var 24 | 829.2 | 1300.3095 | 50%-59.9% | 56.81% | 56.81% | 1
36.06% | Wood Pole Line Management (2024) | 3765.2 | 5122.7667 | 30%-39.9% | 36.06% | 36.06% | 1
-61% | Perform Software Upgrades and Minor Enhancements (2024) | 864.2 | 337.0688 | (69.9%-60%) | -61% | -61% | 1
-15.21% | Upgrade Core OT Infrastructure (2024) | 174.7 | 148.1279 | (19.9%-10%) | -15.21% | -15.21% | 1
45.57% | Update Cyber Security Infrastructure (2024) | 281.3 | 409.501 | 40%-49.9% | 45.57% | 45.57% | 1
30.16% | Replace Network Communications Equipment (2024) | 180.7 | 235.1952 | 30%-39.9% | 30.16% | 30.16% | 1
-9.602% | Minor Telecommunications Enhancements (2024) | 96.9 | 87.5957 | (9.9%-0.01%) | -9.602% | -9.602% | 1
7.048% | Purchase Mobile Devices (2024) | 155.6 | 166.5659 | 0%-9.9% | 7.048% | 7.048% | 1
98.71% | Boiler Condition Assessment and Miscellaneous Upgrades (2024) - Holyrood | 3957.8 | 7864.5455 | 90%-99.9% | 98.71% | 98.71% | 1
-79.62% | Overhaul Pumps (2024) - Holyrood | 661 | 134.7362 | (79.9%-70%) | -79.62% | -79.62% | 1
-40.02% | Replace 48 V Battery Banks and Chargers (2024) | 422.2 | 253.2494 | (49.9%-40%) | -40.02% | -40.02% | 1
-5.88% | Purchase Meters and Metering Equipment (2024) | 470.7 | 443.0241 | (9.9%-0.01%) | -5.88% | -5.88% | 1
20.87% | Upgrade Remote Terminal Units (2024) | 165.9 | 200.5309 | 20%-29.9% | 20.87% | 20.87% | 1
182.3% | Holyrood Fuel Tank #1 Fuel Inspection And Refurbishment - Supplemental | 2052.1 | 5793.7505 | >100% | 182.3% | 182.3% | 0
-15.11% | Purchase Tools and Equipment Less than $50,000 (2024) - Hydraulic Plants | 209.4 | 177.7685 | (19.9%-10%) | -15.11% | -15.11% | 1
-2.392% | Purchase Tools and Equipment Less than $50,000 (2024) - Telecontrol | 45.6 | 44.5092 | (9.9%-0.01%) | -2.392% | -2.392% | 1
4.428% | Purchase Tools and Equipment Less than $50,000 (2024) - Gas Turbine | 18.6 | 19.4235 | 0%-9.9% | 4.428% | 4.428% | 1
-8.875% | Purchase Tools and Equipment Less than $50,000 (2024) - Thermal Plants | 167.1 | 152.2695 | (9.9%-0.01%) | -8.875% | -8.875% | 1
10.12% | Purchase Office Equipment Less Than $50,000 (2024) | 50 | 55.0579 | 10%-19.9% | 10.12% | 10.12% | 1
-61.42% | Perform Office Modifications (2024) - Hydro Place | 249.809 | 96.367 | (69.9%-60%) | -61.42% | -61.42% | 1
-79.36% | Terminal Station In-Service Failures (2025) | 2500 | 516.0051 | (79.9%-70%) | -79.36% | -79.36% | 1
-21.57% | Thermal In-Service Failures (2025) | 3900 | 3058.7405 | (29.9%-20%) | -21.57% | -21.57% | 1
-18.18% | Telecommunications In-Service Failures (2025) | 94.1 | 76.9914 | (19.9%-10%) | -18.18% | -18.18% | 1
-11.92% | Transmission In-Service Failures (2025) | 184.3 | 162.3248 | (19.9%-10%) | -11.92% | -11.92% | 1
-5.196% | Diesel In-Service Failures (2025) | 800 | 758.4302 | (9.9%-0.01%) | -5.196% | -5.196% | 1
273.6% | Gas Turbine In-Service Failures (2025) | 500 | 1868.1898 | >100% | 273.6% | 273.6% | 0
-5.407% | Supply & Install New Work Stations Level 4 Hydro Place (2025) | 747.767 | 707.3335 | (9.9%-0.01%) | -5.407% | -5.407% | 1
36.97% | Additions for Load - Distribution Systems (2024-2026) - Main Brook | 353.02 | 483.5244 | 30%-39.9% | 36.97% | 36.97% | 1
-1.543% | Procure Stop Logs for Bay D'Espoir Units 1-7 | 740 | 728.584 | (9.9%-0.01%) | -1.543% | -1.543% | 1
3.157% | Purchase & Install Site Radio System (2024) - Holyrood | 412.2 | 425.2118 | 0%-9.9% | 3.157% | 3.157% | 1
7.871% | Completion of Fire Restoration – Fourth Floor Hydro Place | 1067.9 | 1151.9531 | 0%-9.9% | 7.871% | 7.871% | 1
-22.96% | Install Additional Fuel Tank Ramea (2025) | 232.5 | 179.1124 | (29.9%-20%) | -22.96% | -22.96% | 1
30.49% | Upgrade DCS Hardware - Units 1 and 2 (2024-2025) - Holyrood | 472.5 | 616.5842 | 30%-39.9% | 30.49% | 30.49% | 1
67.26% | Upgrade Worst-Performing Distribution Feeders (2024-2025) | 3291.7 | 5505.7124 | 60%-69.9% | 67.26% | 67.26% | 1
-3.911% | Renew Distribution Feeders (2024-2025) | 2532.4 | 2433.3572 | (9.9%-0.01%) | -3.911% | -3.911% | 1
-49.01% | Additions for Load (2022) - Mary's Harbour Service Conductor | 359.1 | 183.1224 | (49.9%-40%) | -49.01% | -49.01% | 1
-15.89% | Additions for Load - Wabush Substation Upgrades | 10694.1 | 8995.2589 | (19.9%-10%) | -15.89% | -15.89% | 1
-41.02% | Update Cyber Security Infrastructure (2025) | 115.6 | 68.185 | (49.9%-40%) | -41.02% | -41.02% | 1
-40.45% | Replace Network Communications Equipment (2025) | 413.2 | 246.0502 | (49.9%-40%) | -40.45% | -40.45% | 1
-34.81% | Purchase Tools and Equipment (2025) - Gas Turbines | 46.6 | 30.3801 | (39.9%-30%) | -34.81% | -34.81% | 1
-30.08% | Perform Software Upgrades and Minor Enhancements (2025) | 808.7 | 565.4577 | (39.9%-30%) | -30.08% | -30.08% | 1
-20.96% | Purchase Tools and Equipment (2025) - Thermal Plants | 127.3 | 100.6117 | (29.9%-20%) | -20.96% | -20.96% | 1
45.68% | Upgrade Power Transformers (2024-2025) | 3575.9 | 5209.2209 | 40%-49.9% | 45.68% | 45.68% | 1
-17.31% | Purchase Mobile Devices (2025) | 160.2 | 132.4761 | (19.9%-10%) | -17.31% | -17.31% | 1
-1.429% | Renew Circuit Breakers (2024–2025) | 2304 | 2271.086 | (9.9%-0.01%) | -1.429% | -1.429% | 1
-11.87% | Diesel Genset Replacement Unit 2012 - L'Anse-Au-Loup | 3063.3 | 2699.8056 | (19.9%-10%) | -11.87% | -11.87% | 1
-7.773% | Upgrade Core OT Infrastructure (2025) | 674.3 | 621.8872 | (9.9%-0.01%) | -7.773% | -7.773% | 1
-6.226% | Perform Security Improvements (2025) | 160.7 | 150.6949 | (9.9%-0.01%) | -6.226% | -6.226% | 1
-2.902% | Perform Minor Telecommunications Enhancements (2025) | 99.8 | 96.904 | (9.9%-0.01%) | -2.902% | -2.902% | 1
126.3% | Overhaul Unit 1 Turbine Valves and Generator (2024) - Holyrood | 5181.4 | 11724.3023 | >100% | 126.3% | 126.3% | 0
30.17% | Overhaul Unit 2 Turbine and Valves (2023) - Holyrood | 9701.8 | 12628.3989 | 30%-39.9% | 30.17% | 30.17% | 1
1.059% | Upgrade Remote Terminal Units (2025) | 238.4 | 240.9255 | 0%-9.9% | 1.059% | 1.059% | 1
1.342% | Replace 48 V Battery Banks and Chargers (2025) | 559.1 | 566.6032 | 0%-9.9% | 1.342% | 1.342% | 1
1.609% | Purchase Tools and Equipment (2025) - Telecontrol | 45.3 | 46.029 | 0%-9.9% | 1.609% | 1.609% | 1
10.23% | Overhaul Diesel Units (2025) | 1000 | 1102.2838 | 10%-19.9% | 10.23% | 10.23% | 1
48.88% | Replace Protective Relays (2024–2025) | 3439.1 | 5120.0159 | 40%-49.9% | 48.88% | 48.88% | 1
20.15% | Modify Office Buildings and Procure Furniture, Fixtures, & Equipment (2025) | 178.5 | 214.4658 | 20%-29.9% | 20.15% | 20.15% | 1
23.88% | Purchase Tools and Equipment (2025) - Hydraulic Plants | 154.9 | 191.8962 | 20%-29.9% | 23.88% | 23.88% | 1
8.355% | Replace Mobile Equipment (2024-2025) | 816.6 | 884.8293 | 0%-9.9% | 8.355% | 8.355% | 1
36.16% | Hydraulic In-Service Failures (2025) | 2000 | 2723.2428 | 30%-39.9% | 36.16% | 36.16% | 1
37.28% | Wood Pole Line Management (2025) | 4281.3 | 5877.517 | 30%-39.9% | 37.28% | 37.28% | 1
50.33% | Replace Disconnects (2024–2025) | 1485.5 | 2233.1765 | 50%-59.9% | 50.33% | 50.33% | 1
19.21% | Replace Light- and Heavy-Duty Vehicles (2023-2025) | 4566 | 5443.1925 | 10%-19.9% | 19.21% | 19.21% | 1
64.82% | Perform Boiler Condition Assessment and Miscellaneous Upgrades (2025) - Holyrood | 4905.8 | 8085.6781 | 60%-69.9% | 64.82% | 64.82% | 1
67.37% | Remove Safety Hazards (2025) | 203.3 | 340.2559 | 60%-69.9% | 67.37% | 67.37% | 1
54.54% | Replace Instrument Transformers (2024–2025) | 869.7 | 1344.0434 | 50%-59.9% | 54.54% | 54.54% | 1
56.66% | Replace Terminal Station Battery Banks and Chargers (2024–2025) | 192.7 | 301.8753 | 50%-59.9% | 56.66% | 56.66% | 1
156.5% | Overhaul Major Pumps (2025) - Holyrood | 1101.9 | 2826.12 | >100% | 156.5% | 156.5% | 0
-13.88% | Provide Service to Western Regional Servce Board's Waste Transfer Site - Hampden | 748.4 | 644.5 | (19.9%-10%) | -13.88% | -13.88% | 1
Grand Total |  | 1268186.7225 | 1250322.3177